## DC
NAME | SALES REP | COUNTY | STATE | NTP | HOA | Interconnection | Design | Permit | Installation | Inspection | Meter Change | Access | Registration | PTO Uploaded | SRECs | MD Grant | QA | CANCELLED | PEARL CERTIFICATION
Angel M Lima - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done
Dan Notestein - CASH | Sam Albert | Montgomery County/Town of Blacksburg |  | N/A | approved | Approved VTES | Done | issued | Installation Completed
Juan L Guillen - GL | Thirza Iglesias | Frederick County |  | APPROVED 1.21 | approved | Approved Rappahannock | Done | issued | Installation Completed | Passed | Applied
Fizel Jabbar - DV | Aaron Dawkins | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | site created |  | Done | Done | Done |  |  | Done
Jose Chacon - GL | Carlos Cueto | PG County |  |  | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Julio Fuentes - GL | Carlos Cueto | Montgomery County |  | APPROVED 1.07 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Misael Guillermo - SN | Thornton Fennell | PG County |  |  | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Payment pending | Payment pending |  |  | Done
Willie Ford - GL | Thornton Fennell | PG County |  | APPROVED 1.05 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Yolanda Zelaya - GL | Sarah Romero | PG County |  | APPROVED 1/10 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Mark Reid - GL | Aaron Dawkins | PG County |  | CANCELED |  |  | Done | [10 empty] | YES
Lynne Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 1/20 | N/A | Approved-Pepco | Done | Issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | Done
Raymond Marquis - GL | Noblesolar | Norfolk County |  | APPROVED 2.4 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Jessie Miles - GL | Noblesolar | Norfolk County |  | APPROVED 1/12 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Yilia Jackson - SN | Ted Brown | Baltimore City |  | N/A | NA | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | done |  | Done
Ronny/Taylor Sylvester - GL | Noblesolar | Chesapeake City |  | APPROVED 2.8 | NA | Approved Dominion | Done | Issued | Installation Completed | Passed | Applied | Done |  | Received | Done
Kathryn Alexander - CASH | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Charles Cucina - DV | Danny Dubois | FrederickCounty |  | N/A | NA | Approved Potomac | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Miguel Angel Vernal Nolasco - GL | Sarah Romero | Baltimore County |  | LOAN CANCELED | NA | Have bill | [11 empty] | Yes
Juan Martinez - DV | Sarah Romero | Winchester City |  | N/A | NA | Approved SVEC | Done | issued | Scheduled 6/9
Jose H. Baca Oseguera - GL | Ana Romero | PG County |  | APPROVED 2.8 | NA | Approved-Pepco |  | issued | Installation Completed | Passed | Applied | Done | [6 empty] | Done
Oluseyi Ajayi - GL | Noblesolar | Chesapeake City |  | APPROVED 1.28 | applied | Approved Dominion 02/15/2022 | DONE | Issued | NA
Darryl Girtz - GL | Noblesolar | Norfolk City |  | APPROVED 1.31 | NA | Approved Dominion | Done | Applied-1/24 | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Gerry Evans - GL | Noblesolar | Newport News City |  | APPROVED 1.24 | approved | Approved Dominion | Done | issued | Installation Completed
Matthew Griffin - GL | Noblesolar | VA Beach City |  | APPROVED 1.25 | NA | Approved Dominion | Done | issued | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Donald Deely - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done | Issued | TBS
Brayan Godines - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | done |  | Done | Done | Done |  |  | Done
Matthew Gomez - SL | Roberto Smith | PG County |  | APPROVED 1.24 | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Maxie Lawton -GL | Volt (Ishmael) | PG County |  | APPROVED 1.24 | approved | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Engracio Edesar Abris - DV | Danny Dubois | Arlington County |  | N/A | NA | Approved 03/01/2022 | Done | issued | Installation Completed | Passed |  | Done | [6 empty] | Done
Chris Luk - Cash | Richard Thrutchley | Fairfax County |  | N/A | approved | Approved Dominion | Done | issued | Scheduled 6/3 |  |  | Done
Nabil Ahmed - SL | Roberto Smith | Montgomery County |  | APPROVED 1.28 | approved | Approved Potomac | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | DONE | Done |  |  | Done
Sharon Flowers - DV | Jedi | PG County |  | CANCELED | applied | Approved-BGE | Done | issued
Maricela Pena - GL | Sarah Romero | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | [9 empty] | Done
Malik Abdunafi - SL | Jedi | Baltimore City |  | APPROVED 2.7 | NA | Approved-BGE | Done | Issued | TBS
Delphine London - NS | Noblesolar | VA Beach City |  | APPROVED 2.7 | approved | Approved Dominion | Done |  | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Gary Hill - GL | Noblesolar | York County |  | APPROVED 1.28 | APPROVED | Approved Dominion | Done | applied | Installation Completed
Carmen Bona - SN | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Applied PECO | Done
Tyleek Harris - GL | Noblesolar | Newport News City |  | APPROVED 2.7 | applied | Approved Dominion | Done | issued
Harrison Eacho - GL | Noblesolar | Norfollk City |  | APPROVED 1/28 | NA | Applied Dominion | Done
Olawole Olayinka - GL | Volt Solar (Freddye) | Howard County |  | APPROVED 1/28 | approved | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | V.S
Justin Shoemaker - GL | Noblesolar | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | N.S
Adewale Daramola - GL | Noblesolar | Chesapeake City |  | APPROVED 1.31.22 | applied | Approved Dominion | Done
Silvia Rivera - DV | Sarah Romero | City of Frederick |  | N/A | NA | Approved-Potomac Edison | Done | issued | TBS
Darwin A Fuentes - GL | Alberto Sosa | PG County |  | APPROVED 2.3 | NA |  | Dropbox | issued | [9 empty] | Yes
Charles Hiller - EZ | Sam Albert | Pike County |  | Declined by EZSolarLoan | NA | Applied Met-Ed | Done | [10 empty] | Yes
John Coombs - SL | Roberto Smith | Baltimore County |  | APPROVED 2.1 | NA | Approved-BGE | Done | issued | Installation Completed | [9 empty] | Done
Amy Cervantes - EZ | Sam Albert | Distric of Columbia County | DC | N/A | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Eli Apuya - GL | Noblesolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Done
Brett Dash - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved dominion | Drop Box
Alexander Vasquez Fernandez - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved-dominion | Done
Taiwo Olayinka - GL | Volt Solar (Freddye) | Anne Arundel County |  | APPROVED 2.2 | approved | Approved-BGE | Done | in review | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jessica Green - SN | USA Solar Network | Westmoreland County |  | CANCELED | N/A | Applied - Westpenn Power | Drop Box | issued
William Bryan - GL | USA Solar Network | Bucks County |  | APPROVED 2.3 | N/A | Applied PECO | Done | issued
Kimberly Hayes - GL | USA Solar Network | Luzerne County |  | APPROVED 2..3 | N/A | Approved PPL WO 58650550 | Done | issued | Installation Completed | [9 empty] | U.S solar network
Devin Sharp - GL | USA Solar Network | Pittsylvania County |  | CANCELED | NA | Have Bill Danvill | ELD On Hold | [10 empty] | Yes
James Spadoni - GL | USA Solar Network | Northampton County |  | APPROVED 2.4 | N/A | Applied Met ED | Done
Edward Coley - CASH | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Approved PECO | Done |  | TBS - Roof Pending
Christopher Doane - GL | NobleSolar | Suffolk City |  | APPROVED 2.4 | applied | Approved-dominion | Drop Box
David Nicklas - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done
Margaret Galega - SL | Joseph Allo | PG County |  | APPROVED 2.4 | applied | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Raymond Kabacinski - GL | NobleSolar | Norfolk City |  | APPROVED 2.7 | NA | Approved-dominion | Done | B-issued | Installation Completed |  | Applied | Site Created |  | Received | DONE |  |  |  | N.S
Karen Songwe - SL | Aaron Dawkins | PG County |  | APPROVED 2.8 | applied/NO HOA for this address | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | 22.57 |  |  | Done
Jose H Vega Carapia - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | N/A | Approved - potomac Edison | Done | issued
Jonas Chicas - DV | Sarah Romero | Louisa County |  | N/A | NA | Approved-Dominion | Done | issued | Installation Completed | [9 empty] | Done
Joy Dalesandro - GL - ON HOLD | NobleSolar | Chesapeake City |  | APPROVED 2.9 | applied | Applied Dominion | Done
Christopher Nunley - GL | SolarStrong | Berkeley County |  | APPROVED 3.23 | NA | Approved Potomac WV | Done | in review | Installation Completed | Passed | Applied | DONE
Kevin Coates - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Francis Hawkins - SL | Thornton Fennell | Charles County |  | APPROVED 2.24 | NA | Approved SMECO | Done | issued | Installation Completed | Passed | Approved | DONE |  | Done | Done | 22.2 |  |  | Done
Jon Walman - DV | Skylightnrg | Stafford County |  | N/A | NA | Project Cancell (James Nguyen) | Done | [10 empty] | Yes
Britteny Stone-Joel - GL | NobleSolar | Isle of Wight County |  | APPROVED 3.1 | approved | Approved-Dominion | Drop Box | issued | Installation in Progress |  |  | DONE
Donna Delgado-Johnson - SL | Thornton Fennell | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  | Done |  |  | Done
Kenneth King - GL | NobleSolar | Hampton City |  | APPROVED 2.14 | N/A | Approved-Dominion | Done | issued | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Jaramie York - SN | Jedi | Charles County |  | CANCELED | NA | Have Bill SMECO | [11 empty] | Yes
Jose Oscar Velasco - GL | Carlos Cueto | Montgomery County |  | APPROVED 2.15 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Melvin Blackwell - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved- Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Kenmanze Edmonds - GL | NobleSolar | Isle of Wight County |  | PROJECT CANCELED | NA | Have bill | [11 empty] | Yes
Christopher Bonzek - CASH | Inside Sales | Newport News City |  | N/A | NA | Approved dominion | Done | issued | TBS - Rec Panels
Mary Clowe - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mridul Gupta - DV | Skylightnrg | Henrico County |  | N/A | approved | Approved dominion | Done | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | skylight
Jose Blanco - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Blanca Arevalo - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mark Whitling - GL | NobleSolar | VA Beach City |  | APPROVED 2.14 | deal cancelled | deal cancel | [11 empty] | Yes
Joe Leugers - GL | NobleSolar | Suffolk City |  | APPROVED 2.23 | approved | Approved dominion | Drop Box | issued | Installation Completed |  | Applied | Done | [6 empty] | N.S
Alejandra Juarez - GL | Raf Solar | PG County |  | APPROVED 2.15 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Paul Warren - GL | NobleSolar | VA Beach City |  | APPROVED 2.15 | need action |  | Drop Box | [10 empty] | Yes
Miguel Vernal - GL | Raf Solar | Baltimore County |  | APPROVED 2.15 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
William Smith - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.15 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Eros Lazzerini - CASH | Inside Sales | Distric of Columbia County | DC | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Cletus Ayuk - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved |  |  | Done | Done | Done |  |  | Done
Hannah Emert - GL | NobleSolar | Suffolk City |  | APPROVED 2.17 | applied | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Franklin A Garcia - GL | Alberto Sosa | PG County |  | APPROVED 2.16 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Guillermo West - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.18 | NA | Approved- PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Shirlene Ogburn - DV | Skylightnrg | Charles County |  | N/A |  | Project Cancel by Dealer | [11 empty] | Yes
Kelsey Mijal - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | NA | Approved dominion | Done |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Danielle Goodrum - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | applied | Approved dominion | Done
Nathan Carl - GL | NobleSolar | Portsmouth City |  | APPROVED 3.8 | NA | Approved dominion | Drop Box | in review | Scheduled 5/27 | Passed
Meaghan Jenks - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Applied | Done |  |  | DONE |  |  |  | Done
Queenie May Escubio - EZ |  | Portsmouth City |  | APPROVED 2.17 | NA | Approved dominion | Done | in review | Scheduled 5/28 | Passed | Applied
Alexander Phillips - GL | NobleSolar | Chesapeake City |  | APPROVED 2.17 | applied | Approved dominion | Done | issued
`William Sanders - CASH | Solarsurge | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | in review
Michelle Gomez - GL | Alberto Sosa | PG County |  | APPROVED 3.1 | NA | Approved-Pepco | Drop Box | issued | [9 empty] | Yes
George Knight - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | need policy no# | Drop Box
May Petalcorin - GL | NobleSolar | Suffolk City |  | PROJECT CANCELED | need action | [12 empty] | Yes
DePaul Griffin - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Richard Taylor - GL | NobleSolar | VA Beach City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Rebecca Phillips Ferguson - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Peter Keller - CASH | Solarsurge | Montgomery |  | N/A | NA | Have bill-Pepco
Malcolm Dixon - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Michael Osumlalu - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Constance Kinge -SL | Aaron Dawkins | PG County |  | APPROVED 2.21 | NA | Approved PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Jennifer Joynes - SL | Jedi | Pricness Ann |  | APPROVED 2.21 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | TBS
Ruperto Rivera - GL | Raf Solar | Montgomery County |  | APPROVED 2.21 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed |  | Site created | [6 empty] | Done
Salvador Cueva - GL | Thirza Iglesias | City of frederick |  | APPROVED 2.21 | NA | Approved Potomac Edison | Drop Box | issued | Installation in Progress
Martin Medina Estrada - GL | Carlos Cueto | Town of Elkton |  | APPROVED 2.25 | NA | Approved- PEPCO(Delmarva) | Drop Box | issued | TBS
Luisa Figaro - SL | Remesh Sartani | Princess Anne |  | APPROVED 2.25 | NA | Approved- PEPCO | Drop Box | issued | Installation Completed
Fernando Ortez - GL | Raf Solar | Prince William County |  | APPROVED 2.25 | NA | Approved NOVEC | Done | [10 empty] | Yes
Telesfora Briones - GL | Raf Solar | City of Annapolis |  | APPROVED 2.21 | approved | Approved- BGE | Done | applied
Lap T. Vo - SL | Michael Reid | Montgomery County |  | APPROVED 2.21 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Candy Huynh - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | applied | Approved Dominion | Drop Box |  | Installation Completed | [9 empty] | N.S
Keith Layne - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Oscar Jimenez - GL | Raf Solar | Prince william |  | APPROVED 2.25 | NA | Approved - NOVEC | Drop Box | In review
George Hoskin - SL | Michael Reid | Montgomery County |  | APPROVED 3.4 | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Octavia Pearson - GL | Thornton Fennell | PG County |  | APPROVED 2.24 | NA | Approved - PEPCO | Drop Box | issued | Installation in Progress | Passed | Approved |  |  | Done | Monit not done | Done
Nicolas Lovo - GL | Raf Solar | Charles County |  | APPROVED 3.1 | applied | Approved - SMECO SMECOINT-08593 | Drop Box | Applied
Marcos A Flores - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | NA | Approved potomac | Drop Box | issued | TBS
Paul Rudicki - GL | NobleSolar | Chesapeake City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box |  | Installation Completed |  | Applied | Done |  |  | DONE |  |  |  | N.S
Katherine Heun - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Kyle Scherele - GL | NobleSolar | Hampton City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box | in review | Installation Completed | [9 empty] | N.S
Myrna Michelle Flores - GL | NobleSolar | VA Beach City |  | APPROVED 3.1 | approved | Approved dominion | Drop Box |  | Installation Completed |  | Applied | Done | [6 empty] | N.S
Santos Soto - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Drop Box | [10 empty] | Yes
Mary Rampolla - DV | Skylightnrg | Howard County |  | N/A | NA | Approved- BGE | Drop Box | [10 empty] | Yes
Tracy Winters - SN | USA Solar Network | Delaware County |  | CANCELED | need info | Have Bill - PECO | [11 empty] | Yes
Santos Rivera - GL | Raf Solar | Frederick County |  | APPROVED 2.25 | NA | Have Bill - Dominion | Drop Box | [10 empty] | Yes
Leslie Braithwaite - DV | Skylightnrg | PG County |  | N/A | NA | Applied - PEPCO | Done | in review | [9 empty] | Yes
Keith Wilburn - GL | NobleSolar | Suffolk City |  | APPROVED 2.25 | applied | Approved dominion | Drop Box
Thanaporn Cockran - SL | Jedi | Anne Arundel County |  | APPROVED 5.13 | NA | Approved-BGE | Drop Box | issued | TBS
Florimon Arrey Ndip Etta - GL | Aaron Dawkins | PG County |  | APPROVED 2.28 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Site created |  | Done | DONE | Done |  |  | Done
Yamarco Figaro - SL | Remesh Sartani | Wicomico County |  | APPROVED 2.28 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | Installation Completed | [9 empty] | Done
Veronica Brooks - SL | Thornton Fennell | PG County |  | APPROVED 2.28 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | Monit not done | Done |  |  | Done
Garrye Hepburn - GL | Skylightnrg | PG County |  | APPROVED 3.1 | approved | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | skylight
Adriene Muhammad - DV | Skylightnrg | Branchville |  | N/A | NA | Approved Dominion | Drop Box
Ron Leese - DV | Skylightnrg | Carroll County |  | N/A | NA | Approved-BGE | Drop Box | applied
Samuel Nelson - GL | Inside Sales | Distric of Columbia County | DC | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Site Created
Jorge A. Soto Sanabria - GL | Thirza Iglesias | PG County |  | APPROVED 3.2 | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Site Created | [6 empty] | Done
Federico Vega - GL | Thirza Iglesias | Winchester City |  | APPROVED 3.2 | NA | Applied SVEC | Drop Box | issued
Tae Kim - DV | Skylightnrg | Montgomery County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS | [8 empty] | Yes
Raul Morales Martínez - GL | Carlos Cueto | PG County |  | APPROVED 3.8 | NA | Approved-Pepco | Drop Box | issued | Installation In Progess
Jose Campos - GL | Carlos Cueto | PG County |  | APPROVED 3.4 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Jesus Aguilera - GL | Raf Solar | PG County |  | APPROVED 3.4 | HOA approved | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done |  | SS above 20 |  |  | Done
Miguel Mendoza - GL | Raf Solar | Gaithersburg City |  | APPROVED 3.4 | approved | Approved-PEPCO | Drop Box | in review | Installation In Progess
Steven Miles - GL | Volt Solar (Freddye) | Accokeek County/PG |  | APPROVED 3.9 | NA | Approved SMECO | Drop Box | issued | Installation Completed | [9 empty] | V.S
Virginia Chaziva - GL | Aaron Dawkins | PG County |  | APPROVED 3.9 | applied | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Dilsa Rosales Moscoso - GL | Ana Romero | Montgomery County |  | APPROVED 3.3 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  |  | Done |  |  |  | Done
Mary Satterwhite - SN | Jonathan Ngo | Loudoun County |  | N/A | approved by Jon | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received |  |  |  |  | Done
Patrick Brown - SL | Ric Peters | Baltimore County |  | APPROVED 3.9 | NA | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Philip Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 3.9 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Trad Leavitt - DV | Skylightnrg | Frederick County |  | N/A | approved | Approved Rappahannock | Drop Box | issued | Installation Completed | Passed | Applied | Done
Dante Fenwick - GL | Skylightnrg | PG County |  | APPROVED 3.9 | in review | Approved-Pepco | Drop Box | issued
Steve Kinaman - EZ | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Scheduled 6/2 | Passed | Applied
Raja Balasubramanian - CASH | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | Done
Jian Liu - SL | Roman Bondari | Loudoun County |  | APPROVED 3.11 | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Received |  |  |  |  | Done
Michael Mills - SL | Jedi | Wicomico County |  | APPROVED 3.11 | NA | Approved - PEPCO(Delmarva) | Drop Box | applied | Scheduled 6/2
Karla Martinez - GL | Raf Solar | Fauquier County |  | APPROVED 3.15 | approved | Approved Dominion (modifications) | Drop Box | in review (modifications) | Installation in Progress
Rita Fallon - SL | Ric Peters | Anne Arundel County |  | APPROVED 3.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
David Sheffey - SN | Thornton Fennell | PG County |  | N/A | NA | Applied - PEPCO | Drop Box | issued
Jaiyeola Oluwatosin - GL | USA Solar Network | PG County |  | APPROVED 3.14 | need info | Applied- PEPCO | Drop Box | in review
Ureka Wise - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.14 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Adam Karaffa - GL | USA Solar Network | Westmoreland County |  | APPROVED 3.14 |  | Approved Westpenn Power | Drop Box
Martha Rodriguez - DV | Michael Reid | Prince William County |  | N/A | approved | Approved- Dominion | Drop Box | Applied
Jordan Calabrese - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
Joseph Sheffey - DV | Thornton Fennell | PG County |  | N/A | NA | Approved-PEPCO | Drop Box | in review | Installation Completed | [9 empty] | Done
Jose Yaselli - SN | Jedi | Carroll County |  | N/A | NA | Approved-BGE | Drop Box
Saqr Alawdi - GL | NobleSolar | Hampton City |  | APPROVED 3.23 | NA | Have bill and HOI | ON HOLD | [10 empty] | Yes
John Delgadillo - DV | Jonathan Ngo | Chesterfield County |  | N/A | NA | Approved- Dominion | Drop Box | issued | Installation Completed | [9 empty] | Done
Joel Gonzalez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 3.17 | NA | Approved 4/4/22 | Drop Box | issued | Installation Completed | Passed | Applied | [7 empty] | Done
Arthur Cockran - SL | Jedi | Queen Anne County |  | ON HOLD UNTIL NTP | NA | Approved Choptank Electric | Drop Box | in review
Jose R Guzman Delcid - GL | Ana Romero | City of frederick |  | CHANGE ORDER 5.24 | NA | Approved potomac | Drop Box | issued
Janet Thompson - CASH | Inside Sales | Stafford County |  | N/A | approved | Approved- Dominion | Drop Box | in review
Omkar Prabhu - CASH | Inside Sales | Monroe County |  | N/A | NA | Approved - PPL | Drop Box | issued | TBS
Delia/Joseph Palmer - GL | NobleSolar | Suffolk City |  | CANCELED | need action | have bill & HOI | ELD on hold | [10 empty] | Yes
Misael Moreno - GL | Raf Solar | Anne Arundel County |  | APPROVED 3.31 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Rose Bennett - DV | Skylightnrg | Howard County |  | PROJECT CANCELED | need action | Cancelled by Skylight (Adrienne) | [11 empty] | Yes
Rebecca Gaither - SL | Thornton Fennell | PG County |  | CANCELED | [13 empty] | Yes
Joy Alorro - DV | Danny Dubois | Fairfax County |  | N/A | applied | Approved Novec | Drop Box | in review
Elizabeth Mason - DV | Danny Dubois | Staunton County |  | N/A | NA | Approved- Dominion | Drop Box
Clifford McQueen - GL | Volt (Ishmael) | PG County |  | APPROVED 5.13 | NA | Approved- Pepco | Drop Box | issued | Installation in Progress
Deborah Bailey - SN | Jedi | Baltimore County |  | N/A | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Dawn Banks- SN | Inside Sales (Ishmael) | Charles County |  | N/A | NA | Approved - SMECO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Chikodili Ugokwe - SN | Thornton Fennell | PG County |  | N/A | NA | Approved- BGE | Drop Box | in review | Installation in Progress
Maximiliano Posada - GL | Ana Romero | Montgomery County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Conor P. Williams - CASH | Inside Sales | District of Columbia |  | N/A | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Done | Done |  |  |  | Done
Francisco Jacobo Sanchez - GL | Ana Romero | PG County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | [9 empty] | Done
Dustin Schultz - GL | USA Solar Network | Calvert County |  | APPROVED 3.23 | NA | Conditionally Approved SMECO | Drop Box
Mary Ukwu - SL | Aaron Dawkins | PG County |  | APPROVED 4.1 | approved | Approved- BGE | Drop Box |  | Installation Completed | Passed | Applied | [7 empty] | Done
Liliane Batista - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 3.31 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | 2022-06-01 | [8 empty] | Done
Sharon McGee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.1 |  | Applied-Pepco | Drop Box | issued | Scheduled 5/30
Sandor Slager - CASH | Volt Solar (Brandon) | Distric of Columbia County | DC | N/A | NA | Approved- PEPCO | Drop Box | issued | Installation in Progress
James D. Bryden - EZ | Inside sales | Distric of Columbia County | DC | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - U anchor check
Anthony Field - DV | SkylightNRG | PG County |  | N/A | NA | Have Bill PEPCO | 200AMP | applied
Grace Brunner - CASH | Inside Sales | Distric of Columbia County | DC | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - Roof repair pending
Jeremy Black - CASH | Inside Sales | Lycoming County |  | N/A | NA | Approved PPL | Drop Box | issued | TBS
Phil Nawrocki - CASH | Inside Sales | Allegheny County |  | N/A | NA | Approved DLC | Drop Box
Deborah Whitaker - GL | Jedi | Baltimore City |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Tod Harach - EZ | Inside Sales | Lancaster County |  | N/A | NA | Approved PPL | Drop Box
Guillermo Mendoza - GL | Raf Solar | Montgomery County |  | APPROVED 3.26 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Leonel Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.10 | NA | Approved REC | Drop Box | Applied-5/26
Renardo Williams - DV | Jedi | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Ronisha Dickerson - GL | Volt (Ishmael) | PG County |  | APPROVED 3.27 | approved | Conditional approved SMECO | Drop Box | issued | TBS |  |  | done
Jose Coreas - GL | Carlos Cueto | Baltimore County |  | APPROVED 3.27 | Cancelled by Carlos |  | ELD on Hold | [10 empty] | Yes
Peter Kurilla - GL | USA Solar Network | Montgomery County *PA* |  | APPROVED 4.11 | NA | Applied PECO | Drop Box
Tatiana McCook - GL | Volt Solar (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Rachelle Stephens - SL | Remesh Sartani | Charles County |  | APPROVED 4.20 | NA | Approved SMECOINT-08682 | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Catherine Heath - GL | Volt (Thomas) | Distric of Columbia County | DC | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | [8 empty] | V.S
De'Andre Sheppard - DV | Skylightnrg | Baltimore County |  | N/A | NA | BGE | Drop Box
Sandra Dieterle - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Marisol Muñoz - GL | Bianca del Castillo | City of Rockville |  | APPROVED 5.3 | NA | Approved-Pepco | Drop Box | issued | TBS
Donnie Waites - GL | Volt (Thomas) | Distric of Columbia County | DC | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued
Faye Coles - DV | Skylightnrg | Anne Arundel County |  | N/A | approved | Approved-BGE | Drop Box | applied
Gerald Newsome - DV | Skylightnrg | Charles County |  | N/A | Approved | Approved -SMECO | Drop Box | issued
Queenie May Escubio - EZ | Inside sales | Prince william county |  | N/A | approved | Approved Dominion | Drop Box | Applied
Santosha Lee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.27 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | V.S
Jose Morales - GL | Marcelo Ortiz | Stafford County |  | CANCELED | NA | Applied NNEC | Drop Box | [10 empty] | Yes
Robert & Suzette Kinstler - GL | USA Solar Network | Montgomery County*PA |  | APPROVED 4.1 | NA | Approved PECO | Drop Box | [10 empty] | Yes
Peter Hughes | Double Inside Sale |  |  |  |  | Applied Rappahannock | Drop Box | in revie
Terence Collins - GL | Skylightnrg | Baltimore County |  | APROVED 3.31 | NA |  | Canceled Dt:3/31/22 | [10 empty] | Yes
Dustin Blankenship - GL | USA Solar Network | Carroll County |  | APPROVED 3.31 | NA | Approved Potomac GEN-MD-8107 | Drop Box | in review
Jay Vodela - SN | Jonathan Ngo | Montgomery County |  | N/A | approved | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jaime Salazar - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Melanie Choh - GL | Volt (Ishmael) | PG County |  | APPROVED 3.31 | Approved | Approved-Pepco | Drop Box | issued | TBS
Dawn Peterson - GL | IDC | PG County |  | APPROVED 4.1 | approved | Approved-Pepco | Drop Box | issued | TBS |  |  | DONE
Kwame Gyamfi - SL | Derrol Mcclaren | Montgomery County |  | APPROVED 5.6 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Yvette Dowtin - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | DONE
Bianca Christie - SL | Derrol Mcclaren | Baltimore County |  | APPROVED 4.20 | NA | Approved -BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Silvia Centeno - GL | "Rafael Cabello (Raf Solar )" | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Leroy Inabinett - SL | Aaron Dawkins | Baltimore City |  | CANCELEED | NA | Approved-BGE | Drop Box | In review | [9 empty] | Yes
Edgar Bonilla - GL | Marcelo Ortiz | PG County |  | APPROVED 5.2 | approved | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Marina del Carmen Bonilla - GL | Carlos Cueto | PG County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Reina Alfaro - GL | Marcelo Ortiz | Montgomery County |  | CANCELEED | NA | Approved-Pepco | Drop Box | applied | [9 empty] | Yes
Silvio Espinal - GL | Jorge Carias | Montgomery County |  | APPROVED 4.5 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Ana Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.6 | NA | Applied REC | Drop Box
Silvia Centeno - GL | Raf Solar | PG County |  | APPROVED 4.12 | NA | APPROVED-PEPCO | Drop Box | applied | Installation in Progress
Carlos Hoschmin - GL | Raf Solar | Fairfax county |  | CANCELED | cancel by SR |  | Canceled Email Dt:4/8/22 | [10 empty] | Yes
Colin Eckman - CASH | Inside Sales | Prince William County |  | N/A | approved | Approved dominion | Drop Box | Applied
Jonathan Ford - CASH | Inside Sales | Carrol County |  | N/A | NA | Applied-BGE | Drop Box
Rene Lemus - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Pierre Tekem Noumbi - DV | Skylightnrg | PG County |  | N/A | need action |  | Drop Box | issued
Jose de la Cruz Reyes - GL | Carlos Cueto | Frederick County |  | APPROVED 4.12 | Approved | Approved potomac | Drop Box | issued | TBS
Roger Yobani Diaz - GL | Bianca del Castillo | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Jose Castillo - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | approved | Approved Potomac | Drop Box | issued | Installation Completed | Passed | Applied | Done
Elizabeth Mason - DV | Inside Sales | (Chesterfield) |  | N/A | approved | Applied Dominion | Drop Box | issued
Jose Perez - GL | Raf Solar | PG County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Applied
Juan Villatoro - GL | Marcelo ortiz | Anne Arundel County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Scheduled 5/23 |  |  | Done
Vinicia R Torres - GL | Ana Romero | PG County |  | APPROVED 4.12 | NA | Approved-BGE | Drop Box | issued | Installation Completed
Juan Soto - GL | Raf Solar | PG County |  | APPROVED 4.26 | NA | Applied-Pepco | Drop Box | in review
Nestor Tchinda - SL | Derrol Mcclaren | Montgomery County |  | ON HOLD UNTIL NTP |  | Have Bill BGE
Bernice Alston - GL | Thornton Fennell | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Josias Tekle - DV | Skylightnrg | city of hagerstown |  | N/A | approved | Approved potomac | Drop Box | applied
Tim Johnson - DV | Skylightnrg | St. Mary's County |  | N/A | NA | Approved SMECO | Drop Box | issued | TBS
Theresa Terry - GL | Volt Solar (Freddye) | PG County |  | CANCELED | need info | Have Bill SMECO | 200AMP | applied | [9 empty] | Yes
Louis Drury - GL | Elijah Sutton | Calvert County |  | APPROVED 4.12 | NA | Approved SMECO | Drop Box
Hakeem Ayodeji - SN | Samuel Edwards | Charles County |  | N/A | need info | Conditionally Approved Smeco | Drop Box | issued
Kenisha Jefferson - SN | Theodore Brown | PG County |  | N/A | approved | Approved-PEPCO | Drop Box | issued
Rosa Garcia - GL | Carlos Cueto | PG County |  | APPROVED 4.13 | NA | Approved-BGE | Drop Box | issued | Installation in Progress
Abdullah Amin - GL | Volt (Thomas) | Distric of Columbia County | DC | APPROVED 4.14 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Demetri Kappatos - SL | Charles Carufel | Loudoun County |  | IN REVIEW | IN REVIEW |  | Drop Box
Teodoro Carranza - GL | Ana Romero | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Done
Vicki Powell - DV | Skylightnrg | Cecil County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Kenneth Pilpel - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Potomac | Drop Box | issued | TBS
Jose Resendiz - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Yessenia Marilu Cruz - GL | Carlos Cueto | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Lydia Hagos - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Latanya Cannady - GL | IDC | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Austin Johnson - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.19 | approved | Approved SMECO | Drop Box | issued |  |  |  | Site created
Kirk Ramirez - EZ | Tim Clark | PG County |  | N/A | applied | Approved-Pepco | Drop Box | in review
Derell Kennedo - EZ | Peter kyke | Distric of Columbia County | DC | N/A | NA | Approved-Pepco | Drop Box | in review
Ramon Eclavea - DV | Danny Dubois | Prince William County |  | N/A | applied | Approved Novec | Drop Box | Applied
Ian Roach - SL | Aaron Dawkins | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | in review | TBS
Sade Brown - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued
Jason Coy - CASH | Tim Clark | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
William Burgess - CASH | Tim Clark | Arlington County |  | N/A | NA | Approved Dominion | Drop Box | issued
Paul Leger - DV | Elijah Sutton | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Park - DV | Havar Espedal | Distric of Columbia County | DC | N/A | already approved by HAVAR | Approved-Pepco | Drop Box | in review
John Greesh - DV | Havar Espedal | Distric of Columbia County | DC | N/A | need info | Approved-Pepco | Drop Box | in review
Matthew Lewis - DV | Derrol Mcclaren | PG County |  | CANCELED | NA | Applied-Pepco | Drop Box | in review | [9 empty] | Yes
Marion Bedford - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  | Cancel by Dealer | Designed But Canceled | applied | [9 empty] | Yes
Delcita Lemus - GL | Raf Solar | PG County |  | APPROVED 4.20 | NA | Approved-Pepco | Drop Box | in review
Maria Consuelo Baires - GL | Thirza Iglesias | Loudorn County |  | CANCELED |  | Project Cancelled | Drop Box | [10 empty] | Yes
Richard Vasquez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 4.25 | NA | Applied Dominion | Drop Box | issued
Abdi Mohamed - DV | Derrol Mcclaren | Montgomery County |  | N/A | applied | Approved Potomac | Drop Box | issued
Kuega Ekue - SL | Dawit Abraham | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daysi Martinez - GL | Bianca del Castillo | city of frederick |  | APPROVED 4.25 | NA | Approved Potomac | Drop Box | in review
Rotimi Shittu - SL | Thornton Fennell | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daniel Andres Yanez - GL | Carlos Cueto | Frederick County |  | APPROVED 4.25 | applied | Applied SVEC | Drop Box
James Arthur - SL | Jonathan NGO | Charles County |  | APPROVED 4.25 | approved | Conditionally Approved SMECO | Drop Box | issued
Andrian Cruz - DV | Derrol Mcclaren | Montgomery County |  | N/A | approved | Approved Potomac | Drop Box | issued | TBS
TRAVIS MELSON - SN | USA Solar Network | Petersburg City |  | N/A | NA | Have Bill Dominion HOI | On Hold
Matthew Dreitlein - EZ | Peter Kyke | Fairfax County |  | N/A | applied | Approved Dominion | Drop Box | issued
Melat & Fanual Dawit - EZ | Inside Sales | Distric of Columbia County | DC | N/A | NA | Applied-Pepco | Drop Box | in review
David Brunco - CASH | Peter Kyke | Butler County |  | N/A | NA | Approved Penn Power | Drop Box
Ethan Pacifico - DV | Danny Dubois | Town of Herndon |  | N/A | Approved | Approved Dominion | Drop Box | Issued
Fermin Kelly - SL | Remesh Sertani | Wicomico County |  | APPROVED 4.25 | NA | Approved-Pepco(Delmarva Power) | Drop Box | applied
Mike Mendley - DV | Skylighting | Montgomery County |  | N/A | no need for approval | Approved-Pepco | Drop Box | Issued
Adolfo Mata Garcia - GL | Carlos Cueto | PG County |  | CANCELED | NA | Applied-Pepco(Project Withdrawn) | Drop Box | applied | [9 empty] | Yes
Dawn Frisby - GL | Skylightnrg | PG County |  | ON HOLD UNTIL NTP | approved | Approved-Pepco | Drop Box | in review
Michael Chernau - CASH | Tim Clark | Henrico County |  |  | NA | Applied- Dominion | Drop Box | in review
Douglas Ross - GL | Skylighting | Montgomery County |  | APPROVED 5.19 | NA | Applied-Pepco | Drop Box
Melvin Hernandez - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop Box | issued | TBS
James M. McDermott - SL | Charles Carufel | Loudorn County |  | APPROVED 5.4 | Approved | Approved Dominion | Drop Box | in review | TBS
Doris Scott - GL | Mark Davis | PG County |  | CANCELED | need info | f | ELD on Hold | applied | [9 empty] | Yes
Nicholas Hinko - SL | Charles Carufel | Loudoun County |  | APPROVED 5.5 | Approved | conditional /Approved SMECO | Drop Box | in review | TBS
Karima Ali - DV | Skylighting | Loudorn County |  | N/A | applied | Applied - Dominion | Drop Box | in review
John Whelan - DV | Jedi | Frederick County |  | N/A | applied | Approved-Potomac | Drop Box | issued
Michael Sparks - DV | Jedi | Charles County |  | N/A | NA | approved-Smeco | Drop Box | issued
Travis Melson - GL | USA Solar Network | Chesterfield County |  | ON HOLD UNTIL NTP | NA | Applied- Dominion | Drop Box
Candance Watson - SN | Greg Jonhson - BBS | Chesterfield County |  | N/A | NA | Approved Dominion | Drop Box | issued
GARFIELD KELLIER - SN | Jonathan NGO | PG |  | N/A | applied | Applied-Pepco | Drop Box | in review
Thomas Hayhurst - DV | Skylightngr | Garrett County |  | N/A | to follow | have UB | 200 Amp/On Hold
Carlos M. Claros - GL | Marcelo Ortiz | Prince William County |  | APPROVED 5.2 | approved | Approved Dominion | Drop Box | Applied
Mary Borders - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Carolina Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.2 | NA | Applied-Pepco | Drop Box | in review
Tabitha Demaio - SL | Derrol Mcclaren | Charles County |  | ON HOLD UNTIL NTP | NA | need bill | 200 Amp/On Hold
Richard Cook/Betty Siu - DV | Elijah Sutton | Charles County |  | N/A | NA | conditional /Approved SMECO | Drop Box | issued
Jose Guzman - SN | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Approved- Dominion | Drop Box | Applied | [9 empty] | Yes
Giles Nathaniel Cooke Jr - GL | Thornton Fennell | PG |  | APPROVED 5.20 | NA | Approved-PEPCO | Drop Box | in review
Jose Arbaiza - GL | Carlos cueto | Montgomery County |  | APPROVED 5.10 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Marina I. Tejada - DV | Ana Romero | PG |  | APPROVED 5.7 | NA | Approved-Pepco | Drop Box | in review
Thomas Broach - GL ( Ground Mount) | SolarStrong | Fayette County |  | APPROVED 5.5 | NA | applied-Appalachian power | Drop Box
Regan Crump - CASH | Inside Sales | Montgomery County |  | N/A | Approved | Applied Potomac | Drop Box | issued
Richard Fecher - CASH | Peter Kyle | Loudorn County |  | N/A | need action | Applied dominion | Dropbox
Sandra Schultz - GL | Mark Davis |  |  | CANCELED | [13 empty] | Yes
Fidel Santos - GL | Raf Solar | Montgomery County |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | applied
Lyle Craddock - GL | True Energy (David Twitty) | Boone County |  | APPROVED 5.5 | NA | Applied Applachian Power | Drop Box
Tamara Perez - GL | IDC | PG |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | in review
Crystal Sprowls - EZ | Inside Sales | Allegheny County |  | N/A | need info | Have Dequesne Light | 200 Amp/On Hold
Vincent Lombardi - GL | True Energy (David Twitty) | Tucker County |  | APPROVED 5.23 | NA | Have Bill-MonPower | 200 Amp
Blake Bozeman - SN | Inside Sales | District of Columbia | DC | N/A | NA | Approved-Pepco | Drop box | in review
Celia Delara - SN | Jonathan NGO | Hardford County |  | N/A | NA | Applied-BGE | Drop box | in review
Kemberly Gutierrez - SN | Thornton Fennell | PG County |  | N/A | NA | Applied-Pepco | Drop Box
Anthony Turner 1 - DV | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop box
Anthony Turner 2 - GL | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | BGE | ELD On Hold/MSP Pics Needed
Anselmo Guzman - GL | Raf Solar | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Renett Little - GL | IDC | PG County |  | APPROVED 5.10 | Approved | Approved-Pepco | Drop box | in review
Auildo Kelly Azor - SL | Remesh Sertani | Wicomico County |  | CANCELED | NA | Approved-Pepco(Delmarva Power) | Drop box | [10 empty] | Yes
Lee Webb - GL | True Energy (David Twitty) | Fayette County |  | APPROVED 5.10 | NA | Have Bill-Appalachian Power | Drop box |  | Notes: Take Two 20 and Two 15 Single Pole QO Tandum breaker
Glenn Allander - GL | Daniel Gibson | Cumberland County |  | APPROVED 5.10 | NA | Applied PPL | Drop box
Jacob Richmond- EZ | Sam Albert | Wythe County |  | N/A | need info | on Hold | Drop box
Sandra Gascon-Gracia - CASH | Sam Albert | Cumberland County |  | N/A | need info | have bill PPL | 200 Amp (In Progress)
Brandy Shamrock - DV | Skylightnrg | Franklin City |  | N/A | NA | Approved dominion | Drop box
Ivy Freeman - SL | Charles Carufel | Cumberland County |  | APPROVED 5.11 | applied | Applied Novec | Drop Box
Mariam Menkir - DV | Derrol Mcclaren | Charles County |  | N/A | in review | Approved SMECO | Drop Box | issued
Vivian Segovia - GL | Thirza Iglesias | Frederick County |  | CANCELED | NA | Approved-REC | Drop Box | [10 empty] | Yes
Frank Mestecky - GL | USA Solar Network | Pike County |  | APPROVED 5.19 | applied | Applied Met-Ed | Drop Box
MANUEL GUTIERREZ - SN | Thornton Fennell | PG County |  | N/A | NA | Approved-BGE | Drop Box | in review
Olivier Komeka - DV | Skylighting | PG County |  | N/A | to follow | Need Bill | Drop Box | in review
Joseph Flora - GL | True Energy (David Twitty) | Cabell County |  | APPROVED 5.11 | NA | Metert Number require | Drop Box
Shenee Turner - GL | IDC | PG County |  | APPROVED 5.11 | applied | Approved-Pepco | Drop box | in review
Ramon Campos - GL | Carlos cueto | PG County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop box | in review
Richard Thornburgh - CASH | Michael Reid | Montgomery County |  | N/A | NA | Applied-Pepco | Drop box | Applied
Edward Holman - DV | Skylighting | Chesterfield |  | N/A | NA | need HOI | Drop box | [10 empty] | Yes
Maribel Giovanna Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Philippa & Danielle Durham - CASH | Inside Sales | Caroline County |  | N/A | need info | Conditional Approved-Choptank | Drop Box | applied
Kenia Benitez - GL | Marcelo Ortiz | Harrisonburg City |  | CANCELED | NA | Applied SVEC | Drop Box | [10 empty] | Yes
Luis Perez - EZ | Peter Kyle | Spotsylvania County |  | N/A | applied | Approved REC | Drop Box
Anthony Olaiya Oni - GL | Thornton Fennell | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop Box
Thai-Anh Perry - SL | Charles Carufel | Prince William County |  | STIP - OWNERSHIP | in review | Approved-Novec | Drop Box
MARLYN PIPER WILLIAMS - SN | Samuel Edwards | PG County |  | N/A | need info | Applied-Pepco | Drop Box | in review
Edward Miller - DV | Skylightnrg | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Collins - GL | Heath Dewalt (Nitro) | Charlottesville City |  | ON HOLD UNTIL NTP | need info
Susan Silman - GL | True Energy (David Twitty) | Kanawha County |  | APPROVED 5.16 | NA | Applied-Appalachian | Drop Box
Blanca R Guzman Escobar - GL | Ana Romero | Montgomery County |  | APPROVED 5.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Benjamin Bacon - DV | Skylighting | Frederick County |  | N/A | approved | Approved Potomac | Drop Box | issued
Jamie Summers - GL | Strong Solar | Kanawha County |  | APPROVED 5.18 | NA | Applied-Appalachian Power | Drop Box
Ravinder Mathaudu - SN | Samuel Edwards | Montgomery County |  | N/A | need info | need bill
Everth Alvarado - DV | Danny Dubois | Manassas City |  | N/A | need info | Need Info | Drop Box | [10 empty] | Yes
Kuele Ndingsa - GL | Mark Davis | PG County |  | APPROVED 5.27 | NA | Approved-BGE | Drop Box | in review
Jeff Boggs - GL | Strong Solar | Kanawha County |  | APPROVED 5.16 | NA | Applied-Apalachian Power | Drop Box
Joseph Cotterino - GL | Quativa | Carbon County |  | STIP - OWNERSHIP | NA | PPL | Drop Box
Nang and Hong Huynh - DV | Danny Dubois | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | issued
Isaias Bustamante - GL | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Applied Dominion | Drop Box | [10 empty] | Yes
Edith S Gonzalez Mejia - GL | Carlos cueto | Anne Arundel County |  | APPROVED 6.3 | applied | Approved-BGE | Drop Box | applied
Georgia Thomas - GL | Aaron Dawkins | PG County |  | APPROVED 5.119 | NA | Approved-Pepco | Drop Box | in review
Gabriel Rosenberg - SL | Charles Carufel | Fairfax County |  | APPROVED 5.19 | NA | need correct HOI | Drop Box | applied
Michael Newkirk Jr - SN | Ric Peters | Anne Arundel County |  |  | NA | Approved-BGE | Drop Box | applied
JACQUELIN MARTINEZ - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Carol Jackson - DV | Skylighting | Charles County |  | ON HOLD UNTIL NTP | to follow | Approved Smeco | Drop Box | applied
Wubishet Yizengaw - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | issued
Florinda Escobar - GL | Raf Solar | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Janice Walters - GL | Thornton Fennell | PG County |  | APPROVED 5.20 | NA | Applied-Pepco | Drop Box | in review
Rosalba Ayala Magana - GL | Thirza Iglesias | Frederick County |  | NEED CORRECTION/ADDRESS | need action | Applied-REC | Drop Box
Yessenia Rios rubio - SL | Dawit Abraham | PG County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
David Poindexter - SL | Malik Walker | PG County |  | APPROVED 5.20 | need action | Applied-Pepco | Drop Box | applied
Kathy Rivera - GL | Quativa | Chesterfield County |  | APPROVED 5.20 | NA | Need HOI | Drop Box | applied
Scott Seladoki - GL | Quativa | Ohio County |  | APPROVED 5.20 | NA | Applied Appalachian Power | Drop Box
Rhys Buntua - CASH | Peter Kyle | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | applied
Krystle Gray - GL | Ismael | Anne Arundel County |  | APPROVED 5.28 | NA | Approved-BGE | Drop Box | applied
Abilio Hernandez - GL | Marcelo Ortiz | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Syed Abbas - CASH | Theodore Brown | Howard County |  | N/A | applied | Approved-BGE | Drop Box | Issued
María Angélica Ventura Chavez - DV | Bianca del Castillo | Montgomery County/ City of Gaithsburg/City of rockville |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box
David Bentley - GL | True Energy (David Twitty) | Clay County |  | CANCELED | [13 empty] | Yes
Jai Patel - DV | Skylightngr | Harford County |  | APPROVED 5.24 | applied | Applied-BGE | Drop Box
Toi Wiseman - GL | Ismael | PG County |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box | in review
Santos Menjivar - DV | Bianca del Castillo | Frederick County |  | N/A | NA | Approved Potomac | Drop Box
Neil de Castro - DV | Danny Dubois | Virginia Beach City |  | ON HOLD UNTIL NTP | NA | Applied-Dominion | Drop Box
Shahjahan Molla - CASH | Peter kyle | Cumberland County |  | N/A | NA | Approved PPL | Drop Box
Patrick Norman - CASH | John Lee | Arlington County |  | N/A | NA | need new bill | Drop Box | issued
Christina Sanchez - SL | Eric Strouse | Raleigh County |  | STIP - CUSTOMER NEEDS TO CALL SL | NA | applied-Apalachian Power | Drop Box
Eduviges Zavala - DV | Bianca del Castillo | Montgomery County |  | STIP - ID | NA | Applied-Pepco | Drop Box
Lilian Maribel Martinez Orellana - DV | Bianca del Castillo | Montgomery County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | applied
Jaime Cordero - GL | Marcelo ortiz | Montgomery County |  | APPROVED 5.25 | applied | Applied-Pepco | Drop Box | applied
Ebony Shirley - GL | IDC (Ishmael) | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | in review
Robert Feeman - GL | Quativa | Cumberland County |  | APPROVED 5.25 | need action | Have bill PPL | Drop Box
Rene Smith/Patrick Ward - DV | Skylighting | Frederick County |  | CANCELED | NA | Have Bill-Potomac | [11 empty] | YES
David J. Poindexter III - SL | Malik Walker | PG County |  | APPROVED 5.25 | NA |  | 200 Amp/In Progress | applied
Craig Vaughan - CASH | SolarSurge | Chesterfield County |  | N/A | NA |  | Drop Box | in review
Benedicta Njoku - GL | Dawit Abraham | District of Columbia | DC | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
Anthony Aponte - GL | Quativa | Spotsylvania County |  | APPROVED 5.27 | NA | Have bill & HOI | 200 Amp/Sunova Design
Patrick German - CASH | Quativa | Charles County |  | N/A | NA | Have bill SMECO | 200 Amp/Sunova Design
John Kolber - CASH | Inside Sales | Cumberland County |  | N/A | need info |  | ELD On Hold/MSP Pics Needed
Matthew Herbaugh - CASH | Inside Sales | Isle of Wight County |  | N/A | need info |  | Drop Box | in review
Boleslaw Stefanski - CASH | Inside Sales | Pike County |  | N/A | need action |  | Dropbox
Nick Vattimo - CASH | Inside Sales | Frederick County |  | N/A | need info |  | In Review
Emundo Trivelli - SL | Inside Sales | Prince William County |  | APPROVED 6.1 | need info | Applied Dominion | Drop Box
Jonathan Araya - CASH | Inside Sales | Loudoun County |  | N/A | need info | Apllied Dominion | Drop Box
Raed Jarrar - EZ | Inside Sales | District of Columbia | DC | N/A | need info | Pepco | Sunnova Design | applied
Melanie Johnson - SL | Aaron Dawkins | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | applied
Cheryl Baker - SL | Eric Strouse | Mineral County |  | IN REVIEW | NA | Applied Potomac | Drop Box
Rosalynn Asamoah - DV | Skylighting | Montgomery County |  | STIP - ACH | need action | Have Bill Potomac | Inverter Details N/A
Sergio Martinez - DV | Skylighting | Baltimore City |  | STIP - OWNERSHIP | NA | Applied-BGE | Drop Box | Applied
Kevin Kidwell - CASH | Quativa | Hampshire County |  | N/A | NA |  | Inverter Details N/A
Patrick Primm - GL | Quativa | ClearField County |  | APPROVED 5.31 | NA | Have Bill-Potomac | ELD On Hold/MSP Pics Needed
Cyrus Hormozi - GL | Skylighting | Washington County |  | APPROVED 5.31 | approved | Approved Potomac | Drop Box
Socoya Gorham - GL | Brandon Hyman | District of Columbia | DC | IN REVIEW | NA | Applied-Pepco | Drop Box | applied
Sean Hodgins - GL | Skylighting | Baltimore City |  | APPROVED 6.1 | NA | Applied-BGE | Drop Box
Liz Ehrich - CASH | John Lee (Inside Sales) | Stafford County |  | N/A | need action | Applied -Dominion | Drop Box
Harrison Parson - CASH | Tim Clark (Inside Sales) | Susquehanna County |  | N/A | NA | Have Bill-Penelec | In Progress/Waiting fo Client Consultation
Rene Humberto Suarez- GL | Ana Romero | PG County |  | APPROVED 6.2 | NA | Applied-BGE | Dropbox | applied
Adrian Herring - SL | Tim Clark (Inside Sales) | Allegheny County |  |  | need info |  | Everbright Design N/A
Carol Smith - SL | Solar Strong | Taylor County |  | APPROVED 6.2 | NA |  | 200 amp/Everbright Design
Ramiro Moya - GL | Carlos cueto | Montgomery County |  | APPROVED 6.3 | need action | Applied Potomac | Drop Box | applied
Edgar Sorto - GL | Raf Solar | Winchester City |  | APPROVED 6.3 | applied |  | Drop Box
Mayor William Sanders III - 1 |  |  |  |  | need info
Mayor William Sanders III - 2 |  |  |  |  | need info
Olufemi Oluwatobi Ikusika - DV | Skylighting | Baltimore County |  | APPROVED 6.6 | need action | Applied-BGE | Dropbox
Frank Trujillo - CASH | Peter Kyle ( Inside sales) | Prince William County |  | N/A | applied | Applied -Dominion | Dropbox
Jason Chandler - GL | John Lee (Inside Sales) | District of Columbia | DC | STIP | NA | Approved-Pepco | Dropbox | applied
Linda and James Dwyer - CASH | John Lee (Inside Sales) | PG County |  | N/A | need info |  | Dropbox | applied
James Rodgers - GL | Aaron Dawkins | District of Columbia | DC | APPROVED 6.7 | NA | Applied-Pepco | Dropbox | applied
Omotayo Ogundana - GL | Thornton Fennell | PG County |  | STIP - ID | need info |  | ELD on Hold | applied
Timothy Dixon - SL | John Lee (Inside Sales) | Howard County |  | NEED CORRECTION | need action | Have Bill-BGE | Sunnova Design//200 amp/Waiting fo Client Consultation
Karen Ireland - CASH | John Lee (Inside Sales) | Montgomery County |  | N/A | NA | Applied-Pepco | Dropbox | applied
James Ortmann | John Lee (Inside Sales) | PG County |  |  | NA | Applied-Pepco | Dropbox | applied
Christopher Arzadon - SL | John Lee (Inside Sales) | Prince William County |  | APPROVED 6.8 | need action | Have Bill-Dominion | Dropbox
Olawale Tolulope Ayorinde - SN | IDC (Ishmael) | PG County |  | N/A | need action | Have Bill-Pepco | 200 amp/In progress | applied
Emma Davenport - DV | Skylighting | Baltimore County |  | APPROVED 6.8 | NA | Have Bill-BGE | Site Visit Requested
Matthew Beyers - DV | Skylighting | Frederick County |  | STIP - ACH | need action | Applied Potomac | Dropbox
Christopher Means - SL | Eric Strouse | Kanawha County |  | APPROVED 6.8 | NA | Applied Appalachian | Dropbox
Charles Messerschmidt - GL | Ric Peters | Anne Arundel County |  | APPROVED 6.9 | NA | Applied-BGE | Dropbox
Heather Levander - | Quativa | Fayette County |  |  |  |  | Everbright Design N/A
Harold Gerhart - GL | Quativa | Cumberland County |  | CHANGE ORDER? | NA | Have Bill PPL | Inverter Details N/A
Justin Strickland - GL | Quativa | Cumberland County |  | APPROVED 6.9 | NA | Have Bill-PPL | Everbright Design N/A
Berta Lidia - GL | Marcelo Ortiz | Frederick county |  | APPROVED 6.9 | NA | Have bill potomac
Kenneth Blankenship - SL | Eric Strouse | Nicholas county |  | STIP - OWNERSHIP | NA |  | In Progress
Keith Scarsdale - SL | Mark Davis | Culpeper County |  | IN REVIEW | NA
Sean Magee - CASH | Cinthia Rivera | Loudoun county |  | N/A | NA | Have bill dominion | Drop Box
Todd Benbow - DV | SkylightNGR | Charlotte County |  | IN REVIEW | NA |  | ELD On Hold/MSP Pics Needed
Jlicery Diaz - SL | Eric Strouse | Kanawha County |  | STIP - OWNERSHIP | NA | Have Bill Appalachian AND hoi | drop Box
Austin Snyder - GL | Voltaic (Freddye Jackson) | Lehigh County |  | IN REVIEW |  | PPL | Dropbox
Luis Rosas - GL | Justin Hall | PG county |  | IN REVIEW |  |  | ELD On Hold/MSP Pics Needed
Fatoumatta Bah - DV | SkylightNGR | Frederick county |  | IN REVIEW | need action | Have bill potomac | ELD On Hold/MSP Pics Needed
Jose Martinez - GL | Marcelo Ortiz | Montgomery County |  | IN REVIEW |  |  | In Progress

## WV
NAME | SALES REP | COUNTY | STATE | NTP | HOA | Interconnection | Design | Permit | Installation | Inspection | Meter Change | Access | Registration | PTO Uploaded | SRECs | MD Grant | QA | CANCELLED | PEARL CERTIFICATION
Angel M Lima - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done
Dan Notestein - CASH | Sam Albert | Montgomery County/Town of Blacksburg |  | N/A | approved | Approved VTES | Done | issued | Installation Completed
Juan L Guillen - GL | Thirza Iglesias | Frederick County |  | APPROVED 1.21 | approved | Approved Rappahannock | Done | issued | Installation Completed | Passed | Applied
Fizel Jabbar - DV | Aaron Dawkins | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | site created |  | Done | Done | Done |  |  | Done
Jose Chacon - GL | Carlos Cueto | PG County |  |  | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Julio Fuentes - GL | Carlos Cueto | Montgomery County |  | APPROVED 1.07 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Misael Guillermo - SN | Thornton Fennell | PG County |  |  | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Payment pending | Payment pending |  |  | Done
Willie Ford - GL | Thornton Fennell | PG County |  | APPROVED 1.05 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Yolanda Zelaya - GL | Sarah Romero | PG County |  | APPROVED 1/10 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Mark Reid - GL | Aaron Dawkins | PG County |  | CANCELED |  |  | Done | [10 empty] | YES
Lynne Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 1/20 | N/A | Approved-Pepco | Done | Issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | Done
Raymond Marquis - GL | Noblesolar | Norfolk County |  | APPROVED 2.4 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Jessie Miles - GL | Noblesolar | Norfolk County |  | APPROVED 1/12 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Yilia Jackson - SN | Ted Brown | Baltimore City |  | N/A | NA | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | done |  | Done
Ronny/Taylor Sylvester - GL | Noblesolar | Chesapeake City |  | APPROVED 2.8 | NA | Approved Dominion | Done | Issued | Installation Completed | Passed | Applied | Done |  | Received | Done
Kathryn Alexander - CASH | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Charles Cucina - DV | Danny Dubois | FrederickCounty |  | N/A | NA | Approved Potomac | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Miguel Angel Vernal Nolasco - GL | Sarah Romero | Baltimore County |  | LOAN CANCELED | NA | Have bill | [11 empty] | Yes
Juan Martinez - DV | Sarah Romero | Winchester City |  | N/A | NA | Approved SVEC | Done | issued | Scheduled 6/9
Jose H. Baca Oseguera - GL | Ana Romero | PG County |  | APPROVED 2.8 | NA | Approved-Pepco |  | issued | Installation Completed | Passed | Applied | Done | [6 empty] | Done
Oluseyi Ajayi - GL | Noblesolar | Chesapeake City |  | APPROVED 1.28 | applied | Approved Dominion 02/15/2022 | DONE | Issued | NA
Darryl Girtz - GL | Noblesolar | Norfolk City |  | APPROVED 1.31 | NA | Approved Dominion | Done | Applied-1/24 | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Gerry Evans - GL | Noblesolar | Newport News City |  | APPROVED 1.24 | approved | Approved Dominion | Done | issued | Installation Completed
Matthew Griffin - GL | Noblesolar | VA Beach City |  | APPROVED 1.25 | NA | Approved Dominion | Done | issued | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Donald Deely - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done | Issued | TBS
Brayan Godines - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | done |  | Done | Done | Done |  |  | Done
Matthew Gomez - SL | Roberto Smith | PG County |  | APPROVED 1.24 | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Maxie Lawton -GL | Volt (Ishmael) | PG County |  | APPROVED 1.24 | approved | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Engracio Edesar Abris - DV | Danny Dubois | Arlington County |  | N/A | NA | Approved 03/01/2022 | Done | issued | Installation Completed | Passed |  | Done | [6 empty] | Done
Chris Luk - Cash | Richard Thrutchley | Fairfax County |  | N/A | approved | Approved Dominion | Done | issued | Scheduled 6/3 |  |  | Done
Nabil Ahmed - SL | Roberto Smith | Montgomery County |  | APPROVED 1.28 | approved | Approved Potomac | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | DONE | Done |  |  | Done
Sharon Flowers - DV | Jedi | PG County |  | CANCELED | applied | Approved-BGE | Done | issued
Maricela Pena - GL | Sarah Romero | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | [9 empty] | Done
Malik Abdunafi - SL | Jedi | Baltimore City |  | APPROVED 2.7 | NA | Approved-BGE | Done | Issued | TBS
Delphine London - NS | Noblesolar | VA Beach City |  | APPROVED 2.7 | approved | Approved Dominion | Done |  | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Gary Hill - GL | Noblesolar | York County |  | APPROVED 1.28 | APPROVED | Approved Dominion | Done | applied | Installation Completed
Carmen Bona - SN | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Applied PECO | Done
Tyleek Harris - GL | Noblesolar | Newport News City |  | APPROVED 2.7 | applied | Approved Dominion | Done | issued
Harrison Eacho - GL | Noblesolar | Norfollk City |  | APPROVED 1/28 | NA | Applied Dominion | Done
Olawole Olayinka - GL | Volt Solar (Freddye) | Howard County |  | APPROVED 1/28 | approved | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | V.S
Justin Shoemaker - GL | Noblesolar | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | N.S
Adewale Daramola - GL | Noblesolar | Chesapeake City |  | APPROVED 1.31.22 | applied | Approved Dominion | Done
Silvia Rivera - DV | Sarah Romero | City of Frederick |  | N/A | NA | Approved-Potomac Edison | Done | issued | TBS
Darwin A Fuentes - GL | Alberto Sosa | PG County |  | APPROVED 2.3 | NA |  | Dropbox | issued | [9 empty] | Yes
Charles Hiller - EZ | Sam Albert | Pike County |  | Declined by EZSolarLoan | NA | Applied Met-Ed | Done | [10 empty] | Yes
John Coombs - SL | Roberto Smith | Baltimore County |  | APPROVED 2.1 | NA | Approved-BGE | Done | issued | Installation Completed | [9 empty] | Done
Amy Cervantes - EZ | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Eli Apuya - GL | Noblesolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Done
Brett Dash - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved dominion | Drop Box
Alexander Vasquez Fernandez - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved-dominion | Done
Taiwo Olayinka - GL | Volt Solar (Freddye) | Anne Arundel County |  | APPROVED 2.2 | approved | Approved-BGE | Done | in review | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jessica Green - SN | USA Solar Network | Westmoreland County |  | CANCELED | N/A | Applied - Westpenn Power | Drop Box | issued
William Bryan - GL | USA Solar Network | Bucks County |  | APPROVED 2.3 | N/A | Applied PECO | Done | issued
Kimberly Hayes - GL | USA Solar Network | Luzerne County |  | APPROVED 2..3 | N/A | Approved PPL WO 58650550 | Done | issued | Installation Completed | [9 empty] | U.S solar network
Devin Sharp - GL | USA Solar Network | Pittsylvania County |  | CANCELED | NA | Have Bill Danvill | ELD On Hold | [10 empty] | Yes
James Spadoni - GL | USA Solar Network | Northampton County |  | APPROVED 2.4 | N/A | Applied Met ED | Done
Edward Coley - CASH | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Approved PECO | Done |  | TBS - Roof Pending
Christopher Doane - GL | NobleSolar | Suffolk City |  | APPROVED 2.4 | applied | Approved-dominion | Drop Box
David Nicklas - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done
Margaret Galega - SL | Joseph Allo | PG County |  | APPROVED 2.4 | applied | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Raymond Kabacinski - GL | NobleSolar | Norfolk City |  | APPROVED 2.7 | NA | Approved-dominion | Done | B-issued | Installation Completed |  | Applied | Site Created |  | Received | DONE |  |  |  | N.S
Karen Songwe - SL | Aaron Dawkins | PG County |  | APPROVED 2.8 | applied/NO HOA for this address | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | 22.57 |  |  | Done
Jose H Vega Carapia - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | N/A | Approved - potomac Edison | Done | issued
Jonas Chicas - DV | Sarah Romero | Louisa County |  | N/A | NA | Approved-Dominion | Done | issued | Installation Completed | [9 empty] | Done
Joy Dalesandro - GL - ON HOLD | NobleSolar | Chesapeake City |  | APPROVED 2.9 | applied | Applied Dominion | Done
Christopher Nunley - GL | SolarStrong | Berkeley County | WV | APPROVED 3.23 | NA | Approved Potomac WV | Done | in review | Installation Completed | Passed | Applied | DONE
Kevin Coates - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Francis Hawkins - SL | Thornton Fennell | Charles County |  | APPROVED 2.24 | NA | Approved SMECO | Done | issued | Installation Completed | Passed | Approved | DONE |  | Done | Done | 22.2 |  |  | Done
Jon Walman - DV | Skylightnrg | Stafford County |  | N/A | NA | Project Cancell (James Nguyen) | Done | [10 empty] | Yes
Britteny Stone-Joel - GL | NobleSolar | Isle of Wight County |  | APPROVED 3.1 | approved | Approved-Dominion | Drop Box | issued | Installation in Progress |  |  | DONE
Donna Delgado-Johnson - SL | Thornton Fennell | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  | Done |  |  | Done
Kenneth King - GL | NobleSolar | Hampton City |  | APPROVED 2.14 | N/A | Approved-Dominion | Done | issued | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Jaramie York - SN | Jedi | Charles County |  | CANCELED | NA | Have Bill SMECO | [11 empty] | Yes
Jose Oscar Velasco - GL | Carlos Cueto | Montgomery County |  | APPROVED 2.15 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Melvin Blackwell - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved- Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Kenmanze Edmonds - GL | NobleSolar | Isle of Wight County |  | PROJECT CANCELED | NA | Have bill | [11 empty] | Yes
Christopher Bonzek - CASH | Inside Sales | Newport News City |  | N/A | NA | Approved dominion | Done | issued | TBS - Rec Panels
Mary Clowe - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mridul Gupta - DV | Skylightnrg | Henrico County |  | N/A | approved | Approved dominion | Done | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | skylight
Jose Blanco - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Blanca Arevalo - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mark Whitling - GL | NobleSolar | VA Beach City |  | APPROVED 2.14 | deal cancelled | deal cancel | [11 empty] | Yes
Joe Leugers - GL | NobleSolar | Suffolk City |  | APPROVED 2.23 | approved | Approved dominion | Drop Box | issued | Installation Completed |  | Applied | Done | [6 empty] | N.S
Alejandra Juarez - GL | Raf Solar | PG County |  | APPROVED 2.15 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Paul Warren - GL | NobleSolar | VA Beach City |  | APPROVED 2.15 | need action |  | Drop Box | [10 empty] | Yes
Miguel Vernal - GL | Raf Solar | Baltimore County |  | APPROVED 2.15 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
William Smith - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.15 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Eros Lazzerini - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Cletus Ayuk - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved |  |  | Done | Done | Done |  |  | Done
Hannah Emert - GL | NobleSolar | Suffolk City |  | APPROVED 2.17 | applied | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Franklin A Garcia - GL | Alberto Sosa | PG County |  | APPROVED 2.16 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Guillermo West - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.18 | NA | Approved- PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Shirlene Ogburn - DV | Skylightnrg | Charles County |  | N/A |  | Project Cancel by Dealer | [11 empty] | Yes
Kelsey Mijal - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | NA | Approved dominion | Done |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Danielle Goodrum - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | applied | Approved dominion | Done
Nathan Carl - GL | NobleSolar | Portsmouth City |  | APPROVED 3.8 | NA | Approved dominion | Drop Box | in review | Scheduled 5/27 | Passed
Meaghan Jenks - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Applied | Done |  |  | DONE |  |  |  | Done
Queenie May Escubio - EZ |  | Portsmouth City |  | APPROVED 2.17 | NA | Approved dominion | Done | in review | Scheduled 5/28 | Passed | Applied
Alexander Phillips - GL | NobleSolar | Chesapeake City |  | APPROVED 2.17 | applied | Approved dominion | Done | issued
`William Sanders - CASH | Solarsurge | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | in review
Michelle Gomez - GL | Alberto Sosa | PG County |  | APPROVED 3.1 | NA | Approved-Pepco | Drop Box | issued | [9 empty] | Yes
George Knight - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | need policy no# | Drop Box
May Petalcorin - GL | NobleSolar | Suffolk City |  | PROJECT CANCELED | need action | [12 empty] | Yes
DePaul Griffin - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Richard Taylor - GL | NobleSolar | VA Beach City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Rebecca Phillips Ferguson - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Peter Keller - CASH | Solarsurge | Montgomery |  | N/A | NA | Have bill-Pepco
Malcolm Dixon - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Michael Osumlalu - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Constance Kinge -SL | Aaron Dawkins | PG County |  | APPROVED 2.21 | NA | Approved PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Jennifer Joynes - SL | Jedi | Pricness Ann |  | APPROVED 2.21 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | TBS
Ruperto Rivera - GL | Raf Solar | Montgomery County |  | APPROVED 2.21 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed |  | Site created | [6 empty] | Done
Salvador Cueva - GL | Thirza Iglesias | City of frederick |  | APPROVED 2.21 | NA | Approved Potomac Edison | Drop Box | issued | Installation in Progress
Martin Medina Estrada - GL | Carlos Cueto | Town of Elkton |  | APPROVED 2.25 | NA | Approved- PEPCO(Delmarva) | Drop Box | issued | TBS
Luisa Figaro - SL | Remesh Sartani | Princess Anne |  | APPROVED 2.25 | NA | Approved- PEPCO | Drop Box | issued | Installation Completed
Fernando Ortez - GL | Raf Solar | Prince William County |  | APPROVED 2.25 | NA | Approved NOVEC | Done | [10 empty] | Yes
Telesfora Briones - GL | Raf Solar | City of Annapolis |  | APPROVED 2.21 | approved | Approved- BGE | Done | applied
Lap T. Vo - SL | Michael Reid | Montgomery County |  | APPROVED 2.21 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Candy Huynh - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | applied | Approved Dominion | Drop Box |  | Installation Completed | [9 empty] | N.S
Keith Layne - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Oscar Jimenez - GL | Raf Solar | Prince william |  | APPROVED 2.25 | NA | Approved - NOVEC | Drop Box | In review
George Hoskin - SL | Michael Reid | Montgomery County |  | APPROVED 3.4 | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Octavia Pearson - GL | Thornton Fennell | PG County |  | APPROVED 2.24 | NA | Approved - PEPCO | Drop Box | issued | Installation in Progress | Passed | Approved |  |  | Done | Monit not done | Done
Nicolas Lovo - GL | Raf Solar | Charles County |  | APPROVED 3.1 | applied | Approved - SMECO SMECOINT-08593 | Drop Box | Applied
Marcos A Flores - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | NA | Approved potomac | Drop Box | issued | TBS
Paul Rudicki - GL | NobleSolar | Chesapeake City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box |  | Installation Completed |  | Applied | Done |  |  | DONE |  |  |  | N.S
Katherine Heun - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Kyle Scherele - GL | NobleSolar | Hampton City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box | in review | Installation Completed | [9 empty] | N.S
Myrna Michelle Flores - GL | NobleSolar | VA Beach City |  | APPROVED 3.1 | approved | Approved dominion | Drop Box |  | Installation Completed |  | Applied | Done | [6 empty] | N.S
Santos Soto - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Drop Box | [10 empty] | Yes
Mary Rampolla - DV | Skylightnrg | Howard County |  | N/A | NA | Approved- BGE | Drop Box | [10 empty] | Yes
Tracy Winters - SN | USA Solar Network | Delaware County |  | CANCELED | need info | Have Bill - PECO | [11 empty] | Yes
Santos Rivera - GL | Raf Solar | Frederick County |  | APPROVED 2.25 | NA | Have Bill - Dominion | Drop Box | [10 empty] | Yes
Leslie Braithwaite - DV | Skylightnrg | PG County |  | N/A | NA | Applied - PEPCO | Done | in review | [9 empty] | Yes
Keith Wilburn - GL | NobleSolar | Suffolk City |  | APPROVED 2.25 | applied | Approved dominion | Drop Box
Thanaporn Cockran - SL | Jedi | Anne Arundel County |  | APPROVED 5.13 | NA | Approved-BGE | Drop Box | issued | TBS
Florimon Arrey Ndip Etta - GL | Aaron Dawkins | PG County |  | APPROVED 2.28 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Site created |  | Done | DONE | Done |  |  | Done
Yamarco Figaro - SL | Remesh Sartani | Wicomico County |  | APPROVED 2.28 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | Installation Completed | [9 empty] | Done
Veronica Brooks - SL | Thornton Fennell | PG County |  | APPROVED 2.28 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | Monit not done | Done |  |  | Done
Garrye Hepburn - GL | Skylightnrg | PG County |  | APPROVED 3.1 | approved | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | skylight
Adriene Muhammad - DV | Skylightnrg | Branchville |  | N/A | NA | Approved Dominion | Drop Box
Ron Leese - DV | Skylightnrg | Carroll County |  | N/A | NA | Approved-BGE | Drop Box | applied
Samuel Nelson - GL | Inside Sales | Distric of Columbia County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Site Created
Jorge A. Soto Sanabria - GL | Thirza Iglesias | PG County |  | APPROVED 3.2 | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Site Created | [6 empty] | Done
Federico Vega - GL | Thirza Iglesias | Winchester City |  | APPROVED 3.2 | NA | Applied SVEC | Drop Box | issued
Tae Kim - DV | Skylightnrg | Montgomery County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS | [8 empty] | Yes
Raul Morales Martínez - GL | Carlos Cueto | PG County |  | APPROVED 3.8 | NA | Approved-Pepco | Drop Box | issued | Installation In Progess
Jose Campos - GL | Carlos Cueto | PG County |  | APPROVED 3.4 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Jesus Aguilera - GL | Raf Solar | PG County |  | APPROVED 3.4 | HOA approved | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done |  | SS above 20 |  |  | Done
Miguel Mendoza - GL | Raf Solar | Gaithersburg City |  | APPROVED 3.4 | approved | Approved-PEPCO | Drop Box | in review | Installation In Progess
Steven Miles - GL | Volt Solar (Freddye) | Accokeek County/PG |  | APPROVED 3.9 | NA | Approved SMECO | Drop Box | issued | Installation Completed | [9 empty] | V.S
Virginia Chaziva - GL | Aaron Dawkins | PG County |  | APPROVED 3.9 | applied | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Dilsa Rosales Moscoso - GL | Ana Romero | Montgomery County |  | APPROVED 3.3 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  |  | Done |  |  |  | Done
Mary Satterwhite - SN | Jonathan Ngo | Loudoun County |  | N/A | approved by Jon | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received |  |  |  |  | Done
Patrick Brown - SL | Ric Peters | Baltimore County |  | APPROVED 3.9 | NA | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Philip Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 3.9 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Trad Leavitt - DV | Skylightnrg | Frederick County |  | N/A | approved | Approved Rappahannock | Drop Box | issued | Installation Completed | Passed | Applied | Done
Dante Fenwick - GL | Skylightnrg | PG County |  | APPROVED 3.9 | in review | Approved-Pepco | Drop Box | issued
Steve Kinaman - EZ | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Scheduled 6/2 | Passed | Applied
Raja Balasubramanian - CASH | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | Done
Jian Liu - SL | Roman Bondari | Loudoun County |  | APPROVED 3.11 | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Received |  |  |  |  | Done
Michael Mills - SL | Jedi | Wicomico County |  | APPROVED 3.11 | NA | Approved - PEPCO(Delmarva) | Drop Box | applied | Scheduled 6/2
Karla Martinez - GL | Raf Solar | Fauquier County |  | APPROVED 3.15 | approved | Approved Dominion (modifications) | Drop Box | in review (modifications) | Installation in Progress
Rita Fallon - SL | Ric Peters | Anne Arundel County |  | APPROVED 3.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
David Sheffey - SN | Thornton Fennell | PG County |  | N/A | NA | Applied - PEPCO | Drop Box | issued
Jaiyeola Oluwatosin - GL | USA Solar Network | PG County |  | APPROVED 3.14 | need info | Applied- PEPCO | Drop Box | in review
Ureka Wise - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.14 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Adam Karaffa - GL | USA Solar Network | Westmoreland County |  | APPROVED 3.14 |  | Approved Westpenn Power | Drop Box
Martha Rodriguez - DV | Michael Reid | Prince William County |  | N/A | approved | Approved- Dominion | Drop Box | Applied
Jordan Calabrese - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
Joseph Sheffey - DV | Thornton Fennell | PG County |  | N/A | NA | Approved-PEPCO | Drop Box | in review | Installation Completed | [9 empty] | Done
Jose Yaselli - SN | Jedi | Carroll County |  | N/A | NA | Approved-BGE | Drop Box
Saqr Alawdi - GL | NobleSolar | Hampton City |  | APPROVED 3.23 | NA | Have bill and HOI | ON HOLD | [10 empty] | Yes
John Delgadillo - DV | Jonathan Ngo | Chesterfield County |  | N/A | NA | Approved- Dominion | Drop Box | issued | Installation Completed | [9 empty] | Done
Joel Gonzalez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 3.17 | NA | Approved 4/4/22 | Drop Box | issued | Installation Completed | Passed | Applied | [7 empty] | Done
Arthur Cockran - SL | Jedi | Queen Anne County |  | ON HOLD UNTIL NTP | NA | Approved Choptank Electric | Drop Box | in review
Jose R Guzman Delcid - GL | Ana Romero | City of frederick |  | CHANGE ORDER 5.24 | NA | Approved potomac | Drop Box | issued
Janet Thompson - CASH | Inside Sales | Stafford County |  | N/A | approved | Approved- Dominion | Drop Box | in review
Omkar Prabhu - CASH | Inside Sales | Monroe County |  | N/A | NA | Approved - PPL | Drop Box | issued | TBS
Delia/Joseph Palmer - GL | NobleSolar | Suffolk City |  | CANCELED | need action | have bill & HOI | ELD on hold | [10 empty] | Yes
Misael Moreno - GL | Raf Solar | Anne Arundel County |  | APPROVED 3.31 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Rose Bennett - DV | Skylightnrg | Howard County |  | PROJECT CANCELED | need action | Cancelled by Skylight (Adrienne) | [11 empty] | Yes
Rebecca Gaither - SL | Thornton Fennell | PG County |  | CANCELED | [13 empty] | Yes
Joy Alorro - DV | Danny Dubois | Fairfax County |  | N/A | applied | Approved Novec | Drop Box | in review
Elizabeth Mason - DV | Danny Dubois | Staunton County |  | N/A | NA | Approved- Dominion | Drop Box
Clifford McQueen - GL | Volt (Ishmael) | PG County |  | APPROVED 5.13 | NA | Approved- Pepco | Drop Box | issued | Installation in Progress
Deborah Bailey - SN | Jedi | Baltimore County |  | N/A | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Dawn Banks- SN | Inside Sales (Ishmael) | Charles County |  | N/A | NA | Approved - SMECO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Chikodili Ugokwe - SN | Thornton Fennell | PG County |  | N/A | NA | Approved- BGE | Drop Box | in review | Installation in Progress
Maximiliano Posada - GL | Ana Romero | Montgomery County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Conor P. Williams - CASH | Inside Sales | District of Columbia |  | N/A | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Done | Done |  |  |  | Done
Francisco Jacobo Sanchez - GL | Ana Romero | PG County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | [9 empty] | Done
Dustin Schultz - GL | USA Solar Network | Calvert County |  | APPROVED 3.23 | NA | Conditionally Approved SMECO | Drop Box
Mary Ukwu - SL | Aaron Dawkins | PG County |  | APPROVED 4.1 | approved | Approved- BGE | Drop Box |  | Installation Completed | Passed | Applied | [7 empty] | Done
Liliane Batista - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 3.31 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | 2022-06-01 | [8 empty] | Done
Sharon McGee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.1 |  | Applied-Pepco | Drop Box | issued | Scheduled 5/30
Sandor Slager - CASH | Volt Solar (Brandon) | Distric of Columbia County |  | N/A | NA | Approved- PEPCO | Drop Box | issued | Installation in Progress
James D. Bryden - EZ | Inside sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - U anchor check
Anthony Field - DV | SkylightNRG | PG County |  | N/A | NA | Have Bill PEPCO | 200AMP | applied
Grace Brunner - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - Roof repair pending
Jeremy Black - CASH | Inside Sales | Lycoming County |  | N/A | NA | Approved PPL | Drop Box | issued | TBS
Phil Nawrocki - CASH | Inside Sales | Allegheny County |  | N/A | NA | Approved DLC | Drop Box
Deborah Whitaker - GL | Jedi | Baltimore City |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Tod Harach - EZ | Inside Sales | Lancaster County |  | N/A | NA | Approved PPL | Drop Box
Guillermo Mendoza - GL | Raf Solar | Montgomery County |  | APPROVED 3.26 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Leonel Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.10 | NA | Approved REC | Drop Box | Applied-5/26
Renardo Williams - DV | Jedi | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Ronisha Dickerson - GL | Volt (Ishmael) | PG County |  | APPROVED 3.27 | approved | Conditional approved SMECO | Drop Box | issued | TBS |  |  | done
Jose Coreas - GL | Carlos Cueto | Baltimore County |  | APPROVED 3.27 | Cancelled by Carlos |  | ELD on Hold | [10 empty] | Yes
Peter Kurilla - GL | USA Solar Network | Montgomery County *PA* |  | APPROVED 4.11 | NA | Applied PECO | Drop Box
Tatiana McCook - GL | Volt Solar (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Rachelle Stephens - SL | Remesh Sartani | Charles County |  | APPROVED 4.20 | NA | Approved SMECOINT-08682 | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Catherine Heath - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | [8 empty] | V.S
De'Andre Sheppard - DV | Skylightnrg | Baltimore County |  | N/A | NA | BGE | Drop Box
Sandra Dieterle - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Marisol Muñoz - GL | Bianca del Castillo | City of Rockville |  | APPROVED 5.3 | NA | Approved-Pepco | Drop Box | issued | TBS
Donnie Waites - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued
Faye Coles - DV | Skylightnrg | Anne Arundel County |  | N/A | approved | Approved-BGE | Drop Box | applied
Gerald Newsome - DV | Skylightnrg | Charles County |  | N/A | Approved | Approved -SMECO | Drop Box | issued
Queenie May Escubio - EZ | Inside sales | Prince william county |  | N/A | approved | Approved Dominion | Drop Box | Applied
Santosha Lee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.27 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | V.S
Jose Morales - GL | Marcelo Ortiz | Stafford County |  | CANCELED | NA | Applied NNEC | Drop Box | [10 empty] | Yes
Robert & Suzette Kinstler - GL | USA Solar Network | Montgomery County*PA |  | APPROVED 4.1 | NA | Approved PECO | Drop Box | [10 empty] | Yes
Peter Hughes | Double Inside Sale |  |  |  |  | Applied Rappahannock | Drop Box | in revie
Terence Collins - GL | Skylightnrg | Baltimore County |  | APROVED 3.31 | NA |  | Canceled Dt:3/31/22 | [10 empty] | Yes
Dustin Blankenship - GL | USA Solar Network | Carroll County |  | APPROVED 3.31 | NA | Approved Potomac GEN-MD-8107 | Drop Box | in review
Jay Vodela - SN | Jonathan Ngo | Montgomery County |  | N/A | approved | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jaime Salazar - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Melanie Choh - GL | Volt (Ishmael) | PG County |  | APPROVED 3.31 | Approved | Approved-Pepco | Drop Box | issued | TBS
Dawn Peterson - GL | IDC | PG County |  | APPROVED 4.1 | approved | Approved-Pepco | Drop Box | issued | TBS |  |  | DONE
Kwame Gyamfi - SL | Derrol Mcclaren | Montgomery County |  | APPROVED 5.6 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Yvette Dowtin - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | DONE
Bianca Christie - SL | Derrol Mcclaren | Baltimore County |  | APPROVED 4.20 | NA | Approved -BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Silvia Centeno - GL | "Rafael Cabello (Raf Solar )" | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Leroy Inabinett - SL | Aaron Dawkins | Baltimore City |  | CANCELEED | NA | Approved-BGE | Drop Box | In review | [9 empty] | Yes
Edgar Bonilla - GL | Marcelo Ortiz | PG County |  | APPROVED 5.2 | approved | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Marina del Carmen Bonilla - GL | Carlos Cueto | PG County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Reina Alfaro - GL | Marcelo Ortiz | Montgomery County |  | CANCELEED | NA | Approved-Pepco | Drop Box | applied | [9 empty] | Yes
Silvio Espinal - GL | Jorge Carias | Montgomery County |  | APPROVED 4.5 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Ana Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.6 | NA | Applied REC | Drop Box
Silvia Centeno - GL | Raf Solar | PG County |  | APPROVED 4.12 | NA | APPROVED-PEPCO | Drop Box | applied | Installation in Progress
Carlos Hoschmin - GL | Raf Solar | Fairfax county |  | CANCELED | cancel by SR |  | Canceled Email Dt:4/8/22 | [10 empty] | Yes
Colin Eckman - CASH | Inside Sales | Prince William County |  | N/A | approved | Approved dominion | Drop Box | Applied
Jonathan Ford - CASH | Inside Sales | Carrol County |  | N/A | NA | Applied-BGE | Drop Box
Rene Lemus - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Pierre Tekem Noumbi - DV | Skylightnrg | PG County |  | N/A | need action |  | Drop Box | issued
Jose de la Cruz Reyes - GL | Carlos Cueto | Frederick County |  | APPROVED 4.12 | Approved | Approved potomac | Drop Box | issued | TBS
Roger Yobani Diaz - GL | Bianca del Castillo | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Jose Castillo - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | approved | Approved Potomac | Drop Box | issued | Installation Completed | Passed | Applied | Done
Elizabeth Mason - DV | Inside Sales | (Chesterfield) |  | N/A | approved | Applied Dominion | Drop Box | issued
Jose Perez - GL | Raf Solar | PG County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Applied
Juan Villatoro - GL | Marcelo ortiz | Anne Arundel County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Scheduled 5/23 |  |  | Done
Vinicia R Torres - GL | Ana Romero | PG County |  | APPROVED 4.12 | NA | Approved-BGE | Drop Box | issued | Installation Completed
Juan Soto - GL | Raf Solar | PG County |  | APPROVED 4.26 | NA | Applied-Pepco | Drop Box | in review
Nestor Tchinda - SL | Derrol Mcclaren | Montgomery County |  | ON HOLD UNTIL NTP |  | Have Bill BGE
Bernice Alston - GL | Thornton Fennell | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Josias Tekle - DV | Skylightnrg | city of hagerstown |  | N/A | approved | Approved potomac | Drop Box | applied
Tim Johnson - DV | Skylightnrg | St. Mary's County |  | N/A | NA | Approved SMECO | Drop Box | issued | TBS
Theresa Terry - GL | Volt Solar (Freddye) | PG County |  | CANCELED | need info | Have Bill SMECO | 200AMP | applied | [9 empty] | Yes
Louis Drury - GL | Elijah Sutton | Calvert County |  | APPROVED 4.12 | NA | Approved SMECO | Drop Box
Hakeem Ayodeji - SN | Samuel Edwards | Charles County |  | N/A | need info | Conditionally Approved Smeco | Drop Box | issued
Kenisha Jefferson - SN | Theodore Brown | PG County |  | N/A | approved | Approved-PEPCO | Drop Box | issued
Rosa Garcia - GL | Carlos Cueto | PG County |  | APPROVED 4.13 | NA | Approved-BGE | Drop Box | issued | Installation in Progress
Abdullah Amin - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.14 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Demetri Kappatos - SL | Charles Carufel | Loudoun County |  | IN REVIEW | IN REVIEW |  | Drop Box
Teodoro Carranza - GL | Ana Romero | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Done
Vicki Powell - DV | Skylightnrg | Cecil County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Kenneth Pilpel - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Potomac | Drop Box | issued | TBS
Jose Resendiz - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Yessenia Marilu Cruz - GL | Carlos Cueto | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Lydia Hagos - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Latanya Cannady - GL | IDC | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Austin Johnson - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.19 | approved | Approved SMECO | Drop Box | issued |  |  |  | Site created
Kirk Ramirez - EZ | Tim Clark | PG County |  | N/A | applied | Approved-Pepco | Drop Box | in review
Derell Kennedo - EZ | Peter kyke | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Drop Box | in review
Ramon Eclavea - DV | Danny Dubois | Prince William County |  | N/A | applied | Approved Novec | Drop Box | Applied
Ian Roach - SL | Aaron Dawkins | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | in review | TBS
Sade Brown - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued
Jason Coy - CASH | Tim Clark | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
William Burgess - CASH | Tim Clark | Arlington County |  | N/A | NA | Approved Dominion | Drop Box | issued
Paul Leger - DV | Elijah Sutton | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Park - DV | Havar Espedal | Distric of Columbia County |  | N/A | already approved by HAVAR | Approved-Pepco | Drop Box | in review
John Greesh - DV | Havar Espedal | Distric of Columbia County |  | N/A | need info | Approved-Pepco | Drop Box | in review
Matthew Lewis - DV | Derrol Mcclaren | PG County |  | CANCELED | NA | Applied-Pepco | Drop Box | in review | [9 empty] | Yes
Marion Bedford - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  | Cancel by Dealer | Designed But Canceled | applied | [9 empty] | Yes
Delcita Lemus - GL | Raf Solar | PG County |  | APPROVED 4.20 | NA | Approved-Pepco | Drop Box | in review
Maria Consuelo Baires - GL | Thirza Iglesias | Loudorn County |  | CANCELED |  | Project Cancelled | Drop Box | [10 empty] | Yes
Richard Vasquez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 4.25 | NA | Applied Dominion | Drop Box | issued
Abdi Mohamed - DV | Derrol Mcclaren | Montgomery County |  | N/A | applied | Approved Potomac | Drop Box | issued
Kuega Ekue - SL | Dawit Abraham | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daysi Martinez - GL | Bianca del Castillo | city of frederick |  | APPROVED 4.25 | NA | Approved Potomac | Drop Box | in review
Rotimi Shittu - SL | Thornton Fennell | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daniel Andres Yanez - GL | Carlos Cueto | Frederick County |  | APPROVED 4.25 | applied | Applied SVEC | Drop Box
James Arthur - SL | Jonathan NGO | Charles County |  | APPROVED 4.25 | approved | Conditionally Approved SMECO | Drop Box | issued
Andrian Cruz - DV | Derrol Mcclaren | Montgomery County |  | N/A | approved | Approved Potomac | Drop Box | issued | TBS
TRAVIS MELSON - SN | USA Solar Network | Petersburg City |  | N/A | NA | Have Bill Dominion HOI | On Hold
Matthew Dreitlein - EZ | Peter Kyke | Fairfax County |  | N/A | applied | Approved Dominion | Drop Box | issued
Melat & Fanual Dawit - EZ | Inside Sales | Distric of Columbia County |  | N/A | NA | Applied-Pepco | Drop Box | in review
David Brunco - CASH | Peter Kyke | Butler County |  | N/A | NA | Approved Penn Power | Drop Box
Ethan Pacifico - DV | Danny Dubois | Town of Herndon |  | N/A | Approved | Approved Dominion | Drop Box | Issued
Fermin Kelly - SL | Remesh Sertani | Wicomico County |  | APPROVED 4.25 | NA | Approved-Pepco(Delmarva Power) | Drop Box | applied
Mike Mendley - DV | Skylighting | Montgomery County |  | N/A | no need for approval | Approved-Pepco | Drop Box | Issued
Adolfo Mata Garcia - GL | Carlos Cueto | PG County |  | CANCELED | NA | Applied-Pepco(Project Withdrawn) | Drop Box | applied | [9 empty] | Yes
Dawn Frisby - GL | Skylightnrg | PG County |  | ON HOLD UNTIL NTP | approved | Approved-Pepco | Drop Box | in review
Michael Chernau - CASH | Tim Clark | Henrico County |  |  | NA | Applied- Dominion | Drop Box | in review
Douglas Ross - GL | Skylighting | Montgomery County |  | APPROVED 5.19 | NA | Applied-Pepco | Drop Box
Melvin Hernandez - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop Box | issued | TBS
James M. McDermott - SL | Charles Carufel | Loudorn County |  | APPROVED 5.4 | Approved | Approved Dominion | Drop Box | in review | TBS
Doris Scott - GL | Mark Davis | PG County |  | CANCELED | need info | f | ELD on Hold | applied | [9 empty] | Yes
Nicholas Hinko - SL | Charles Carufel | Loudoun County |  | APPROVED 5.5 | Approved | conditional /Approved SMECO | Drop Box | in review | TBS
Karima Ali - DV | Skylighting | Loudorn County |  | N/A | applied | Applied - Dominion | Drop Box | in review
John Whelan - DV | Jedi | Frederick County |  | N/A | applied | Approved-Potomac | Drop Box | issued
Michael Sparks - DV | Jedi | Charles County |  | N/A | NA | approved-Smeco | Drop Box | issued
Travis Melson - GL | USA Solar Network | Chesterfield County |  | ON HOLD UNTIL NTP | NA | Applied- Dominion | Drop Box
Candance Watson - SN | Greg Jonhson - BBS | Chesterfield County |  | N/A | NA | Approved Dominion | Drop Box | issued
GARFIELD KELLIER - SN | Jonathan NGO | PG |  | N/A | applied | Applied-Pepco | Drop Box | in review
Thomas Hayhurst - DV | Skylightngr | Garrett County |  | N/A | to follow | have UB | 200 Amp/On Hold
Carlos M. Claros - GL | Marcelo Ortiz | Prince William County |  | APPROVED 5.2 | approved | Approved Dominion | Drop Box | Applied
Mary Borders - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Carolina Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.2 | NA | Applied-Pepco | Drop Box | in review
Tabitha Demaio - SL | Derrol Mcclaren | Charles County |  | ON HOLD UNTIL NTP | NA | need bill | 200 Amp/On Hold
Richard Cook/Betty Siu - DV | Elijah Sutton | Charles County |  | N/A | NA | conditional /Approved SMECO | Drop Box | issued
Jose Guzman - SN | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Approved- Dominion | Drop Box | Applied | [9 empty] | Yes
Giles Nathaniel Cooke Jr - GL | Thornton Fennell | PG |  | APPROVED 5.20 | NA | Approved-PEPCO | Drop Box | in review
Jose Arbaiza - GL | Carlos cueto | Montgomery County |  | APPROVED 5.10 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Marina I. Tejada - DV | Ana Romero | PG |  | APPROVED 5.7 | NA | Approved-Pepco | Drop Box | in review
Thomas Broach - GL ( Ground Mount) | SolarStrong | Fayette County | WV | APPROVED 5.5 | NA | applied-Appalachian power | Drop Box
Regan Crump - CASH | Inside Sales | Montgomery County |  | N/A | Approved | Applied Potomac | Drop Box | issued
Richard Fecher - CASH | Peter Kyle | Loudorn County |  | N/A | need action | Applied dominion | Dropbox
Sandra Schultz - GL | Mark Davis |  |  | CANCELED | [13 empty] | Yes
Fidel Santos - GL | Raf Solar | Montgomery County |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | applied
Lyle Craddock - GL | True Energy (David Twitty) | Boone County | WV | APPROVED 5.5 | NA | Applied Applachian Power | Drop Box
Tamara Perez - GL | IDC | PG |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | in review
Crystal Sprowls - EZ | Inside Sales | Allegheny County |  | N/A | need info | Have Dequesne Light | 200 Amp/On Hold
Vincent Lombardi - GL | True Energy (David Twitty) | Tucker County | WV | APPROVED 5.23 | NA | Have Bill-MonPower | 200 Amp
Blake Bozeman - SN | Inside Sales | District of Columbia |  | N/A | NA | Approved-Pepco | Drop box | in review
Celia Delara - SN | Jonathan NGO | Hardford County |  | N/A | NA | Applied-BGE | Drop box | in review
Kemberly Gutierrez - SN | Thornton Fennell | PG County |  | N/A | NA | Applied-Pepco | Drop Box
Anthony Turner 1 - DV | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop box
Anthony Turner 2 - GL | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | BGE | ELD On Hold/MSP Pics Needed
Anselmo Guzman - GL | Raf Solar | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Renett Little - GL | IDC | PG County |  | APPROVED 5.10 | Approved | Approved-Pepco | Drop box | in review
Auildo Kelly Azor - SL | Remesh Sertani | Wicomico County |  | CANCELED | NA | Approved-Pepco(Delmarva Power) | Drop box | [10 empty] | Yes
Lee Webb - GL | True Energy (David Twitty) | Fayette County | WV | APPROVED 5.10 | NA | Have Bill-Appalachian Power | Drop box |  | Notes: Take Two 20 and Two 15 Single Pole QO Tandum breaker
Glenn Allander - GL | Daniel Gibson | Cumberland County |  | APPROVED 5.10 | NA | Applied PPL | Drop box
Jacob Richmond- EZ | Sam Albert | Wythe County | WV | N/A | need info | on Hold | Drop box
Sandra Gascon-Gracia - CASH | Sam Albert | Cumberland County |  | N/A | need info | have bill PPL | 200 Amp (In Progress)
Brandy Shamrock - DV | Skylightnrg | Franklin City |  | N/A | NA | Approved dominion | Drop box
Ivy Freeman - SL | Charles Carufel | Cumberland County |  | APPROVED 5.11 | applied | Applied Novec | Drop Box
Mariam Menkir - DV | Derrol Mcclaren | Charles County |  | N/A | in review | Approved SMECO | Drop Box | issued
Vivian Segovia - GL | Thirza Iglesias | Frederick County |  | CANCELED | NA | Approved-REC | Drop Box | [10 empty] | Yes
Frank Mestecky - GL | USA Solar Network | Pike County |  | APPROVED 5.19 | applied | Applied Met-Ed | Drop Box
MANUEL GUTIERREZ - SN | Thornton Fennell | PG County |  | N/A | NA | Approved-BGE | Drop Box | in review
Olivier Komeka - DV | Skylighting | PG County |  | N/A | to follow | Need Bill | Drop Box | in review
Joseph Flora - GL | True Energy (David Twitty) | Cabell County | WV | APPROVED 5.11 | NA | Metert Number require | Drop Box
Shenee Turner - GL | IDC | PG County |  | APPROVED 5.11 | applied | Approved-Pepco | Drop box | in review
Ramon Campos - GL | Carlos cueto | PG County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop box | in review
Richard Thornburgh - CASH | Michael Reid | Montgomery County |  | N/A | NA | Applied-Pepco | Drop box | Applied
Edward Holman - DV | Skylighting | Chesterfield |  | N/A | NA | need HOI | Drop box | [10 empty] | Yes
Maribel Giovanna Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Philippa & Danielle Durham - CASH | Inside Sales | Caroline County |  | N/A | need info | Conditional Approved-Choptank | Drop Box | applied
Kenia Benitez - GL | Marcelo Ortiz | Harrisonburg City |  | CANCELED | NA | Applied SVEC | Drop Box | [10 empty] | Yes
Luis Perez - EZ | Peter Kyle | Spotsylvania County |  | N/A | applied | Approved REC | Drop Box
Anthony Olaiya Oni - GL | Thornton Fennell | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop Box
Thai-Anh Perry - SL | Charles Carufel | Prince William County |  | STIP - OWNERSHIP | in review | Approved-Novec | Drop Box
MARLYN PIPER WILLIAMS - SN | Samuel Edwards | PG County |  | N/A | need info | Applied-Pepco | Drop Box | in review
Edward Miller - DV | Skylightnrg | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Collins - GL | Heath Dewalt (Nitro) | Charlottesville City |  | ON HOLD UNTIL NTP | need info
Susan Silman - GL | True Energy (David Twitty) | Kanawha County | WV | APPROVED 5.16 | NA | Applied-Appalachian | Drop Box
Blanca R Guzman Escobar - GL | Ana Romero | Montgomery County |  | APPROVED 5.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Benjamin Bacon - DV | Skylighting | Frederick County |  | N/A | approved | Approved Potomac | Drop Box | issued
Jamie Summers - GL | Strong Solar | Kanawha County | WV | APPROVED 5.18 | NA | Applied-Appalachian Power | Drop Box
Ravinder Mathaudu - SN | Samuel Edwards | Montgomery County |  | N/A | need info | need bill
Everth Alvarado - DV | Danny Dubois | Manassas City |  | N/A | need info | Need Info | Drop Box | [10 empty] | Yes
Kuele Ndingsa - GL | Mark Davis | PG County |  | APPROVED 5.27 | NA | Approved-BGE | Drop Box | in review
Jeff Boggs - GL | Strong Solar | Kanawha County | WV | APPROVED 5.16 | NA | Applied-Apalachian Power | Drop Box
Joseph Cotterino - GL | Quativa | Carbon County |  | STIP - OWNERSHIP | NA | PPL | Drop Box
Nang and Hong Huynh - DV | Danny Dubois | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | issued
Isaias Bustamante - GL | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Applied Dominion | Drop Box | [10 empty] | Yes
Edith S Gonzalez Mejia - GL | Carlos cueto | Anne Arundel County |  | APPROVED 6.3 | applied | Approved-BGE | Drop Box | applied
Georgia Thomas - GL | Aaron Dawkins | PG County |  | APPROVED 5.119 | NA | Approved-Pepco | Drop Box | in review
Gabriel Rosenberg - SL | Charles Carufel | Fairfax County |  | APPROVED 5.19 | NA | need correct HOI | Drop Box | applied
Michael Newkirk Jr - SN | Ric Peters | Anne Arundel County |  |  | NA | Approved-BGE | Drop Box | applied
JACQUELIN MARTINEZ - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Carol Jackson - DV | Skylighting | Charles County |  | ON HOLD UNTIL NTP | to follow | Approved Smeco | Drop Box | applied
Wubishet Yizengaw - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | issued
Florinda Escobar - GL | Raf Solar | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Janice Walters - GL | Thornton Fennell | PG County |  | APPROVED 5.20 | NA | Applied-Pepco | Drop Box | in review
Rosalba Ayala Magana - GL | Thirza Iglesias | Frederick County |  | NEED CORRECTION/ADDRESS | need action | Applied-REC | Drop Box
Yessenia Rios rubio - SL | Dawit Abraham | PG County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
David Poindexter - SL | Malik Walker | PG County |  | APPROVED 5.20 | need action | Applied-Pepco | Drop Box | applied
Kathy Rivera - GL | Quativa | Chesterfield County |  | APPROVED 5.20 | NA | Need HOI | Drop Box | applied
Scott Seladoki - GL | Quativa | Ohio County | WV | APPROVED 5.20 | NA | Applied Appalachian Power | Drop Box
Rhys Buntua - CASH | Peter Kyle | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | applied
Krystle Gray - GL | Ismael | Anne Arundel County |  | APPROVED 5.28 | NA | Approved-BGE | Drop Box | applied
Abilio Hernandez - GL | Marcelo Ortiz | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Syed Abbas - CASH | Theodore Brown | Howard County |  | N/A | applied | Approved-BGE | Drop Box | Issued
María Angélica Ventura Chavez - DV | Bianca del Castillo | Montgomery County/ City of Gaithsburg/City of rockville |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box
David Bentley - GL | True Energy (David Twitty) | Clay County | WV | CANCELED | [13 empty] | Yes
Jai Patel - DV | Skylightngr | Harford County |  | APPROVED 5.24 | applied | Applied-BGE | Drop Box
Toi Wiseman - GL | Ismael | PG County |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box | in review
Santos Menjivar - DV | Bianca del Castillo | Frederick County |  | N/A | NA | Approved Potomac | Drop Box
Neil de Castro - DV | Danny Dubois | Virginia Beach City |  | ON HOLD UNTIL NTP | NA | Applied-Dominion | Drop Box
Shahjahan Molla - CASH | Peter kyle | Cumberland County |  | N/A | NA | Approved PPL | Drop Box
Patrick Norman - CASH | John Lee | Arlington County |  | N/A | NA | need new bill | Drop Box | issued
Christina Sanchez - SL | Eric Strouse | Raleigh County | WV | STIP - CUSTOMER NEEDS TO CALL SL | NA | applied-Apalachian Power | Drop Box
Eduviges Zavala - DV | Bianca del Castillo | Montgomery County |  | STIP - ID | NA | Applied-Pepco | Drop Box
Lilian Maribel Martinez Orellana - DV | Bianca del Castillo | Montgomery County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | applied
Jaime Cordero - GL | Marcelo ortiz | Montgomery County |  | APPROVED 5.25 | applied | Applied-Pepco | Drop Box | applied
Ebony Shirley - GL | IDC (Ishmael) | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | in review
Robert Feeman - GL | Quativa | Cumberland County |  | APPROVED 5.25 | need action | Have bill PPL | Drop Box
Rene Smith/Patrick Ward - DV | Skylighting | Frederick County |  | CANCELED | NA | Have Bill-Potomac | [11 empty] | YES
David J. Poindexter III - SL | Malik Walker | PG County |  | APPROVED 5.25 | NA |  | 200 Amp/In Progress | applied
Craig Vaughan - CASH | SolarSurge | Chesterfield County |  | N/A | NA |  | Drop Box | in review
Benedicta Njoku - GL | Dawit Abraham | District of Columbia |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
Anthony Aponte - GL | Quativa | Spotsylvania County |  | APPROVED 5.27 | NA | Have bill & HOI | 200 Amp/Sunova Design
Patrick German - CASH | Quativa | Charles County |  | N/A | NA | Have bill SMECO | 200 Amp/Sunova Design
John Kolber - CASH | Inside Sales | Cumberland County |  | N/A | need info |  | ELD On Hold/MSP Pics Needed
Matthew Herbaugh - CASH | Inside Sales | Isle of Wight County |  | N/A | need info |  | Drop Box | in review
Boleslaw Stefanski - CASH | Inside Sales | Pike County |  | N/A | need action |  | Dropbox
Nick Vattimo - CASH | Inside Sales | Frederick County |  | N/A | need info |  | In Review
Emundo Trivelli - SL | Inside Sales | Prince William County |  | APPROVED 6.1 | need info | Applied Dominion | Drop Box
Jonathan Araya - CASH | Inside Sales | Loudoun County |  | N/A | need info | Apllied Dominion | Drop Box
Raed Jarrar - EZ | Inside Sales | District of Columbia |  | N/A | need info | Pepco | Sunnova Design | applied
Melanie Johnson - SL | Aaron Dawkins | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | applied
Cheryl Baker - SL | Eric Strouse | Mineral County | WV | IN REVIEW | NA | Applied Potomac | Drop Box
Rosalynn Asamoah - DV | Skylighting | Montgomery County |  | STIP - ACH | need action | Have Bill Potomac | Inverter Details N/A
Sergio Martinez - DV | Skylighting | Baltimore City |  | STIP - OWNERSHIP | NA | Applied-BGE | Drop Box | Applied
Kevin Kidwell - CASH | Quativa | Hampshire County | WV | N/A | NA |  | Inverter Details N/A
Patrick Primm - GL | Quativa | ClearField County |  | APPROVED 5.31 | NA | Have Bill-Potomac | ELD On Hold/MSP Pics Needed
Cyrus Hormozi - GL | Skylighting | Washington County |  | APPROVED 5.31 | approved | Approved Potomac | Drop Box
Socoya Gorham - GL | Brandon Hyman | District of Columbia |  | IN REVIEW | NA | Applied-Pepco | Drop Box | applied
Sean Hodgins - GL | Skylighting | Baltimore City |  | APPROVED 6.1 | NA | Applied-BGE | Drop Box
Liz Ehrich - CASH | John Lee (Inside Sales) | Stafford County |  | N/A | need action | Applied -Dominion | Drop Box
Harrison Parson - CASH | Tim Clark (Inside Sales) | Susquehanna County |  | N/A | NA | Have Bill-Penelec | In Progress/Waiting fo Client Consultation
Rene Humberto Suarez- GL | Ana Romero | PG County |  | APPROVED 6.2 | NA | Applied-BGE | Dropbox | applied
Adrian Herring - SL | Tim Clark (Inside Sales) | Allegheny County |  |  | need info |  | Everbright Design N/A
Carol Smith - SL | Solar Strong | Taylor County |  | APPROVED 6.2 | NA |  | 200 amp/Everbright Design
Ramiro Moya - GL | Carlos cueto | Montgomery County |  | APPROVED 6.3 | need action | Applied Potomac | Drop Box | applied
Edgar Sorto - GL | Raf Solar | Winchester City |  | APPROVED 6.3 | applied |  | Drop Box
Mayor William Sanders III - 1 |  |  |  |  | need info
Mayor William Sanders III - 2 |  |  |  |  | need info
Olufemi Oluwatobi Ikusika - DV | Skylighting | Baltimore County |  | APPROVED 6.6 | need action | Applied-BGE | Dropbox
Frank Trujillo - CASH | Peter Kyle ( Inside sales) | Prince William County |  | N/A | applied | Applied -Dominion | Dropbox
Jason Chandler - GL | John Lee (Inside Sales) | District of Columbia |  | STIP | NA | Approved-Pepco | Dropbox | applied
Linda and James Dwyer - CASH | John Lee (Inside Sales) | PG County |  | N/A | need info |  | Dropbox | applied
James Rodgers - GL | Aaron Dawkins | District of Columbia |  | APPROVED 6.7 | NA | Applied-Pepco | Dropbox | applied
Omotayo Ogundana - GL | Thornton Fennell | PG County |  | STIP - ID | need info |  | ELD on Hold | applied
Timothy Dixon - SL | John Lee (Inside Sales) | Howard County |  | NEED CORRECTION | need action | Have Bill-BGE | Sunnova Design//200 amp/Waiting fo Client Consultation
Karen Ireland - CASH | John Lee (Inside Sales) | Montgomery County |  | N/A | NA | Applied-Pepco | Dropbox | applied
James Ortmann | John Lee (Inside Sales) | PG County |  |  | NA | Applied-Pepco | Dropbox | applied
Christopher Arzadon - SL | John Lee (Inside Sales) | Prince William County |  | APPROVED 6.8 | need action | Have Bill-Dominion | Dropbox
Olawale Tolulope Ayorinde - SN | IDC (Ishmael) | PG County |  | N/A | need action | Have Bill-Pepco | 200 amp/In progress | applied
Emma Davenport - DV | Skylighting | Baltimore County |  | APPROVED 6.8 | NA | Have Bill-BGE | Site Visit Requested
Matthew Beyers - DV | Skylighting | Frederick County |  | STIP - ACH | need action | Applied Potomac | Dropbox
Christopher Means - SL | Eric Strouse | Kanawha County | WV | APPROVED 6.8 | NA | Applied Appalachian | Dropbox
Charles Messerschmidt - GL | Ric Peters | Anne Arundel County |  | APPROVED 6.9 | NA | Applied-BGE | Dropbox
Harold Gerhart - GL | Quativa | Cumberland County |  | CHANGE ORDER? | NA | Have Bill PPL | Inverter Details N/A
Justin Strickland - GL | Quativa | Cumberland County |  | APPROVED 6.9 | NA | Have Bill-PPL | Everbright Design N/A
Berta Lidia - GL | Marcelo Ortiz | Frederick county |  | APPROVED 6.9 | NA | Have bill potomac
Kenneth Blankenship - SL | Eric Strouse | Nicholas county | WV | STIP - OWNERSHIP | NA |  | In Progress
Keith Scarsdale - SL | Mark Davis | Culpeper County |  | IN REVIEW | NA
Sean Magee - CASH | Cinthia Rivera | Loudoun county |  | N/A | NA | Have bill dominion | Drop Box
Todd Benbow - DV | SkylightNGR | Charlotte County |  | IN REVIEW | NA |  | ELD On Hold/MSP Pics Needed
Jlicery Diaz - SL | Eric Strouse | Kanawha County | WV | STIP - OWNERSHIP | NA | Have Bill Appalachian AND hoi | drop Box
Austin Snyder - GL | Voltaic (Freddye Jackson) | Lehigh County |  | IN REVIEW |  | PPL | Dropbox
Luis Rosas - GL | Justin Hall | PG county |  | IN REVIEW |  |  | ELD On Hold/MSP Pics Needed
Fatoumatta Bah - DV | SkylightNGR | Frederick county |  | IN REVIEW | need action | Have bill potomac | ELD On Hold/MSP Pics Needed
Jose Martinez - GL | Marcelo Ortiz | Montgomery County |  | IN REVIEW |  |  | In Progress

## PA
NAME | SALES REP | COUNTY | STATE | NTP | HOA | Interconnection | Design | Permit | Installation | Inspection | Meter Change | Access | Registration | PTO Uploaded | SRECs | MD Grant | QA | CANCELLED | PEARL CERTIFICATION
Angel M Lima - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done
Dan Notestein - CASH | Sam Albert | Montgomery County/Town of Blacksburg |  | N/A | approved | Approved VTES | Done | issued | Installation Completed
Juan L Guillen - GL | Thirza Iglesias | Frederick County |  | APPROVED 1.21 | approved | Approved Rappahannock | Done | issued | Installation Completed | Passed | Applied
Fizel Jabbar - DV | Aaron Dawkins | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | site created |  | Done | Done | Done |  |  | Done
Jose Chacon - GL | Carlos Cueto | PG County |  |  | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Julio Fuentes - GL | Carlos Cueto | Montgomery County |  | APPROVED 1.07 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Misael Guillermo - SN | Thornton Fennell | PG County |  |  | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Payment pending | Payment pending |  |  | Done
Willie Ford - GL | Thornton Fennell | PG County |  | APPROVED 1.05 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Yolanda Zelaya - GL | Sarah Romero | PG County |  | APPROVED 1/10 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Mark Reid - GL | Aaron Dawkins | PG County |  | CANCELED |  |  | Done | [10 empty] | YES
Lynne Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 1/20 | N/A | Approved-Pepco | Done | Issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | Done
Raymond Marquis - GL | Noblesolar | Norfolk County |  | APPROVED 2.4 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Jessie Miles - GL | Noblesolar | Norfolk County |  | APPROVED 1/12 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Yilia Jackson - SN | Ted Brown | Baltimore City |  | N/A | NA | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | done |  | Done
Ronny/Taylor Sylvester - GL | Noblesolar | Chesapeake City |  | APPROVED 2.8 | NA | Approved Dominion | Done | Issued | Installation Completed | Passed | Applied | Done |  | Received | Done
Kathryn Alexander - CASH | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Charles Cucina - DV | Danny Dubois | FrederickCounty |  | N/A | NA | Approved Potomac | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Miguel Angel Vernal Nolasco - GL | Sarah Romero | Baltimore County |  | LOAN CANCELED | NA | Have bill | [11 empty] | Yes
Juan Martinez - DV | Sarah Romero | Winchester City |  | N/A | NA | Approved SVEC | Done | issued | Scheduled 6/9
Jose H. Baca Oseguera - GL | Ana Romero | PG County |  | APPROVED 2.8 | NA | Approved-Pepco |  | issued | Installation Completed | Passed | Applied | Done | [6 empty] | Done
Oluseyi Ajayi - GL | Noblesolar | Chesapeake City |  | APPROVED 1.28 | applied | Approved Dominion 02/15/2022 | DONE | Issued | NA
Darryl Girtz - GL | Noblesolar | Norfolk City |  | APPROVED 1.31 | NA | Approved Dominion | Done | Applied-1/24 | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Gerry Evans - GL | Noblesolar | Newport News City |  | APPROVED 1.24 | approved | Approved Dominion | Done | issued | Installation Completed
Matthew Griffin - GL | Noblesolar | VA Beach City |  | APPROVED 1.25 | NA | Approved Dominion | Done | issued | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Donald Deely - CASH | Sam Albert | Allegheny county | PA | N/A | NA | Approved DLC | Done | Issued | TBS
Brayan Godines - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | done |  | Done | Done | Done |  |  | Done
Matthew Gomez - SL | Roberto Smith | PG County |  | APPROVED 1.24 | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Maxie Lawton -GL | Volt (Ishmael) | PG County |  | APPROVED 1.24 | approved | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Engracio Edesar Abris - DV | Danny Dubois | Arlington County |  | N/A | NA | Approved 03/01/2022 | Done | issued | Installation Completed | Passed |  | Done | [6 empty] | Done
Chris Luk - Cash | Richard Thrutchley | Fairfax County |  | N/A | approved | Approved Dominion | Done | issued | Scheduled 6/3 |  |  | Done
Nabil Ahmed - SL | Roberto Smith | Montgomery County |  | APPROVED 1.28 | approved | Approved Potomac | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | DONE | Done |  |  | Done
Sharon Flowers - DV | Jedi | PG County |  | CANCELED | applied | Approved-BGE | Done | issued
Maricela Pena - GL | Sarah Romero | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | [9 empty] | Done
Malik Abdunafi - SL | Jedi | Baltimore City |  | APPROVED 2.7 | NA | Approved-BGE | Done | Issued | TBS
Delphine London - NS | Noblesolar | VA Beach City |  | APPROVED 2.7 | approved | Approved Dominion | Done |  | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Gary Hill - GL | Noblesolar | York County |  | APPROVED 1.28 | APPROVED | Approved Dominion | Done | applied | Installation Completed
Carmen Bona - SN | USA Solar Network | Montgomery County *PA* | PA | N/A | NA | Applied PECO | Done
Tyleek Harris - GL | Noblesolar | Newport News City |  | APPROVED 2.7 | applied | Approved Dominion | Done | issued
Harrison Eacho - GL | Noblesolar | Norfollk City |  | APPROVED 1/28 | NA | Applied Dominion | Done
Olawole Olayinka - GL | Volt Solar (Freddye) | Howard County |  | APPROVED 1/28 | approved | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | V.S
Justin Shoemaker - GL | Noblesolar | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | N.S
Adewale Daramola - GL | Noblesolar | Chesapeake City |  | APPROVED 1.31.22 | applied | Approved Dominion | Done
Silvia Rivera - DV | Sarah Romero | City of Frederick |  | N/A | NA | Approved-Potomac Edison | Done | issued | TBS
Darwin A Fuentes - GL | Alberto Sosa | PG County |  | APPROVED 2.3 | NA |  | Dropbox | issued | [9 empty] | Yes
Charles Hiller - EZ | Sam Albert | Pike County | PA | Declined by EZSolarLoan | NA | Applied Met-Ed | Done | [10 empty] | Yes
John Coombs - SL | Roberto Smith | Baltimore County |  | APPROVED 2.1 | NA | Approved-BGE | Done | issued | Installation Completed | [9 empty] | Done
Amy Cervantes - EZ | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Eli Apuya - GL | Noblesolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Done
Brett Dash - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved dominion | Drop Box
Alexander Vasquez Fernandez - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved-dominion | Done
Taiwo Olayinka - GL | Volt Solar (Freddye) | Anne Arundel County |  | APPROVED 2.2 | approved | Approved-BGE | Done | in review | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jessica Green - SN | USA Solar Network | Westmoreland County | PA | CANCELED | N/A | Applied - Westpenn Power | Drop Box | issued
William Bryan - GL | USA Solar Network | Bucks County | PA | APPROVED 2.3 | N/A | Applied PECO | Done | issued
Kimberly Hayes - GL | USA Solar Network | Luzerne County | PA | APPROVED 2..3 | N/A | Approved PPL WO 58650550 | Done | issued | Installation Completed | [9 empty] | U.S solar network
Devin Sharp - GL | USA Solar Network | Pittsylvania County |  | CANCELED | NA | Have Bill Danvill | ELD On Hold | [10 empty] | Yes
James Spadoni - GL | USA Solar Network | Northampton County | PA | APPROVED 2.4 | N/A | Applied Met ED | Done
Edward Coley - CASH | USA Solar Network | Montgomery County *PA* | PA | N/A | NA | Approved PECO | Done |  | TBS - Roof Pending
Christopher Doane - GL | NobleSolar | Suffolk City |  | APPROVED 2.4 | applied | Approved-dominion | Drop Box
David Nicklas - CASH | Sam Albert | Allegheny county | PA | N/A | NA | Approved DLC | Done
Margaret Galega - SL | Joseph Allo | PG County |  | APPROVED 2.4 | applied | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Raymond Kabacinski - GL | NobleSolar | Norfolk City |  | APPROVED 2.7 | NA | Approved-dominion | Done | B-issued | Installation Completed |  | Applied | Site Created |  | Received | DONE |  |  |  | N.S
Karen Songwe - SL | Aaron Dawkins | PG County |  | APPROVED 2.8 | applied/NO HOA for this address | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | 22.57 |  |  | Done
Jose H Vega Carapia - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | N/A | Approved - potomac Edison | Done | issued
Jonas Chicas - DV | Sarah Romero | Louisa County |  | N/A | NA | Approved-Dominion | Done | issued | Installation Completed | [9 empty] | Done
Joy Dalesandro - GL - ON HOLD | NobleSolar | Chesapeake City |  | APPROVED 2.9 | applied | Applied Dominion | Done
Christopher Nunley - GL | SolarStrong | Berkeley County |  | APPROVED 3.23 | NA | Approved Potomac WV | Done | in review | Installation Completed | Passed | Applied | DONE
Kevin Coates - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Francis Hawkins - SL | Thornton Fennell | Charles County |  | APPROVED 2.24 | NA | Approved SMECO | Done | issued | Installation Completed | Passed | Approved | DONE |  | Done | Done | 22.2 |  |  | Done
Jon Walman - DV | Skylightnrg | Stafford County |  | N/A | NA | Project Cancell (James Nguyen) | Done | [10 empty] | Yes
Britteny Stone-Joel - GL | NobleSolar | Isle of Wight County |  | APPROVED 3.1 | approved | Approved-Dominion | Drop Box | issued | Installation in Progress |  |  | DONE
Donna Delgado-Johnson - SL | Thornton Fennell | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  | Done |  |  | Done
Kenneth King - GL | NobleSolar | Hampton City |  | APPROVED 2.14 | N/A | Approved-Dominion | Done | issued | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Jaramie York - SN | Jedi | Charles County |  | CANCELED | NA | Have Bill SMECO | [11 empty] | Yes
Jose Oscar Velasco - GL | Carlos Cueto | Montgomery County |  | APPROVED 2.15 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Melvin Blackwell - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved- Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Kenmanze Edmonds - GL | NobleSolar | Isle of Wight County |  | PROJECT CANCELED | NA | Have bill | [11 empty] | Yes
Christopher Bonzek - CASH | Inside Sales | Newport News City |  | N/A | NA | Approved dominion | Done | issued | TBS - Rec Panels
Mary Clowe - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mridul Gupta - DV | Skylightnrg | Henrico County |  | N/A | approved | Approved dominion | Done | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | skylight
Jose Blanco - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Blanca Arevalo - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mark Whitling - GL | NobleSolar | VA Beach City |  | APPROVED 2.14 | deal cancelled | deal cancel | [11 empty] | Yes
Joe Leugers - GL | NobleSolar | Suffolk City |  | APPROVED 2.23 | approved | Approved dominion | Drop Box | issued | Installation Completed |  | Applied | Done | [6 empty] | N.S
Alejandra Juarez - GL | Raf Solar | PG County |  | APPROVED 2.15 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Paul Warren - GL | NobleSolar | VA Beach City |  | APPROVED 2.15 | need action |  | Drop Box | [10 empty] | Yes
Miguel Vernal - GL | Raf Solar | Baltimore County |  | APPROVED 2.15 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
William Smith - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.15 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Eros Lazzerini - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Cletus Ayuk - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved |  |  | Done | Done | Done |  |  | Done
Hannah Emert - GL | NobleSolar | Suffolk City |  | APPROVED 2.17 | applied | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Franklin A Garcia - GL | Alberto Sosa | PG County |  | APPROVED 2.16 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Guillermo West - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.18 | NA | Approved- PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Shirlene Ogburn - DV | Skylightnrg | Charles County |  | N/A |  | Project Cancel by Dealer | [11 empty] | Yes
Kelsey Mijal - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | NA | Approved dominion | Done |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Danielle Goodrum - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | applied | Approved dominion | Done
Nathan Carl - GL | NobleSolar | Portsmouth City |  | APPROVED 3.8 | NA | Approved dominion | Drop Box | in review | Scheduled 5/27 | Passed
Meaghan Jenks - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Applied | Done |  |  | DONE |  |  |  | Done
Queenie May Escubio - EZ |  | Portsmouth City |  | APPROVED 2.17 | NA | Approved dominion | Done | in review | Scheduled 5/28 | Passed | Applied
Alexander Phillips - GL | NobleSolar | Chesapeake City |  | APPROVED 2.17 | applied | Approved dominion | Done | issued
`William Sanders - CASH | Solarsurge | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | in review
Michelle Gomez - GL | Alberto Sosa | PG County |  | APPROVED 3.1 | NA | Approved-Pepco | Drop Box | issued | [9 empty] | Yes
George Knight - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | need policy no# | Drop Box
May Petalcorin - GL | NobleSolar | Suffolk City |  | PROJECT CANCELED | need action | [12 empty] | Yes
DePaul Griffin - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Richard Taylor - GL | NobleSolar | VA Beach City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Rebecca Phillips Ferguson - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Peter Keller - CASH | Solarsurge | Montgomery |  | N/A | NA | Have bill-Pepco
Malcolm Dixon - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Michael Osumlalu - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Constance Kinge -SL | Aaron Dawkins | PG County |  | APPROVED 2.21 | NA | Approved PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Jennifer Joynes - SL | Jedi | Pricness Ann |  | APPROVED 2.21 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | TBS
Ruperto Rivera - GL | Raf Solar | Montgomery County |  | APPROVED 2.21 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed |  | Site created | [6 empty] | Done
Salvador Cueva - GL | Thirza Iglesias | City of frederick |  | APPROVED 2.21 | NA | Approved Potomac Edison | Drop Box | issued | Installation in Progress
Martin Medina Estrada - GL | Carlos Cueto | Town of Elkton |  | APPROVED 2.25 | NA | Approved- PEPCO(Delmarva) | Drop Box | issued | TBS
Luisa Figaro - SL | Remesh Sartani | Princess Anne |  | APPROVED 2.25 | NA | Approved- PEPCO | Drop Box | issued | Installation Completed
Fernando Ortez - GL | Raf Solar | Prince William County |  | APPROVED 2.25 | NA | Approved NOVEC | Done | [10 empty] | Yes
Telesfora Briones - GL | Raf Solar | City of Annapolis |  | APPROVED 2.21 | approved | Approved- BGE | Done | applied
Lap T. Vo - SL | Michael Reid | Montgomery County |  | APPROVED 2.21 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Candy Huynh - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | applied | Approved Dominion | Drop Box |  | Installation Completed | [9 empty] | N.S
Keith Layne - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Oscar Jimenez - GL | Raf Solar | Prince william |  | APPROVED 2.25 | NA | Approved - NOVEC | Drop Box | In review
George Hoskin - SL | Michael Reid | Montgomery County |  | APPROVED 3.4 | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Octavia Pearson - GL | Thornton Fennell | PG County |  | APPROVED 2.24 | NA | Approved - PEPCO | Drop Box | issued | Installation in Progress | Passed | Approved |  |  | Done | Monit not done | Done
Nicolas Lovo - GL | Raf Solar | Charles County |  | APPROVED 3.1 | applied | Approved - SMECO SMECOINT-08593 | Drop Box | Applied
Marcos A Flores - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | NA | Approved potomac | Drop Box | issued | TBS
Paul Rudicki - GL | NobleSolar | Chesapeake City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box |  | Installation Completed |  | Applied | Done |  |  | DONE |  |  |  | N.S
Katherine Heun - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Kyle Scherele - GL | NobleSolar | Hampton City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box | in review | Installation Completed | [9 empty] | N.S
Myrna Michelle Flores - GL | NobleSolar | VA Beach City |  | APPROVED 3.1 | approved | Approved dominion | Drop Box |  | Installation Completed |  | Applied | Done | [6 empty] | N.S
Santos Soto - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Drop Box | [10 empty] | Yes
Mary Rampolla - DV | Skylightnrg | Howard County |  | N/A | NA | Approved- BGE | Drop Box | [10 empty] | Yes
Tracy Winters - SN | USA Solar Network | Delaware County | PA | CANCELED | need info | Have Bill - PECO | [11 empty] | Yes
Santos Rivera - GL | Raf Solar | Frederick County |  | APPROVED 2.25 | NA | Have Bill - Dominion | Drop Box | [10 empty] | Yes
Leslie Braithwaite - DV | Skylightnrg | PG County |  | N/A | NA | Applied - PEPCO | Done | in review | [9 empty] | Yes
Keith Wilburn - GL | NobleSolar | Suffolk City |  | APPROVED 2.25 | applied | Approved dominion | Drop Box
Thanaporn Cockran - SL | Jedi | Anne Arundel County |  | APPROVED 5.13 | NA | Approved-BGE | Drop Box | issued | TBS
Florimon Arrey Ndip Etta - GL | Aaron Dawkins | PG County |  | APPROVED 2.28 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Site created |  | Done | DONE | Done |  |  | Done
Yamarco Figaro - SL | Remesh Sartani | Wicomico County |  | APPROVED 2.28 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | Installation Completed | [9 empty] | Done
Veronica Brooks - SL | Thornton Fennell | PG County |  | APPROVED 2.28 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | Monit not done | Done |  |  | Done
Garrye Hepburn - GL | Skylightnrg | PG County |  | APPROVED 3.1 | approved | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | skylight
Adriene Muhammad - DV | Skylightnrg | Branchville |  | N/A | NA | Approved Dominion | Drop Box
Ron Leese - DV | Skylightnrg | Carroll County |  | N/A | NA | Approved-BGE | Drop Box | applied
Samuel Nelson - GL | Inside Sales | Distric of Columbia County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Site Created
Jorge A. Soto Sanabria - GL | Thirza Iglesias | PG County |  | APPROVED 3.2 | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Site Created | [6 empty] | Done
Federico Vega - GL | Thirza Iglesias | Winchester City |  | APPROVED 3.2 | NA | Applied SVEC | Drop Box | issued
Tae Kim - DV | Skylightnrg | Montgomery County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS | [8 empty] | Yes
Raul Morales Martínez - GL | Carlos Cueto | PG County |  | APPROVED 3.8 | NA | Approved-Pepco | Drop Box | issued | Installation In Progess
Jose Campos - GL | Carlos Cueto | PG County |  | APPROVED 3.4 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Jesus Aguilera - GL | Raf Solar | PG County |  | APPROVED 3.4 | HOA approved | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done |  | SS above 20 |  |  | Done
Miguel Mendoza - GL | Raf Solar | Gaithersburg City |  | APPROVED 3.4 | approved | Approved-PEPCO | Drop Box | in review | Installation In Progess
Steven Miles - GL | Volt Solar (Freddye) | Accokeek County/PG |  | APPROVED 3.9 | NA | Approved SMECO | Drop Box | issued | Installation Completed | [9 empty] | V.S
Virginia Chaziva - GL | Aaron Dawkins | PG County |  | APPROVED 3.9 | applied | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Dilsa Rosales Moscoso - GL | Ana Romero | Montgomery County |  | APPROVED 3.3 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  |  | Done |  |  |  | Done
Mary Satterwhite - SN | Jonathan Ngo | Loudoun County |  | N/A | approved by Jon | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received |  |  |  |  | Done
Patrick Brown - SL | Ric Peters | Baltimore County |  | APPROVED 3.9 | NA | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Philip Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 3.9 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Trad Leavitt - DV | Skylightnrg | Frederick County |  | N/A | approved | Approved Rappahannock | Drop Box | issued | Installation Completed | Passed | Applied | Done
Dante Fenwick - GL | Skylightnrg | PG County |  | APPROVED 3.9 | in review | Approved-Pepco | Drop Box | issued
Steve Kinaman - EZ | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Scheduled 6/2 | Passed | Applied
Raja Balasubramanian - CASH | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | Done
Jian Liu - SL | Roman Bondari | Loudoun County |  | APPROVED 3.11 | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Received |  |  |  |  | Done
Michael Mills - SL | Jedi | Wicomico County |  | APPROVED 3.11 | NA | Approved - PEPCO(Delmarva) | Drop Box | applied | Scheduled 6/2
Karla Martinez - GL | Raf Solar | Fauquier County |  | APPROVED 3.15 | approved | Approved Dominion (modifications) | Drop Box | in review (modifications) | Installation in Progress
Rita Fallon - SL | Ric Peters | Anne Arundel County |  | APPROVED 3.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
David Sheffey - SN | Thornton Fennell | PG County |  | N/A | NA | Applied - PEPCO | Drop Box | issued
Jaiyeola Oluwatosin - GL | USA Solar Network | PG County |  | APPROVED 3.14 | need info | Applied- PEPCO | Drop Box | in review
Ureka Wise - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.14 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Adam Karaffa - GL | USA Solar Network | Westmoreland County | PA | APPROVED 3.14 |  | Approved Westpenn Power | Drop Box
Martha Rodriguez - DV | Michael Reid | Prince William County |  | N/A | approved | Approved- Dominion | Drop Box | Applied
Jordan Calabrese - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
Joseph Sheffey - DV | Thornton Fennell | PG County |  | N/A | NA | Approved-PEPCO | Drop Box | in review | Installation Completed | [9 empty] | Done
Jose Yaselli - SN | Jedi | Carroll County |  | N/A | NA | Approved-BGE | Drop Box
Saqr Alawdi - GL | NobleSolar | Hampton City |  | APPROVED 3.23 | NA | Have bill and HOI | ON HOLD | [10 empty] | Yes
John Delgadillo - DV | Jonathan Ngo | Chesterfield County |  | N/A | NA | Approved- Dominion | Drop Box | issued | Installation Completed | [9 empty] | Done
Joel Gonzalez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 3.17 | NA | Approved 4/4/22 | Drop Box | issued | Installation Completed | Passed | Applied | [7 empty] | Done
Arthur Cockran - SL | Jedi | Queen Anne County |  | ON HOLD UNTIL NTP | NA | Approved Choptank Electric | Drop Box | in review
Jose R Guzman Delcid - GL | Ana Romero | City of frederick |  | CHANGE ORDER 5.24 | NA | Approved potomac | Drop Box | issued
Janet Thompson - CASH | Inside Sales | Stafford County |  | N/A | approved | Approved- Dominion | Drop Box | in review
Omkar Prabhu - CASH | Inside Sales | Monroe County | PA | N/A | NA | Approved - PPL | Drop Box | issued | TBS
Delia/Joseph Palmer - GL | NobleSolar | Suffolk City |  | CANCELED | need action | have bill & HOI | ELD on hold | [10 empty] | Yes
Misael Moreno - GL | Raf Solar | Anne Arundel County |  | APPROVED 3.31 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Rose Bennett - DV | Skylightnrg | Howard County |  | PROJECT CANCELED | need action | Cancelled by Skylight (Adrienne) | [11 empty] | Yes
Rebecca Gaither - SL | Thornton Fennell | PG County |  | CANCELED | [13 empty] | Yes
Joy Alorro - DV | Danny Dubois | Fairfax County |  | N/A | applied | Approved Novec | Drop Box | in review
Elizabeth Mason - DV | Danny Dubois | Staunton County |  | N/A | NA | Approved- Dominion | Drop Box
Clifford McQueen - GL | Volt (Ishmael) | PG County |  | APPROVED 5.13 | NA | Approved- Pepco | Drop Box | issued | Installation in Progress
Deborah Bailey - SN | Jedi | Baltimore County |  | N/A | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Dawn Banks- SN | Inside Sales (Ishmael) | Charles County |  | N/A | NA | Approved - SMECO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Chikodili Ugokwe - SN | Thornton Fennell | PG County |  | N/A | NA | Approved- BGE | Drop Box | in review | Installation in Progress
Maximiliano Posada - GL | Ana Romero | Montgomery County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Conor P. Williams - CASH | Inside Sales | District of Columbia |  | N/A | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Done | Done |  |  |  | Done
Francisco Jacobo Sanchez - GL | Ana Romero | PG County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | [9 empty] | Done
Dustin Schultz - GL | USA Solar Network | Calvert County |  | APPROVED 3.23 | NA | Conditionally Approved SMECO | Drop Box
Mary Ukwu - SL | Aaron Dawkins | PG County |  | APPROVED 4.1 | approved | Approved- BGE | Drop Box |  | Installation Completed | Passed | Applied | [7 empty] | Done
Liliane Batista - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 3.31 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | 2022-06-01 | [8 empty] | Done
Sharon McGee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.1 |  | Applied-Pepco | Drop Box | issued | Scheduled 5/30
Sandor Slager - CASH | Volt Solar (Brandon) | Distric of Columbia County |  | N/A | NA | Approved- PEPCO | Drop Box | issued | Installation in Progress
James D. Bryden - EZ | Inside sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - U anchor check
Anthony Field - DV | SkylightNRG | PG County |  | N/A | NA | Have Bill PEPCO | 200AMP | applied
Grace Brunner - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - Roof repair pending
Jeremy Black - CASH | Inside Sales | Lycoming County | PA | N/A | NA | Approved PPL | Drop Box | issued | TBS
Phil Nawrocki - CASH | Inside Sales | Allegheny County | PA | N/A | NA | Approved DLC | Drop Box
Deborah Whitaker - GL | Jedi | Baltimore City |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Tod Harach - EZ | Inside Sales | Lancaster County | PA | N/A | NA | Approved PPL | Drop Box
Guillermo Mendoza - GL | Raf Solar | Montgomery County |  | APPROVED 3.26 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Leonel Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.10 | NA | Approved REC | Drop Box | Applied-5/26
Renardo Williams - DV | Jedi | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Ronisha Dickerson - GL | Volt (Ishmael) | PG County |  | APPROVED 3.27 | approved | Conditional approved SMECO | Drop Box | issued | TBS |  |  | done
Jose Coreas - GL | Carlos Cueto | Baltimore County |  | APPROVED 3.27 | Cancelled by Carlos |  | ELD on Hold | [10 empty] | Yes
Peter Kurilla - GL | USA Solar Network | Montgomery County *PA* | PA | APPROVED 4.11 | NA | Applied PECO | Drop Box
Tatiana McCook - GL | Volt Solar (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Rachelle Stephens - SL | Remesh Sartani | Charles County |  | APPROVED 4.20 | NA | Approved SMECOINT-08682 | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Catherine Heath - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | [8 empty] | V.S
De'Andre Sheppard - DV | Skylightnrg | Baltimore County |  | N/A | NA | BGE | Drop Box
Sandra Dieterle - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Marisol Muñoz - GL | Bianca del Castillo | City of Rockville |  | APPROVED 5.3 | NA | Approved-Pepco | Drop Box | issued | TBS
Donnie Waites - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued
Faye Coles - DV | Skylightnrg | Anne Arundel County |  | N/A | approved | Approved-BGE | Drop Box | applied
Gerald Newsome - DV | Skylightnrg | Charles County |  | N/A | Approved | Approved -SMECO | Drop Box | issued
Queenie May Escubio - EZ | Inside sales | Prince william county |  | N/A | approved | Approved Dominion | Drop Box | Applied
Santosha Lee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.27 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | V.S
Jose Morales - GL | Marcelo Ortiz | Stafford County |  | CANCELED | NA | Applied NNEC | Drop Box | [10 empty] | Yes
Robert & Suzette Kinstler - GL | USA Solar Network | Montgomery County*PA | PA | APPROVED 4.1 | NA | Approved PECO | Drop Box | [10 empty] | Yes
Peter Hughes | Double Inside Sale |  |  |  |  | Applied Rappahannock | Drop Box | in revie
Terence Collins - GL | Skylightnrg | Baltimore County |  | APROVED 3.31 | NA |  | Canceled Dt:3/31/22 | [10 empty] | Yes
Dustin Blankenship - GL | USA Solar Network | Carroll County |  | APPROVED 3.31 | NA | Approved Potomac GEN-MD-8107 | Drop Box | in review
Jay Vodela - SN | Jonathan Ngo | Montgomery County |  | N/A | approved | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jaime Salazar - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Melanie Choh - GL | Volt (Ishmael) | PG County |  | APPROVED 3.31 | Approved | Approved-Pepco | Drop Box | issued | TBS
Dawn Peterson - GL | IDC | PG County |  | APPROVED 4.1 | approved | Approved-Pepco | Drop Box | issued | TBS |  |  | DONE
Kwame Gyamfi - SL | Derrol Mcclaren | Montgomery County |  | APPROVED 5.6 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Yvette Dowtin - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | DONE
Bianca Christie - SL | Derrol Mcclaren | Baltimore County |  | APPROVED 4.20 | NA | Approved -BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Silvia Centeno - GL | "Rafael Cabello (Raf Solar )" | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Leroy Inabinett - SL | Aaron Dawkins | Baltimore City |  | CANCELEED | NA | Approved-BGE | Drop Box | In review | [9 empty] | Yes
Edgar Bonilla - GL | Marcelo Ortiz | PG County |  | APPROVED 5.2 | approved | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Marina del Carmen Bonilla - GL | Carlos Cueto | PG County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Reina Alfaro - GL | Marcelo Ortiz | Montgomery County |  | CANCELEED | NA | Approved-Pepco | Drop Box | applied | [9 empty] | Yes
Silvio Espinal - GL | Jorge Carias | Montgomery County |  | APPROVED 4.5 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Ana Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.6 | NA | Applied REC | Drop Box
Silvia Centeno - GL | Raf Solar | PG County |  | APPROVED 4.12 | NA | APPROVED-PEPCO | Drop Box | applied | Installation in Progress
Carlos Hoschmin - GL | Raf Solar | Fairfax county |  | CANCELED | cancel by SR |  | Canceled Email Dt:4/8/22 | [10 empty] | Yes
Colin Eckman - CASH | Inside Sales | Prince William County |  | N/A | approved | Approved dominion | Drop Box | Applied
Jonathan Ford - CASH | Inside Sales | Carrol County |  | N/A | NA | Applied-BGE | Drop Box
Rene Lemus - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Pierre Tekem Noumbi - DV | Skylightnrg | PG County |  | N/A | need action |  | Drop Box | issued
Jose de la Cruz Reyes - GL | Carlos Cueto | Frederick County |  | APPROVED 4.12 | Approved | Approved potomac | Drop Box | issued | TBS
Roger Yobani Diaz - GL | Bianca del Castillo | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Jose Castillo - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | approved | Approved Potomac | Drop Box | issued | Installation Completed | Passed | Applied | Done
Elizabeth Mason - DV | Inside Sales | (Chesterfield) |  | N/A | approved | Applied Dominion | Drop Box | issued
Jose Perez - GL | Raf Solar | PG County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Applied
Juan Villatoro - GL | Marcelo ortiz | Anne Arundel County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Scheduled 5/23 |  |  | Done
Vinicia R Torres - GL | Ana Romero | PG County |  | APPROVED 4.12 | NA | Approved-BGE | Drop Box | issued | Installation Completed
Juan Soto - GL | Raf Solar | PG County |  | APPROVED 4.26 | NA | Applied-Pepco | Drop Box | in review
Nestor Tchinda - SL | Derrol Mcclaren | Montgomery County |  | ON HOLD UNTIL NTP |  | Have Bill BGE
Bernice Alston - GL | Thornton Fennell | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Josias Tekle - DV | Skylightnrg | city of hagerstown |  | N/A | approved | Approved potomac | Drop Box | applied
Tim Johnson - DV | Skylightnrg | St. Mary's County |  | N/A | NA | Approved SMECO | Drop Box | issued | TBS
Theresa Terry - GL | Volt Solar (Freddye) | PG County |  | CANCELED | need info | Have Bill SMECO | 200AMP | applied | [9 empty] | Yes
Louis Drury - GL | Elijah Sutton | Calvert County |  | APPROVED 4.12 | NA | Approved SMECO | Drop Box
Hakeem Ayodeji - SN | Samuel Edwards | Charles County |  | N/A | need info | Conditionally Approved Smeco | Drop Box | issued
Kenisha Jefferson - SN | Theodore Brown | PG County |  | N/A | approved | Approved-PEPCO | Drop Box | issued
Rosa Garcia - GL | Carlos Cueto | PG County |  | APPROVED 4.13 | NA | Approved-BGE | Drop Box | issued | Installation in Progress
Abdullah Amin - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.14 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Demetri Kappatos - SL | Charles Carufel | Loudoun County |  | IN REVIEW | IN REVIEW |  | Drop Box
Teodoro Carranza - GL | Ana Romero | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Done
Vicki Powell - DV | Skylightnrg | Cecil County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Kenneth Pilpel - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Potomac | Drop Box | issued | TBS
Jose Resendiz - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Yessenia Marilu Cruz - GL | Carlos Cueto | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Lydia Hagos - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Latanya Cannady - GL | IDC | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Austin Johnson - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.19 | approved | Approved SMECO | Drop Box | issued |  |  |  | Site created
Kirk Ramirez - EZ | Tim Clark | PG County |  | N/A | applied | Approved-Pepco | Drop Box | in review
Derell Kennedo - EZ | Peter kyke | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Drop Box | in review
Ramon Eclavea - DV | Danny Dubois | Prince William County |  | N/A | applied | Approved Novec | Drop Box | Applied
Ian Roach - SL | Aaron Dawkins | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | in review | TBS
Sade Brown - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued
Jason Coy - CASH | Tim Clark | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
William Burgess - CASH | Tim Clark | Arlington County |  | N/A | NA | Approved Dominion | Drop Box | issued
Paul Leger - DV | Elijah Sutton | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Park - DV | Havar Espedal | Distric of Columbia County |  | N/A | already approved by HAVAR | Approved-Pepco | Drop Box | in review
John Greesh - DV | Havar Espedal | Distric of Columbia County |  | N/A | need info | Approved-Pepco | Drop Box | in review
Matthew Lewis - DV | Derrol Mcclaren | PG County |  | CANCELED | NA | Applied-Pepco | Drop Box | in review | [9 empty] | Yes
Marion Bedford - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  | Cancel by Dealer | Designed But Canceled | applied | [9 empty] | Yes
Delcita Lemus - GL | Raf Solar | PG County |  | APPROVED 4.20 | NA | Approved-Pepco | Drop Box | in review
Maria Consuelo Baires - GL | Thirza Iglesias | Loudorn County |  | CANCELED |  | Project Cancelled | Drop Box | [10 empty] | Yes
Richard Vasquez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 4.25 | NA | Applied Dominion | Drop Box | issued
Abdi Mohamed - DV | Derrol Mcclaren | Montgomery County |  | N/A | applied | Approved Potomac | Drop Box | issued
Kuega Ekue - SL | Dawit Abraham | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daysi Martinez - GL | Bianca del Castillo | city of frederick |  | APPROVED 4.25 | NA | Approved Potomac | Drop Box | in review
Rotimi Shittu - SL | Thornton Fennell | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daniel Andres Yanez - GL | Carlos Cueto | Frederick County |  | APPROVED 4.25 | applied | Applied SVEC | Drop Box
James Arthur - SL | Jonathan NGO | Charles County |  | APPROVED 4.25 | approved | Conditionally Approved SMECO | Drop Box | issued
Andrian Cruz - DV | Derrol Mcclaren | Montgomery County |  | N/A | approved | Approved Potomac | Drop Box | issued | TBS
TRAVIS MELSON - SN | USA Solar Network | Petersburg City |  | N/A | NA | Have Bill Dominion HOI | On Hold
Matthew Dreitlein - EZ | Peter Kyke | Fairfax County |  | N/A | applied | Approved Dominion | Drop Box | issued
Melat & Fanual Dawit - EZ | Inside Sales | Distric of Columbia County |  | N/A | NA | Applied-Pepco | Drop Box | in review
David Brunco - CASH | Peter Kyke | Butler County | PA | N/A | NA | Approved Penn Power | Drop Box
Ethan Pacifico - DV | Danny Dubois | Town of Herndon |  | N/A | Approved | Approved Dominion | Drop Box | Issued
Fermin Kelly - SL | Remesh Sertani | Wicomico County |  | APPROVED 4.25 | NA | Approved-Pepco(Delmarva Power) | Drop Box | applied
Mike Mendley - DV | Skylighting | Montgomery County |  | N/A | no need for approval | Approved-Pepco | Drop Box | Issued
Adolfo Mata Garcia - GL | Carlos Cueto | PG County |  | CANCELED | NA | Applied-Pepco(Project Withdrawn) | Drop Box | applied | [9 empty] | Yes
Dawn Frisby - GL | Skylightnrg | PG County |  | ON HOLD UNTIL NTP | approved | Approved-Pepco | Drop Box | in review
Michael Chernau - CASH | Tim Clark | Henrico County |  |  | NA | Applied- Dominion | Drop Box | in review
Douglas Ross - GL | Skylighting | Montgomery County |  | APPROVED 5.19 | NA | Applied-Pepco | Drop Box
Melvin Hernandez - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop Box | issued | TBS
James M. McDermott - SL | Charles Carufel | Loudorn County |  | APPROVED 5.4 | Approved | Approved Dominion | Drop Box | in review | TBS
Doris Scott - GL | Mark Davis | PG County |  | CANCELED | need info | f | ELD on Hold | applied | [9 empty] | Yes
Nicholas Hinko - SL | Charles Carufel | Loudoun County |  | APPROVED 5.5 | Approved | conditional /Approved SMECO | Drop Box | in review | TBS
Karima Ali - DV | Skylighting | Loudorn County |  | N/A | applied | Applied - Dominion | Drop Box | in review
John Whelan - DV | Jedi | Frederick County |  | N/A | applied | Approved-Potomac | Drop Box | issued
Michael Sparks - DV | Jedi | Charles County |  | N/A | NA | approved-Smeco | Drop Box | issued
Travis Melson - GL | USA Solar Network | Chesterfield County |  | ON HOLD UNTIL NTP | NA | Applied- Dominion | Drop Box
Candance Watson - SN | Greg Jonhson - BBS | Chesterfield County |  | N/A | NA | Approved Dominion | Drop Box | issued
GARFIELD KELLIER - SN | Jonathan NGO | PG |  | N/A | applied | Applied-Pepco | Drop Box | in review
Thomas Hayhurst - DV | Skylightngr | Garrett County |  | N/A | to follow | have UB | 200 Amp/On Hold
Carlos M. Claros - GL | Marcelo Ortiz | Prince William County |  | APPROVED 5.2 | approved | Approved Dominion | Drop Box | Applied
Mary Borders - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Carolina Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.2 | NA | Applied-Pepco | Drop Box | in review
Tabitha Demaio - SL | Derrol Mcclaren | Charles County |  | ON HOLD UNTIL NTP | NA | need bill | 200 Amp/On Hold
Richard Cook/Betty Siu - DV | Elijah Sutton | Charles County |  | N/A | NA | conditional /Approved SMECO | Drop Box | issued
Jose Guzman - SN | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Approved- Dominion | Drop Box | Applied | [9 empty] | Yes
Giles Nathaniel Cooke Jr - GL | Thornton Fennell | PG |  | APPROVED 5.20 | NA | Approved-PEPCO | Drop Box | in review
Jose Arbaiza - GL | Carlos cueto | Montgomery County |  | APPROVED 5.10 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Marina I. Tejada - DV | Ana Romero | PG |  | APPROVED 5.7 | NA | Approved-Pepco | Drop Box | in review
Regan Crump - CASH | Inside Sales | Montgomery County |  | N/A | Approved | Applied Potomac | Drop Box | issued
Richard Fecher - CASH | Peter Kyle | Loudorn County |  | N/A | need action | Applied dominion | Dropbox
Sandra Schultz - GL | Mark Davis |  |  | CANCELED | [13 empty] | Yes
Fidel Santos - GL | Raf Solar | Montgomery County |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | applied
Lyle Craddock - GL | True Energy (David Twitty) | Boone County |  | APPROVED 5.5 | NA | Applied Applachian Power | Drop Box
Tamara Perez - GL | IDC | PG |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | in review
Crystal Sprowls - EZ | Inside Sales | Allegheny County | PA | N/A | need info | Have Dequesne Light | 200 Amp/On Hold
Vincent Lombardi - GL | True Energy (David Twitty) | Tucker County |  | APPROVED 5.23 | NA | Have Bill-MonPower | 200 Amp
Blake Bozeman - SN | Inside Sales | District of Columbia |  | N/A | NA | Approved-Pepco | Drop box | in review
Celia Delara - SN | Jonathan NGO | Hardford County |  | N/A | NA | Applied-BGE | Drop box | in review
Kemberly Gutierrez - SN | Thornton Fennell | PG County |  | N/A | NA | Applied-Pepco | Drop Box
Anthony Turner 1 - DV | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop box
Anthony Turner 2 - GL | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | BGE | ELD On Hold/MSP Pics Needed
Anselmo Guzman - GL | Raf Solar | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Renett Little - GL | IDC | PG County |  | APPROVED 5.10 | Approved | Approved-Pepco | Drop box | in review
Auildo Kelly Azor - SL | Remesh Sertani | Wicomico County |  | CANCELED | NA | Approved-Pepco(Delmarva Power) | Drop box | [10 empty] | Yes
Glenn Allander - GL | Daniel Gibson | Cumberland County | PA | APPROVED 5.10 | NA | Applied PPL | Drop box
Jacob Richmond- EZ | Sam Albert | Wythe County |  | N/A | need info | on Hold | Drop box
Sandra Gascon-Gracia - CASH | Sam Albert | Cumberland County | PA | N/A | need info | have bill PPL | 200 Amp (In Progress)
Brandy Shamrock - DV | Skylightnrg | Franklin City |  | N/A | NA | Approved dominion | Drop box
Ivy Freeman - SL | Charles Carufel | Cumberland County | PA | APPROVED 5.11 | applied | Applied Novec | Drop Box
Mariam Menkir - DV | Derrol Mcclaren | Charles County |  | N/A | in review | Approved SMECO | Drop Box | issued
Vivian Segovia - GL | Thirza Iglesias | Frederick County |  | CANCELED | NA | Approved-REC | Drop Box | [10 empty] | Yes
Frank Mestecky - GL | USA Solar Network | Pike County | PA | APPROVED 5.19 | applied | Applied Met-Ed | Drop Box
MANUEL GUTIERREZ - SN | Thornton Fennell | PG County |  | N/A | NA | Approved-BGE | Drop Box | in review
Olivier Komeka - DV | Skylighting | PG County |  | N/A | to follow | Need Bill | Drop Box | in review
Joseph Flora - GL | True Energy (David Twitty) | Cabell County |  | APPROVED 5.11 | NA | Metert Number require | Drop Box
Shenee Turner - GL | IDC | PG County |  | APPROVED 5.11 | applied | Approved-Pepco | Drop box | in review
Ramon Campos - GL | Carlos cueto | PG County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop box | in review
Richard Thornburgh - CASH | Michael Reid | Montgomery County |  | N/A | NA | Applied-Pepco | Drop box | Applied
Edward Holman - DV | Skylighting | Chesterfield |  | N/A | NA | need HOI | Drop box | [10 empty] | Yes
Maribel Giovanna Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Philippa & Danielle Durham - CASH | Inside Sales | Caroline County |  | N/A | need info | Conditional Approved-Choptank | Drop Box | applied
Kenia Benitez - GL | Marcelo Ortiz | Harrisonburg City |  | CANCELED | NA | Applied SVEC | Drop Box | [10 empty] | Yes
Luis Perez - EZ | Peter Kyle | Spotsylvania County |  | N/A | applied | Approved REC | Drop Box
Anthony Olaiya Oni - GL | Thornton Fennell | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop Box
Thai-Anh Perry - SL | Charles Carufel | Prince William County |  | STIP - OWNERSHIP | in review | Approved-Novec | Drop Box
MARLYN PIPER WILLIAMS - SN | Samuel Edwards | PG County |  | N/A | need info | Applied-Pepco | Drop Box | in review
Edward Miller - DV | Skylightnrg | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Collins - GL | Heath Dewalt (Nitro) | Charlottesville City |  | ON HOLD UNTIL NTP | need info
Susan Silman - GL | True Energy (David Twitty) | Kanawha County |  | APPROVED 5.16 | NA | Applied-Appalachian | Drop Box
Blanca R Guzman Escobar - GL | Ana Romero | Montgomery County |  | APPROVED 5.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Benjamin Bacon - DV | Skylighting | Frederick County |  | N/A | approved | Approved Potomac | Drop Box | issued
Jamie Summers - GL | Strong Solar | Kanawha County |  | APPROVED 5.18 | NA | Applied-Appalachian Power | Drop Box
Ravinder Mathaudu - SN | Samuel Edwards | Montgomery County |  | N/A | need info | need bill
Everth Alvarado - DV | Danny Dubois | Manassas City |  | N/A | need info | Need Info | Drop Box | [10 empty] | Yes
Kuele Ndingsa - GL | Mark Davis | PG County |  | APPROVED 5.27 | NA | Approved-BGE | Drop Box | in review
Jeff Boggs - GL | Strong Solar | Kanawha County |  | APPROVED 5.16 | NA | Applied-Apalachian Power | Drop Box
Joseph Cotterino - GL | Quativa | Carbon County |  | STIP - OWNERSHIP | NA | PPL | Drop Box
Nang and Hong Huynh - DV | Danny Dubois | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | issued
Isaias Bustamante - GL | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Applied Dominion | Drop Box | [10 empty] | Yes
Edith S Gonzalez Mejia - GL | Carlos cueto | Anne Arundel County |  | APPROVED 6.3 | applied | Approved-BGE | Drop Box | applied
Georgia Thomas - GL | Aaron Dawkins | PG County |  | APPROVED 5.119 | NA | Approved-Pepco | Drop Box | in review
Gabriel Rosenberg - SL | Charles Carufel | Fairfax County |  | APPROVED 5.19 | NA | need correct HOI | Drop Box | applied
Michael Newkirk Jr - SN | Ric Peters | Anne Arundel County |  |  | NA | Approved-BGE | Drop Box | applied
JACQUELIN MARTINEZ - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Carol Jackson - DV | Skylighting | Charles County |  | ON HOLD UNTIL NTP | to follow | Approved Smeco | Drop Box | applied
Wubishet Yizengaw - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | issued
Florinda Escobar - GL | Raf Solar | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Janice Walters - GL | Thornton Fennell | PG County |  | APPROVED 5.20 | NA | Applied-Pepco | Drop Box | in review
Rosalba Ayala Magana - GL | Thirza Iglesias | Frederick County |  | NEED CORRECTION/ADDRESS | need action | Applied-REC | Drop Box
Yessenia Rios rubio - SL | Dawit Abraham | PG County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
David Poindexter - SL | Malik Walker | PG County |  | APPROVED 5.20 | need action | Applied-Pepco | Drop Box | applied
Kathy Rivera - GL | Quativa | Chesterfield County |  | APPROVED 5.20 | NA | Need HOI | Drop Box | applied
Scott Seladoki - GL | Quativa | Ohio County |  | APPROVED 5.20 | NA | Applied Appalachian Power | Drop Box
Rhys Buntua - CASH | Peter Kyle | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | applied
Krystle Gray - GL | Ismael | Anne Arundel County |  | APPROVED 5.28 | NA | Approved-BGE | Drop Box | applied
Abilio Hernandez - GL | Marcelo Ortiz | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Syed Abbas - CASH | Theodore Brown | Howard County |  | N/A | applied | Approved-BGE | Drop Box | Issued
María Angélica Ventura Chavez - DV | Bianca del Castillo | Montgomery County/ City of Gaithsburg/City of rockville |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box
David Bentley - GL | True Energy (David Twitty) | Clay County |  | CANCELED | [13 empty] | Yes
Jai Patel - DV | Skylightngr | Harford County |  | APPROVED 5.24 | applied | Applied-BGE | Drop Box
Toi Wiseman - GL | Ismael | PG County |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box | in review
Santos Menjivar - DV | Bianca del Castillo | Frederick County |  | N/A | NA | Approved Potomac | Drop Box
Neil de Castro - DV | Danny Dubois | Virginia Beach City |  | ON HOLD UNTIL NTP | NA | Applied-Dominion | Drop Box
Shahjahan Molla - CASH | Peter kyle | Cumberland County | PA | N/A | NA | Approved PPL | Drop Box
Patrick Norman - CASH | John Lee | Arlington County |  | N/A | NA | need new bill | Drop Box | issued
Christina Sanchez - SL | Eric Strouse | Raleigh County |  | STIP - CUSTOMER NEEDS TO CALL SL | NA | applied-Apalachian Power | Drop Box
Eduviges Zavala - DV | Bianca del Castillo | Montgomery County |  | STIP - ID | NA | Applied-Pepco | Drop Box
Lilian Maribel Martinez Orellana - DV | Bianca del Castillo | Montgomery County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | applied
Jaime Cordero - GL | Marcelo ortiz | Montgomery County |  | APPROVED 5.25 | applied | Applied-Pepco | Drop Box | applied
Ebony Shirley - GL | IDC (Ishmael) | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | in review
Robert Feeman - GL | Quativa | Cumberland County | PA | APPROVED 5.25 | need action | Have bill PPL | Drop Box
Rene Smith/Patrick Ward - DV | Skylighting | Frederick County |  | CANCELED | NA | Have Bill-Potomac | [11 empty] | YES
David J. Poindexter III - SL | Malik Walker | PG County |  | APPROVED 5.25 | NA |  | 200 Amp/In Progress | applied
Craig Vaughan - CASH | SolarSurge | Chesterfield County |  | N/A | NA |  | Drop Box | in review
Benedicta Njoku - GL | Dawit Abraham | District of Columbia |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
Anthony Aponte - GL | Quativa | Spotsylvania County |  | APPROVED 5.27 | NA | Have bill & HOI | 200 Amp/Sunova Design
Patrick German - CASH | Quativa | Charles County |  | N/A | NA | Have bill SMECO | 200 Amp/Sunova Design
John Kolber - CASH | Inside Sales | Cumberland County | PA | N/A | need info |  | ELD On Hold/MSP Pics Needed
Matthew Herbaugh - CASH | Inside Sales | Isle of Wight County |  | N/A | need info |  | Drop Box | in review
Boleslaw Stefanski - CASH | Inside Sales | Pike County | PA | N/A | need action |  | Dropbox
Nick Vattimo - CASH | Inside Sales | Frederick County |  | N/A | need info |  | In Review
Emundo Trivelli - SL | Inside Sales | Prince William County |  | APPROVED 6.1 | need info | Applied Dominion | Drop Box
Jonathan Araya - CASH | Inside Sales | Loudoun County |  | N/A | need info | Apllied Dominion | Drop Box
Raed Jarrar - EZ | Inside Sales | District of Columbia |  | N/A | need info | Pepco | Sunnova Design | applied
Melanie Johnson - SL | Aaron Dawkins | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | applied
Cheryl Baker - SL | Eric Strouse | Mineral County |  | IN REVIEW | NA | Applied Potomac | Drop Box
Rosalynn Asamoah - DV | Skylighting | Montgomery County |  | STIP - ACH | need action | Have Bill Potomac | Inverter Details N/A
Sergio Martinez - DV | Skylighting | Baltimore City |  | STIP - OWNERSHIP | NA | Applied-BGE | Drop Box | Applied
Kevin Kidwell - CASH | Quativa | Hampshire County | PA | N/A | NA |  | Inverter Details N/A
Patrick Primm - GL | Quativa | ClearField County | PA | APPROVED 5.31 | NA | Have Bill-Potomac | ELD On Hold/MSP Pics Needed
Cyrus Hormozi - GL | Skylighting | Washington County |  | APPROVED 5.31 | approved | Approved Potomac | Drop Box
Socoya Gorham - GL | Brandon Hyman | District of Columbia |  | IN REVIEW | NA | Applied-Pepco | Drop Box | applied
Sean Hodgins - GL | Skylighting | Baltimore City |  | APPROVED 6.1 | NA | Applied-BGE | Drop Box
Liz Ehrich - CASH | John Lee (Inside Sales) | Stafford County |  | N/A | need action | Applied -Dominion | Drop Box
Harrison Parson - CASH | Tim Clark (Inside Sales) | Susquehanna County | PA | N/A | NA | Have Bill-Penelec | In Progress/Waiting fo Client Consultation
Rene Humberto Suarez- GL | Ana Romero | PG County |  | APPROVED 6.2 | NA | Applied-BGE | Dropbox | applied
Adrian Herring - SL | Tim Clark (Inside Sales) | Allegheny County | PA |  | need info |  | Everbright Design N/A
Carol Smith - SL | Solar Strong | Taylor County |  | APPROVED 6.2 | NA |  | 200 amp/Everbright Design
Ramiro Moya - GL | Carlos cueto | Montgomery County |  | APPROVED 6.3 | need action | Applied Potomac | Drop Box | applied
Edgar Sorto - GL | Raf Solar | Winchester City |  | APPROVED 6.3 | applied |  | Drop Box
Mayor William Sanders III - 1 |  |  |  |  | need info
Mayor William Sanders III - 2 |  |  |  |  | need info
Olufemi Oluwatobi Ikusika - DV | Skylighting | Baltimore County |  | APPROVED 6.6 | need action | Applied-BGE | Dropbox
Frank Trujillo - CASH | Peter Kyle ( Inside sales) | Prince William County |  | N/A | applied | Applied -Dominion | Dropbox
Jason Chandler - GL | John Lee (Inside Sales) | District of Columbia |  | STIP | NA | Approved-Pepco | Dropbox | applied
Linda and James Dwyer - CASH | John Lee (Inside Sales) | PG County |  | N/A | need info |  | Dropbox | applied
James Rodgers - GL | Aaron Dawkins | District of Columbia |  | APPROVED 6.7 | NA | Applied-Pepco | Dropbox | applied
Omotayo Ogundana - GL | Thornton Fennell | PG County |  | STIP - ID | need info |  | ELD on Hold | applied
Timothy Dixon - SL | John Lee (Inside Sales) | Howard County |  | NEED CORRECTION | need action | Have Bill-BGE | Sunnova Design//200 amp/Waiting fo Client Consultation
Karen Ireland - CASH | John Lee (Inside Sales) | Montgomery County |  | N/A | NA | Applied-Pepco | Dropbox | applied
James Ortmann | John Lee (Inside Sales) | PG County |  |  | NA | Applied-Pepco | Dropbox | applied
Christopher Arzadon - SL | John Lee (Inside Sales) | Prince William County |  | APPROVED 6.8 | need action | Have Bill-Dominion | Dropbox
Olawale Tolulope Ayorinde - SN | IDC (Ishmael) | PG County |  | N/A | need action | Have Bill-Pepco | 200 amp/In progress | applied
Emma Davenport - DV | Skylighting | Baltimore County |  | APPROVED 6.8 | NA | Have Bill-BGE | Site Visit Requested
Matthew Beyers - DV | Skylighting | Frederick County |  | STIP - ACH | need action | Applied Potomac | Dropbox
Christopher Means - SL | Eric Strouse | Kanawha County |  | APPROVED 6.8 | NA | Applied Appalachian | Dropbox
Charles Messerschmidt - GL | Ric Peters | Anne Arundel County |  | APPROVED 6.9 | NA | Applied-BGE | Dropbox
Heather Levander - | Quativa | Fayette County | PA |  |  |  | Everbright Design N/A
Harold Gerhart - GL | Quativa | Cumberland County | PA | CHANGE ORDER? | NA | Have Bill PPL | Inverter Details N/A
Justin Strickland - GL | Quativa | Cumberland County | PA | APPROVED 6.9 | NA | Have Bill-PPL | Everbright Design N/A
Berta Lidia - GL | Marcelo Ortiz | Frederick county |  | APPROVED 6.9 | NA | Have bill potomac
Kenneth Blankenship - SL | Eric Strouse | Nicholas county |  | STIP - OWNERSHIP | NA |  | In Progress
Keith Scarsdale - SL | Mark Davis | Culpeper County | PA | IN REVIEW | NA
Sean Magee - CASH | Cinthia Rivera | Loudoun county |  | N/A | NA | Have bill dominion | Drop Box
Todd Benbow - DV | SkylightNGR | Charlotte County |  | IN REVIEW | NA |  | ELD On Hold/MSP Pics Needed
Jlicery Diaz - SL | Eric Strouse | Kanawha County |  | STIP - OWNERSHIP | NA | Have Bill Appalachian AND hoi | drop Box
Austin Snyder - GL | Voltaic (Freddye Jackson) | Lehigh County | PA | IN REVIEW |  | PPL | Dropbox
Luis Rosas - GL | Justin Hall | PG county |  | IN REVIEW |  |  | ELD On Hold/MSP Pics Needed
Fatoumatta Bah - DV | SkylightNGR | Frederick county |  | IN REVIEW | need action | Have bill potomac | ELD On Hold/MSP Pics Needed
Jose Martinez - GL | Marcelo Ortiz | Montgomery County |  | IN REVIEW |  |  | In Progress

## MD
NAME | SALES REP | COUNTY | STATE | NTP | HOA | Interconnection | Design | Permit | Installation | Inspection | Meter Change | Access | Registration | PTO Uploaded | SRECs | MD Grant | QA | CANCELLED | PEARL CERTIFICATION
Angel M Lima - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done
Dan Notestein - CASH | Sam Albert | Montgomery County/Town of Blacksburg | MD | N/A | approved | Approved VTES | Done | issued | Installation Completed
Juan L Guillen - GL | Thirza Iglesias | Frederick County | MD | APPROVED 1.21 | approved | Approved Rappahannock | Done | issued | Installation Completed | Passed | Applied
Fizel Jabbar - DV | Aaron Dawkins | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | site created |  | Done | Done | Done |  |  | Done
Jose Chacon - GL | Carlos Cueto | PG County |  |  | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Julio Fuentes - GL | Carlos Cueto | Montgomery County |  | APPROVED 1.07 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Misael Guillermo - SN | Thornton Fennell | PG County | MD |  | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Payment pending | Payment pending |  |  | Done
Willie Ford - GL | Thornton Fennell | PG County |  | APPROVED 1.05 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Yolanda Zelaya - GL | Sarah Romero | PG County | MD | APPROVED 1/10 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Mark Reid - GL | Aaron Dawkins | PG County | MD | CANCELED |  |  | Done | [10 empty] | YES
Lynne Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 1/20 | N/A | Approved-Pepco | Done | Issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | Done
Raymond Marquis - GL | Noblesolar | Norfolk County |  | APPROVED 2.4 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Jessie Miles - GL | Noblesolar | Norfolk County |  | APPROVED 1/12 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Yilia Jackson - SN | Ted Brown | Baltimore City | MD | N/A | NA | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | done |  | Done
Ronny/Taylor Sylvester - GL | Noblesolar | Chesapeake City |  | APPROVED 2.8 | NA | Approved Dominion | Done | Issued | Installation Completed | Passed | Applied | Done |  | Received | Done
Kathryn Alexander - CASH | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Charles Cucina - DV | Danny Dubois | FrederickCounty | MD | N/A | NA | Approved Potomac | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Miguel Angel Vernal Nolasco - GL | Sarah Romero | Baltimore County | MD | LOAN CANCELED | NA | Have bill | [11 empty] | Yes
Juan Martinez - DV | Sarah Romero | Winchester City |  | N/A | NA | Approved SVEC | Done | issued | Scheduled 6/9
Jose H. Baca Oseguera - GL | Ana Romero | PG County | MD | APPROVED 2.8 | NA | Approved-Pepco |  | issued | Installation Completed | Passed | Applied | Done | [6 empty] | Done
Oluseyi Ajayi - GL | Noblesolar | Chesapeake City |  | APPROVED 1.28 | applied | Approved Dominion 02/15/2022 | DONE | Issued | NA
Darryl Girtz - GL | Noblesolar | Norfolk City |  | APPROVED 1.31 | NA | Approved Dominion | Done | Applied-1/24 | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Gerry Evans - GL | Noblesolar | Newport News City |  | APPROVED 1.24 | approved | Approved Dominion | Done | issued | Installation Completed
Matthew Griffin - GL | Noblesolar | VA Beach City |  | APPROVED 1.25 | NA | Approved Dominion | Done | issued | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Donald Deely - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done | Issued | TBS
Brayan Godines - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | done |  | Done | Done | Done |  |  | Done
Matthew Gomez - SL | Roberto Smith | PG County | MD | APPROVED 1.24 | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Maxie Lawton -GL | Volt (Ishmael) | PG County |  | APPROVED 1.24 | approved | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Engracio Edesar Abris - DV | Danny Dubois | Arlington County |  | N/A | NA | Approved 03/01/2022 | Done | issued | Installation Completed | Passed |  | Done | [6 empty] | Done
Chris Luk - Cash | Richard Thrutchley | Fairfax County |  | N/A | approved | Approved Dominion | Done | issued | Scheduled 6/3 |  |  | Done
Nabil Ahmed - SL | Roberto Smith | Montgomery County |  | APPROVED 1.28 | approved | Approved Potomac | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | DONE | Done |  |  | Done
Sharon Flowers - DV | Jedi | PG County | MD | CANCELED | applied | Approved-BGE | Done | issued
Maricela Pena - GL | Sarah Romero | PG County | MD | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | [9 empty] | Done
Malik Abdunafi - SL | Jedi | Baltimore City | MD | APPROVED 2.7 | NA | Approved-BGE | Done | Issued | TBS
Delphine London - NS | Noblesolar | VA Beach City |  | APPROVED 2.7 | approved | Approved Dominion | Done |  | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Gary Hill - GL | Noblesolar | York County |  | APPROVED 1.28 | APPROVED | Approved Dominion | Done | applied | Installation Completed
Carmen Bona - SN | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Applied PECO | Done
Tyleek Harris - GL | Noblesolar | Newport News City |  | APPROVED 2.7 | applied | Approved Dominion | Done | issued
Harrison Eacho - GL | Noblesolar | Norfollk City |  | APPROVED 1/28 | NA | Applied Dominion | Done
Olawole Olayinka - GL | Volt Solar (Freddye) | Howard County |  | APPROVED 1/28 | approved | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | V.S
Justin Shoemaker - GL | Noblesolar | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | N.S
Adewale Daramola - GL | Noblesolar | Chesapeake City |  | APPROVED 1.31.22 | applied | Approved Dominion | Done
Silvia Rivera - DV | Sarah Romero | City of Frederick | MD | N/A | NA | Approved-Potomac Edison | Done | issued | TBS
Darwin A Fuentes - GL | Alberto Sosa | PG County | MD | APPROVED 2.3 | NA |  | Dropbox | issued | [9 empty] | Yes
Charles Hiller - EZ | Sam Albert | Pike County |  | Declined by EZSolarLoan | NA | Applied Met-Ed | Done | [10 empty] | Yes
John Coombs - SL | Roberto Smith | Baltimore County | MD | APPROVED 2.1 | NA | Approved-BGE | Done | issued | Installation Completed | [9 empty] | Done
Amy Cervantes - EZ | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Eli Apuya - GL | Noblesolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Done
Brett Dash - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved dominion | Drop Box
Alexander Vasquez Fernandez - GL | Noblesolar | Suffolk City |  | APPROVED 2.1 | in review | Approved-dominion | Done
Taiwo Olayinka - GL | Volt Solar (Freddye) | Anne Arundel County | MD | APPROVED 2.2 | approved | Approved-BGE | Done | in review | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jessica Green - SN | USA Solar Network | Westmoreland County |  | CANCELED | N/A | Applied - Westpenn Power | Drop Box | issued
William Bryan - GL | USA Solar Network | Bucks County |  | APPROVED 2.3 | N/A | Applied PECO | Done | issued
Kimberly Hayes - GL | USA Solar Network | Luzerne County |  | APPROVED 2..3 | N/A | Approved PPL WO 58650550 | Done | issued | Installation Completed | [9 empty] | U.S solar network
Devin Sharp - GL | USA Solar Network | Pittsylvania County |  | CANCELED | NA | Have Bill Danvill | ELD On Hold | [10 empty] | Yes
James Spadoni - GL | USA Solar Network | Northampton County |  | APPROVED 2.4 | N/A | Applied Met ED | Done
Edward Coley - CASH | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Approved PECO | Done |  | TBS - Roof Pending
Christopher Doane - GL | NobleSolar | Suffolk City |  | APPROVED 2.4 | applied | Approved-dominion | Drop Box
David Nicklas - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done
Margaret Galega - SL | Joseph Allo | PG County | MD | APPROVED 2.4 | applied | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Raymond Kabacinski - GL | NobleSolar | Norfolk City |  | APPROVED 2.7 | NA | Approved-dominion | Done | B-issued | Installation Completed |  | Applied | Site Created |  | Received | DONE |  |  |  | N.S
Karen Songwe - SL | Aaron Dawkins | PG County |  | APPROVED 2.8 | applied/NO HOA for this address | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | 22.57 |  |  | Done
Jose H Vega Carapia - GL | Ana Romero | City of Frederick | MD | APPROVED 2.24 | N/A | Approved - potomac Edison | Done | issued
Jonas Chicas - DV | Sarah Romero | Louisa County |  | N/A | NA | Approved-Dominion | Done | issued | Installation Completed | [9 empty] | Done
Joy Dalesandro - GL - ON HOLD | NobleSolar | Chesapeake City |  | APPROVED 2.9 | applied | Applied Dominion | Done
Christopher Nunley - GL | SolarStrong | Berkeley County |  | APPROVED 3.23 | NA | Approved Potomac WV | Done | in review | Installation Completed | Passed | Applied | DONE
Kevin Coates - SN | Ric Peters | Anne Arundel County | MD | N/A | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Francis Hawkins - SL | Thornton Fennell | Charles County |  | APPROVED 2.24 | NA | Approved SMECO | Done | issued | Installation Completed | Passed | Approved | DONE |  | Done | Done | 22.2 |  |  | Done
Jon Walman - DV | Skylightnrg | Stafford County |  | N/A | NA | Project Cancell (James Nguyen) | Done | [10 empty] | Yes
Britteny Stone-Joel - GL | NobleSolar | Isle of Wight County |  | APPROVED 3.1 | approved | Approved-Dominion | Drop Box | issued | Installation in Progress |  |  | DONE
Donna Delgado-Johnson - SL | Thornton Fennell | PG County | MD | APPROVED 3.1 | NA | Approved - PEPCO | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  | Done |  |  | Done
Kenneth King - GL | NobleSolar | Hampton City |  | APPROVED 2.14 | N/A | Approved-Dominion | Done | issued | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Jaramie York - SN | Jedi | Charles County | MD | CANCELED | NA | Have Bill SMECO | [11 empty] | Yes
Jose Oscar Velasco - GL | Carlos Cueto | Montgomery County |  | APPROVED 2.15 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Melvin Blackwell - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved- Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Kenmanze Edmonds - GL | NobleSolar | Isle of Wight County |  | PROJECT CANCELED | NA | Have bill | [11 empty] | Yes
Christopher Bonzek - CASH | Inside Sales | Newport News City |  | N/A | NA | Approved dominion | Done | issued | TBS - Rec Panels
Mary Clowe - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mridul Gupta - DV | Skylightnrg | Henrico County |  | N/A | approved | Approved dominion | Done | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | skylight
Jose Blanco - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Blanca Arevalo - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mark Whitling - GL | NobleSolar | VA Beach City |  | APPROVED 2.14 | deal cancelled | deal cancel | [11 empty] | Yes
Joe Leugers - GL | NobleSolar | Suffolk City |  | APPROVED 2.23 | approved | Approved dominion | Drop Box | issued | Installation Completed |  | Applied | Done | [6 empty] | N.S
Alejandra Juarez - GL | Raf Solar | PG County | MD | APPROVED 2.15 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Paul Warren - GL | NobleSolar | VA Beach City |  | APPROVED 2.15 | need action |  | Drop Box | [10 empty] | Yes
Miguel Vernal - GL | Raf Solar | Baltimore County |  | APPROVED 2.15 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
William Smith - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.15 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Eros Lazzerini - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Cletus Ayuk - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved |  |  | Done | Done | Done |  |  | Done
Hannah Emert - GL | NobleSolar | Suffolk City |  | APPROVED 2.17 | applied | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Franklin A Garcia - GL | Alberto Sosa | PG County |  | APPROVED 2.16 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Guillermo West - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.18 | NA | Approved- PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Shirlene Ogburn - DV | Skylightnrg | Charles County | MD | N/A |  | Project Cancel by Dealer | [11 empty] | Yes
Kelsey Mijal - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | NA | Approved dominion | Done |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Danielle Goodrum - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | applied | Approved dominion | Done
Nathan Carl - GL | NobleSolar | Portsmouth City |  | APPROVED 3.8 | NA | Approved dominion | Drop Box | in review | Scheduled 5/27 | Passed
Meaghan Jenks - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Applied | Done |  |  | DONE |  |  |  | Done
Queenie May Escubio - EZ |  | Portsmouth City |  | APPROVED 2.17 | NA | Approved dominion | Done | in review | Scheduled 5/28 | Passed | Applied
Alexander Phillips - GL | NobleSolar | Chesapeake City |  | APPROVED 2.17 | applied | Approved dominion | Done | issued
`William Sanders - CASH | Solarsurge | Anne Arundel County | MD | N/A | NA | Approved-BGE | Drop Box | in review
Michelle Gomez - GL | Alberto Sosa | PG County | MD | APPROVED 3.1 | NA | Approved-Pepco | Drop Box | issued | [9 empty] | Yes
George Knight - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | need policy no# | Drop Box
May Petalcorin - GL | NobleSolar | Suffolk City |  | PROJECT CANCELED | need action | [12 empty] | Yes
DePaul Griffin - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Richard Taylor - GL | NobleSolar | VA Beach City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Rebecca Phillips Ferguson - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Peter Keller - CASH | Solarsurge | Montgomery | MD | N/A | NA | Have bill-Pepco
Malcolm Dixon - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Michael Osumlalu - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | in review | Approved dominion | Drop Box
Constance Kinge -SL | Aaron Dawkins | PG County |  | APPROVED 2.21 | NA | Approved PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Jennifer Joynes - SL | Jedi | Pricness Ann | MD | APPROVED 2.21 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | TBS
Ruperto Rivera - GL | Raf Solar | Montgomery County | MD | APPROVED 2.21 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed |  | Site created | [6 empty] | Done
Salvador Cueva - GL | Thirza Iglesias | City of frederick | MD | APPROVED 2.21 | NA | Approved Potomac Edison | Drop Box | issued | Installation in Progress
Martin Medina Estrada - GL | Carlos Cueto | Town of Elkton | MD | APPROVED 2.25 | NA | Approved- PEPCO(Delmarva) | Drop Box | issued | TBS
Luisa Figaro - SL | Remesh Sartani | Princess Anne | MD | APPROVED 2.25 | NA | Approved- PEPCO | Drop Box | issued | Installation Completed
Fernando Ortez - GL | Raf Solar | Prince William County |  | APPROVED 2.25 | NA | Approved NOVEC | Done | [10 empty] | Yes
Telesfora Briones - GL | Raf Solar | City of Annapolis | MD | APPROVED 2.21 | approved | Approved- BGE | Done | applied
Lap T. Vo - SL | Michael Reid | Montgomery County |  | APPROVED 2.21 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Candy Huynh - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | applied | Approved Dominion | Drop Box |  | Installation Completed | [9 empty] | N.S
Keith Layne - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Oscar Jimenez - GL | Raf Solar | Prince william |  | APPROVED 2.25 | NA | Approved - NOVEC | Drop Box | In review
George Hoskin - SL | Michael Reid | Montgomery County |  | APPROVED 3.4 | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Octavia Pearson - GL | Thornton Fennell | PG County | MD | APPROVED 2.24 | NA | Approved - PEPCO | Drop Box | issued | Installation in Progress | Passed | Approved |  |  | Done | Monit not done | Done
Nicolas Lovo - GL | Raf Solar | Charles County | MD | APPROVED 3.1 | applied | Approved - SMECO SMECOINT-08593 | Drop Box | Applied
Marcos A Flores - GL | Ana Romero | City of Frederick | MD | APPROVED 2.24 | NA | Approved potomac | Drop Box | issued | TBS
Paul Rudicki - GL | NobleSolar | Chesapeake City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box |  | Installation Completed |  | Applied | Done |  |  | DONE |  |  |  | N.S
Katherine Heun - GL | NobleSolar | Chesapeake City |  | APPROVED 2.25 | NA | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Kyle Scherele - GL | NobleSolar | Hampton City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box | in review | Installation Completed | [9 empty] | N.S
Myrna Michelle Flores - GL | NobleSolar | VA Beach City |  | APPROVED 3.1 | approved | Approved dominion | Drop Box |  | Installation Completed |  | Applied | Done | [6 empty] | N.S
Santos Soto - GL | NobleSolar | Suffolk City |  | APPROVED 2.24 | applied | Approved dominion | Drop Box | [10 empty] | Yes
Mary Rampolla - DV | Skylightnrg | Howard County | MD | N/A | NA | Approved- BGE | Drop Box | [10 empty] | Yes
Tracy Winters - SN | USA Solar Network | Delaware County |  | CANCELED | need info | Have Bill - PECO | [11 empty] | Yes
Santos Rivera - GL | Raf Solar | Frederick County | MD | APPROVED 2.25 | NA | Have Bill - Dominion | Drop Box | [10 empty] | Yes
Leslie Braithwaite - DV | Skylightnrg | PG County | MD | N/A | NA | Applied - PEPCO | Done | in review | [9 empty] | Yes
Keith Wilburn - GL | NobleSolar | Suffolk City |  | APPROVED 2.25 | applied | Approved dominion | Drop Box
Thanaporn Cockran - SL | Jedi | Anne Arundel County | MD | APPROVED 5.13 | NA | Approved-BGE | Drop Box | issued | TBS
Florimon Arrey Ndip Etta - GL | Aaron Dawkins | PG County |  | APPROVED 2.28 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Site created |  | Done | DONE | Done |  |  | Done
Yamarco Figaro - SL | Remesh Sartani | Wicomico County | MD | APPROVED 2.28 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | Installation Completed | [9 empty] | Done
Veronica Brooks - SL | Thornton Fennell | PG County | MD | APPROVED 2.28 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | Monit not done | Done |  |  | Done
Garrye Hepburn - GL | Skylightnrg | PG County |  | APPROVED 3.1 | approved | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | skylight
Adriene Muhammad - DV | Skylightnrg | Branchville |  | N/A | NA | Approved Dominion | Drop Box
Ron Leese - DV | Skylightnrg | Carroll County | MD | N/A | NA | Approved-BGE | Drop Box | applied
Samuel Nelson - GL | Inside Sales | Distric of Columbia County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Site Created
Jorge A. Soto Sanabria - GL | Thirza Iglesias | PG County | MD | APPROVED 3.2 | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Site Created | [6 empty] | Done
Federico Vega - GL | Thirza Iglesias | Winchester City |  | APPROVED 3.2 | NA | Applied SVEC | Drop Box | issued
Tae Kim - DV | Skylightnrg | Montgomery County | MD | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS | [8 empty] | Yes
Raul Morales Martínez - GL | Carlos Cueto | PG County | MD | APPROVED 3.8 | NA | Approved-Pepco | Drop Box | issued | Installation In Progess
Jose Campos - GL | Carlos Cueto | PG County |  | APPROVED 3.4 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Jesus Aguilera - GL | Raf Solar | PG County | MD | APPROVED 3.4 | HOA approved | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done |  | SS above 20 |  |  | Done
Miguel Mendoza - GL | Raf Solar | Gaithersburg City | MD | APPROVED 3.4 | approved | Approved-PEPCO | Drop Box | in review | Installation In Progess
Steven Miles - GL | Volt Solar (Freddye) | Accokeek County/PG | MD | APPROVED 3.9 | NA | Approved SMECO | Drop Box | issued | Installation Completed | [9 empty] | V.S
Virginia Chaziva - GL | Aaron Dawkins | PG County | MD | APPROVED 3.9 | applied | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Dilsa Rosales Moscoso - GL | Ana Romero | Montgomery County |  | APPROVED 3.3 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  |  | Done |  |  |  | Done
Mary Satterwhite - SN | Jonathan Ngo | Loudoun County |  | N/A | approved by Jon | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received |  |  |  |  | Done
Patrick Brown - SL | Ric Peters | Baltimore County |  | APPROVED 3.9 | NA | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Philip Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 3.9 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Trad Leavitt - DV | Skylightnrg | Frederick County | MD | N/A | approved | Approved Rappahannock | Drop Box | issued | Installation Completed | Passed | Applied | Done
Dante Fenwick - GL | Skylightnrg | PG County | MD | APPROVED 3.9 | in review | Approved-Pepco | Drop Box | issued
Steve Kinaman - EZ | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Scheduled 6/2 | Passed | Applied
Raja Balasubramanian - CASH | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | Done
Jian Liu - SL | Roman Bondari | Loudoun County |  | APPROVED 3.11 | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Received |  |  |  |  | Done
Michael Mills - SL | Jedi | Wicomico County | MD | APPROVED 3.11 | NA | Approved - PEPCO(Delmarva) | Drop Box | applied | Scheduled 6/2
Karla Martinez - GL | Raf Solar | Fauquier County |  | APPROVED 3.15 | approved | Approved Dominion (modifications) | Drop Box | in review (modifications) | Installation in Progress
Rita Fallon - SL | Ric Peters | Anne Arundel County | MD | APPROVED 3.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
David Sheffey - SN | Thornton Fennell | PG County | MD | N/A | NA | Applied - PEPCO | Drop Box | issued
Jaiyeola Oluwatosin - GL | USA Solar Network | PG County | MD | APPROVED 3.14 | need info | Applied- PEPCO | Drop Box | in review
Ureka Wise - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.14 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Adam Karaffa - GL | USA Solar Network | Westmoreland County |  | APPROVED 3.14 |  | Approved Westpenn Power | Drop Box
Martha Rodriguez - DV | Michael Reid | Prince William County |  | N/A | approved | Approved- Dominion | Drop Box | Applied
Jordan Calabrese - SN | Ric Peters | Anne Arundel County | MD | N/A | NA | Approved-BGE | Drop Box | issued | TBS
Joseph Sheffey - DV | Thornton Fennell | PG County | MD | N/A | NA | Approved-PEPCO | Drop Box | in review | Installation Completed | [9 empty] | Done
Jose Yaselli - SN | Jedi | Carroll County | MD | N/A | NA | Approved-BGE | Drop Box
Saqr Alawdi - GL | NobleSolar | Hampton City |  | APPROVED 3.23 | NA | Have bill and HOI | ON HOLD | [10 empty] | Yes
John Delgadillo - DV | Jonathan Ngo | Chesterfield County |  | N/A | NA | Approved- Dominion | Drop Box | issued | Installation Completed | [9 empty] | Done
Joel Gonzalez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 3.17 | NA | Approved 4/4/22 | Drop Box | issued | Installation Completed | Passed | Applied | [7 empty] | Done
Arthur Cockran - SL | Jedi | Queen Anne County | MD | ON HOLD UNTIL NTP | NA | Approved Choptank Electric | Drop Box | in review
Jose R Guzman Delcid - GL | Ana Romero | City of frederick | MD | CHANGE ORDER 5.24 | NA | Approved potomac | Drop Box | issued
Janet Thompson - CASH | Inside Sales | Stafford County |  | N/A | approved | Approved- Dominion | Drop Box | in review
Omkar Prabhu - CASH | Inside Sales | Monroe County |  | N/A | NA | Approved - PPL | Drop Box | issued | TBS
Delia/Joseph Palmer - GL | NobleSolar | Suffolk City |  | CANCELED | need action | have bill & HOI | ELD on hold | [10 empty] | Yes
Misael Moreno - GL | Raf Solar | Anne Arundel County | MD | APPROVED 3.31 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Rose Bennett - DV | Skylightnrg | Howard County | MD | PROJECT CANCELED | need action | Cancelled by Skylight (Adrienne) | [11 empty] | Yes
Rebecca Gaither - SL | Thornton Fennell | PG County | MD | CANCELED | [13 empty] | Yes
Joy Alorro - DV | Danny Dubois | Fairfax County |  | N/A | applied | Approved Novec | Drop Box | in review
Elizabeth Mason - DV | Danny Dubois | Staunton County |  | N/A | NA | Approved- Dominion | Drop Box
Clifford McQueen - GL | Volt (Ishmael) | PG County | MD | APPROVED 5.13 | NA | Approved- Pepco | Drop Box | issued | Installation in Progress
Deborah Bailey - SN | Jedi | Baltimore County | MD | N/A | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Dawn Banks- SN | Inside Sales (Ishmael) | Charles County |  | N/A | NA | Approved - SMECO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Chikodili Ugokwe - SN | Thornton Fennell | PG County | MD | N/A | NA | Approved- BGE | Drop Box | in review | Installation in Progress
Maximiliano Posada - GL | Ana Romero | Montgomery County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Conor P. Williams - CASH | Inside Sales | District of Columbia |  | N/A | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Done | Done |  |  |  | Done
Francisco Jacobo Sanchez - GL | Ana Romero | PG County | MD | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | [9 empty] | Done
Dustin Schultz - GL | USA Solar Network | Calvert County | MD | APPROVED 3.23 | NA | Conditionally Approved SMECO | Drop Box
Mary Ukwu - SL | Aaron Dawkins | PG County | MD | APPROVED 4.1 | approved | Approved- BGE | Drop Box |  | Installation Completed | Passed | Applied | [7 empty] | Done
Liliane Batista - GL | Marcelo Ortiz | Montgomery County | MD | APPROVED 3.31 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | 2022-06-01 | [8 empty] | Done
Sharon McGee - GL | Volt Solar (Freddye) | PG County | MD | APPROVED 4.1 |  | Applied-Pepco | Drop Box | issued | Scheduled 5/30
Sandor Slager - CASH | Volt Solar (Brandon) | Distric of Columbia County |  | N/A | NA | Approved- PEPCO | Drop Box | issued | Installation in Progress
James D. Bryden - EZ | Inside sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - U anchor check
Anthony Field - DV | SkylightNRG | PG County | MD | N/A | NA | Have Bill PEPCO | 200AMP | applied
Grace Brunner - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - Roof repair pending
Jeremy Black - CASH | Inside Sales | Lycoming County |  | N/A | NA | Approved PPL | Drop Box | issued | TBS
Phil Nawrocki - CASH | Inside Sales | Allegheny County |  | N/A | NA | Approved DLC | Drop Box
Deborah Whitaker - GL | Jedi | Baltimore City | MD | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Tod Harach - EZ | Inside Sales | Lancaster County |  | N/A | NA | Approved PPL | Drop Box
Guillermo Mendoza - GL | Raf Solar | Montgomery County |  | APPROVED 3.26 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Leonel Majano - GL | Marcelo Ortiz | Frederick County | MD | APPROVED 5.10 | NA | Approved REC | Drop Box | Applied-5/26
Renardo Williams - DV | Jedi | Anne Arundel County | MD | N/A | NA | Approved-BGE | Drop Box | applied
Ronisha Dickerson - GL | Volt (Ishmael) | PG County | MD | APPROVED 3.27 | approved | Conditional approved SMECO | Drop Box | issued | TBS |  |  | done
Jose Coreas - GL | Carlos Cueto | Baltimore County | MD | APPROVED 3.27 | Cancelled by Carlos |  | ELD on Hold | [10 empty] | Yes
Peter Kurilla - GL | USA Solar Network | Montgomery County *PA* |  | APPROVED 4.11 | NA | Applied PECO | Drop Box
Tatiana McCook - GL | Volt Solar (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Rachelle Stephens - SL | Remesh Sartani | Charles County |  | APPROVED 4.20 | NA | Approved SMECOINT-08682 | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Catherine Heath - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | [8 empty] | V.S
De'Andre Sheppard - DV | Skylightnrg | Baltimore County | MD | N/A | NA | BGE | Drop Box
Sandra Dieterle - DV | Skylightnrg | Baltimore City | MD | N/A | NA | Approved-BGE | Drop Box | In review
Marisol Muñoz - GL | Bianca del Castillo | City of Rockville | MD | APPROVED 5.3 | NA | Approved-Pepco | Drop Box | issued | TBS
Donnie Waites - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued
Faye Coles - DV | Skylightnrg | Anne Arundel County | MD | N/A | approved | Approved-BGE | Drop Box | applied
Gerald Newsome - DV | Skylightnrg | Charles County | MD | N/A | Approved | Approved -SMECO | Drop Box | issued
Queenie May Escubio - EZ | Inside sales | Prince william county |  | N/A | approved | Approved Dominion | Drop Box | Applied
Santosha Lee - GL | Volt Solar (Freddye) | PG County | MD | APPROVED 4.27 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | V.S
Jose Morales - GL | Marcelo Ortiz | Stafford County |  | CANCELED | NA | Applied NNEC | Drop Box | [10 empty] | Yes
Robert & Suzette Kinstler - GL | USA Solar Network | Montgomery County*PA |  | APPROVED 4.1 | NA | Approved PECO | Drop Box | [10 empty] | Yes
Peter Hughes | Double Inside Sale |  |  |  |  | Applied Rappahannock | Drop Box | in revie
Terence Collins - GL | Skylightnrg | Baltimore County | MD | APROVED 3.31 | NA |  | Canceled Dt:3/31/22 | [10 empty] | Yes
Dustin Blankenship - GL | USA Solar Network | Carroll County | MD | APPROVED 3.31 | NA | Approved Potomac GEN-MD-8107 | Drop Box | in review
Jay Vodela - SN | Jonathan Ngo | Montgomery County | MD | N/A | approved | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jaime Salazar - CASH | Inside Sales | Montgomery County | MD | N/A | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Melanie Choh - GL | Volt (Ishmael) | PG County | MD | APPROVED 3.31 | Approved | Approved-Pepco | Drop Box | issued | TBS
Dawn Peterson - GL | IDC | PG County | MD | APPROVED 4.1 | approved | Approved-Pepco | Drop Box | issued | TBS |  |  | DONE
Kwame Gyamfi - SL | Derrol Mcclaren | Montgomery County | MD | APPROVED 5.6 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Yvette Dowtin - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | DONE
Bianca Christie - SL | Derrol Mcclaren | Baltimore County |  | APPROVED 4.20 | NA | Approved -BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Silvia Centeno - GL | "Rafael Cabello (Raf Solar )" | PG County | MD | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Leroy Inabinett - SL | Aaron Dawkins | Baltimore City | MD | CANCELEED | NA | Approved-BGE | Drop Box | In review | [9 empty] | Yes
Edgar Bonilla - GL | Marcelo Ortiz | PG County | MD | APPROVED 5.2 | approved | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Marina del Carmen Bonilla - GL | Carlos Cueto | PG County | MD | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Reina Alfaro - GL | Marcelo Ortiz | Montgomery County | MD | CANCELEED | NA | Approved-Pepco | Drop Box | applied | [9 empty] | Yes
Silvio Espinal - GL | Jorge Carias | Montgomery County | MD | APPROVED 4.5 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Ana Majano - GL | Marcelo Ortiz | Frederick County | MD | APPROVED 5.6 | NA | Applied REC | Drop Box
Silvia Centeno - GL | Raf Solar | PG County | MD | APPROVED 4.12 | NA | APPROVED-PEPCO | Drop Box | applied | Installation in Progress
Carlos Hoschmin - GL | Raf Solar | Fairfax county |  | CANCELED | cancel by SR |  | Canceled Email Dt:4/8/22 | [10 empty] | Yes
Colin Eckman - CASH | Inside Sales | Prince William County |  | N/A | approved | Approved dominion | Drop Box | Applied
Jonathan Ford - CASH | Inside Sales | Carrol County | MD | N/A | NA | Applied-BGE | Drop Box
Rene Lemus - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Pierre Tekem Noumbi - DV | Skylightnrg | PG County | MD | N/A | need action |  | Drop Box | issued
Jose de la Cruz Reyes - GL | Carlos Cueto | Frederick County | MD | APPROVED 4.12 | Approved | Approved potomac | Drop Box | issued | TBS
Roger Yobani Diaz - GL | Bianca del Castillo | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Jose Castillo - GL | Marcelo Ortiz | Montgomery County | MD | APPROVED 4.11 | approved | Approved Potomac | Drop Box | issued | Installation Completed | Passed | Applied | Done
Elizabeth Mason - DV | Inside Sales | (Chesterfield) |  | N/A | approved | Applied Dominion | Drop Box | issued
Jose Perez - GL | Raf Solar | PG County | MD | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Applied
Juan Villatoro - GL | Marcelo ortiz | Anne Arundel County | MD | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Scheduled 5/23 |  |  | Done
Vinicia R Torres - GL | Ana Romero | PG County | MD | APPROVED 4.12 | NA | Approved-BGE | Drop Box | issued | Installation Completed
Juan Soto - GL | Raf Solar | PG County | MD | APPROVED 4.26 | NA | Applied-Pepco | Drop Box | in review
Nestor Tchinda - SL | Derrol Mcclaren | Montgomery County | MD | ON HOLD UNTIL NTP |  | Have Bill BGE
Bernice Alston - GL | Thornton Fennell | PG County | MD | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Josias Tekle - DV | Skylightnrg | city of hagerstown | MD | N/A | approved | Approved potomac | Drop Box | applied
Tim Johnson - DV | Skylightnrg | St. Mary's County | MD | N/A | NA | Approved SMECO | Drop Box | issued | TBS
Theresa Terry - GL | Volt Solar (Freddye) | PG County | MD | CANCELED | need info | Have Bill SMECO | 200AMP | applied | [9 empty] | Yes
Louis Drury - GL | Elijah Sutton | Calvert County | MD | APPROVED 4.12 | NA | Approved SMECO | Drop Box
Hakeem Ayodeji - SN | Samuel Edwards | Charles County | MD | N/A | need info | Conditionally Approved Smeco | Drop Box | issued
Kenisha Jefferson - SN | Theodore Brown | PG County | MD | N/A | approved | Approved-PEPCO | Drop Box | issued
Rosa Garcia - GL | Carlos Cueto | PG County | MD | APPROVED 4.13 | NA | Approved-BGE | Drop Box | issued | Installation in Progress
Abdullah Amin - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.14 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Demetri Kappatos - SL | Charles Carufel | Loudoun County |  | IN REVIEW | IN REVIEW |  | Drop Box
Teodoro Carranza - GL | Ana Romero | Montgomery County | MD | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Done
Vicki Powell - DV | Skylightnrg | Cecil County | MD | N/A | NA | Applied-Pepco | Drop Box | Applied
Kenneth Pilpel - DV | Skylightnrg | Montgomery County | MD | N/A | Approved | Approved-Potomac | Drop Box | issued | TBS
Jose Resendiz - DV | Skylightnrg | Baltimore City | MD | N/A | NA | Approved-BGE | Drop Box | In review
Yessenia Marilu Cruz - GL | Carlos Cueto | PG County | MD | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Lydia Hagos - GL | Volt Solar (Freddye) | PG County | MD | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Latanya Cannady - GL | IDC | PG County | MD | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Austin Johnson - GL | Volt Solar (Freddye) | PG County | MD | APPROVED 4.19 | approved | Approved SMECO | Drop Box | issued |  |  |  | Site created
Kirk Ramirez - EZ | Tim Clark | PG County | MD | N/A | applied | Approved-Pepco | Drop Box | in review
Derell Kennedo - EZ | Peter kyke | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Drop Box | in review
Ramon Eclavea - DV | Danny Dubois | Prince William County |  | N/A | applied | Approved Novec | Drop Box | Applied
Ian Roach - SL | Aaron Dawkins | PG County | MD | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | in review | TBS
Sade Brown - SN | Ric Peters | Anne Arundel County | MD | N/A | NA | Approved-BGE | Drop Box | issued
Jason Coy - CASH | Tim Clark | Anne Arundel County | MD | N/A | NA | Approved-BGE | Drop Box | issued | TBS
William Burgess - CASH | Tim Clark | Arlington County |  | N/A | NA | Approved Dominion | Drop Box | issued
Paul Leger - DV | Elijah Sutton | Howard County | MD | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Park - DV | Havar Espedal | Distric of Columbia County |  | N/A | already approved by HAVAR | Approved-Pepco | Drop Box | in review
John Greesh - DV | Havar Espedal | Distric of Columbia County |  | N/A | need info | Approved-Pepco | Drop Box | in review
Matthew Lewis - DV | Derrol Mcclaren | PG County | MD | CANCELED | NA | Applied-Pepco | Drop Box | in review | [9 empty] | Yes
Marion Bedford - GL | Volt Solar (Freddye) | PG County | MD | CANCELED |  | Cancel by Dealer | Designed But Canceled | applied | [9 empty] | Yes
Delcita Lemus - GL | Raf Solar | PG County | MD | APPROVED 4.20 | NA | Approved-Pepco | Drop Box | in review
Maria Consuelo Baires - GL | Thirza Iglesias | Loudorn County |  | CANCELED |  | Project Cancelled | Drop Box | [10 empty] | Yes
Richard Vasquez - GL | Marcelo Ortiz | Fairfax County |  | APPROVED 4.25 | NA | Applied Dominion | Drop Box | issued
Abdi Mohamed - DV | Derrol Mcclaren | Montgomery County | MD | N/A | applied | Approved Potomac | Drop Box | issued
Kuega Ekue - SL | Dawit Abraham | PG County | MD | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daysi Martinez - GL | Bianca del Castillo | city of frederick | MD | APPROVED 4.25 | NA | Approved Potomac | Drop Box | in review
Rotimi Shittu - SL | Thornton Fennell | PG County | MD | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daniel Andres Yanez - GL | Carlos Cueto | Frederick County | MD | APPROVED 4.25 | applied | Applied SVEC | Drop Box
James Arthur - SL | Jonathan NGO | Charles County | MD | APPROVED 4.25 | approved | Conditionally Approved SMECO | Drop Box | issued
Andrian Cruz - DV | Derrol Mcclaren | Montgomery County | MD | N/A | approved | Approved Potomac | Drop Box | issued | TBS
TRAVIS MELSON - SN | USA Solar Network | Petersburg City |  | N/A | NA | Have Bill Dominion HOI | On Hold
Matthew Dreitlein - EZ | Peter Kyke | Fairfax County |  | N/A | applied | Approved Dominion | Drop Box | issued
Melat & Fanual Dawit - EZ | Inside Sales | Distric of Columbia County |  | N/A | NA | Applied-Pepco | Drop Box | in review
David Brunco - CASH | Peter Kyke | Butler County |  | N/A | NA | Approved Penn Power | Drop Box
Ethan Pacifico - DV | Danny Dubois | Town of Herndon |  | N/A | Approved | Approved Dominion | Drop Box | Issued
Fermin Kelly - SL | Remesh Sertani | Wicomico County | MD | APPROVED 4.25 | NA | Approved-Pepco(Delmarva Power) | Drop Box | applied
Mike Mendley - DV | Skylighting | Montgomery County | MD | N/A | no need for approval | Approved-Pepco | Drop Box | Issued
Adolfo Mata Garcia - GL | Carlos Cueto | PG County | MD | CANCELED | NA | Applied-Pepco(Project Withdrawn) | Drop Box | applied | [9 empty] | Yes
Dawn Frisby - GL | Skylightnrg | PG County | MD | ON HOLD UNTIL NTP | approved | Approved-Pepco | Drop Box | in review
Michael Chernau - CASH | Tim Clark | Henrico County |  |  | NA | Applied- Dominion | Drop Box | in review
Douglas Ross - GL | Skylighting | Montgomery County | MD | APPROVED 5.19 | NA | Applied-Pepco | Drop Box
Melvin Hernandez - GL | Marcelo Ortiz | Montgomery County | MD | APPROVED 5.11 | NA | Approved-Pepco | Drop Box | issued | TBS
James M. McDermott - SL | Charles Carufel | Loudorn County |  | APPROVED 5.4 | Approved | Approved Dominion | Drop Box | in review | TBS
Doris Scott - GL | Mark Davis | PG County | MD | CANCELED | need info | f | ELD on Hold | applied | [9 empty] | Yes
Nicholas Hinko - SL | Charles Carufel | Loudoun County |  | APPROVED 5.5 | Approved | conditional /Approved SMECO | Drop Box | in review | TBS
Karima Ali - DV | Skylighting | Loudorn County |  | N/A | applied | Applied - Dominion | Drop Box | in review
John Whelan - DV | Jedi | Frederick County | MD | N/A | applied | Approved-Potomac | Drop Box | issued
Michael Sparks - DV | Jedi | Charles County | MD | N/A | NA | approved-Smeco | Drop Box | issued
Travis Melson - GL | USA Solar Network | Chesterfield County |  | ON HOLD UNTIL NTP | NA | Applied- Dominion | Drop Box
Candance Watson - SN | Greg Jonhson - BBS | Chesterfield County |  | N/A | NA | Approved Dominion | Drop Box | issued
GARFIELD KELLIER - SN | Jonathan NGO | PG | MD | N/A | applied | Applied-Pepco | Drop Box | in review
Thomas Hayhurst - DV | Skylightngr | Garrett County | MD | N/A | to follow | have UB | 200 Amp/On Hold
Carlos M. Claros - GL | Marcelo Ortiz | Prince William County |  | APPROVED 5.2 | approved | Approved Dominion | Drop Box | Applied
Mary Borders - DV | Skylighting | Montgomery County | MD | N/A | NA | Applied-Pepco | Drop Box | Applied
Carolina Sanchez - GL | Carlos cueto | PG County | MD | APPROVED 5.2 | NA | Applied-Pepco | Drop Box | in review
Tabitha Demaio - SL | Derrol Mcclaren | Charles County | MD | ON HOLD UNTIL NTP | NA | need bill | 200 Amp/On Hold
Richard Cook/Betty Siu - DV | Elijah Sutton | Charles County | MD | N/A | NA | conditional /Approved SMECO | Drop Box | issued
Jose Guzman - SN | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Approved- Dominion | Drop Box | Applied | [9 empty] | Yes
Giles Nathaniel Cooke Jr - GL | Thornton Fennell | PG | MD | APPROVED 5.20 | NA | Approved-PEPCO | Drop Box | in review
Jose Arbaiza - GL | Carlos cueto | Montgomery County | MD | APPROVED 5.10 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Marina I. Tejada - DV | Ana Romero | PG | MD | APPROVED 5.7 | NA | Approved-Pepco | Drop Box | in review
Thomas Broach - GL ( Ground Mount) | SolarStrong | Fayette County |  | APPROVED 5.5 | NA | applied-Appalachian power | Drop Box
Regan Crump - CASH | Inside Sales | Montgomery County | MD | N/A | Approved | Applied Potomac | Drop Box | issued
Richard Fecher - CASH | Peter Kyle | Loudorn County |  | N/A | need action | Applied dominion | Dropbox
Sandra Schultz - GL | Mark Davis |  |  | CANCELED | [13 empty] | Yes
Fidel Santos - GL | Raf Solar | Montgomery County | MD | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | applied
Lyle Craddock - GL | True Energy (David Twitty) | Boone County |  | APPROVED 5.5 | NA | Applied Applachian Power | Drop Box
Tamara Perez - GL | IDC | PG | MD | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | in review
Crystal Sprowls - EZ | Inside Sales | Allegheny County |  | N/A | need info | Have Dequesne Light | 200 Amp/On Hold
Vincent Lombardi - GL | True Energy (David Twitty) | Tucker County |  | APPROVED 5.23 | NA | Have Bill-MonPower | 200 Amp
Blake Bozeman - SN | Inside Sales | District of Columbia |  | N/A | NA | Approved-Pepco | Drop box | in review
Celia Delara - SN | Jonathan NGO | Hardford County | MD | N/A | NA | Applied-BGE | Drop box | in review
Kemberly Gutierrez - SN | Thornton Fennell | PG County | MD | N/A | NA | Applied-Pepco | Drop Box
Anthony Turner 1 - DV | Skylightnrg | Baltimore County | MD | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop box
Anthony Turner 2 - GL | Skylightnrg | Baltimore County | MD | ON HOLD UNTIL NTP | NA | BGE | ELD On Hold/MSP Pics Needed
Anselmo Guzman - GL | Raf Solar | PG County | MD | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Renett Little - GL | IDC | PG County | MD | APPROVED 5.10 | Approved | Approved-Pepco | Drop box | in review
Auildo Kelly Azor - SL | Remesh Sertani | Wicomico County | MD | CANCELED | NA | Approved-Pepco(Delmarva Power) | Drop box | [10 empty] | Yes
Lee Webb - GL | True Energy (David Twitty) | Fayette County |  | APPROVED 5.10 | NA | Have Bill-Appalachian Power | Drop box |  | Notes: Take Two 20 and Two 15 Single Pole QO Tandum breaker
Glenn Allander - GL | Daniel Gibson | Cumberland County |  | APPROVED 5.10 | NA | Applied PPL | Drop box
Jacob Richmond- EZ | Sam Albert | Wythe County |  | N/A | need info | on Hold | Drop box
Sandra Gascon-Gracia - CASH | Sam Albert | Cumberland County |  | N/A | need info | have bill PPL | 200 Amp (In Progress)
Brandy Shamrock - DV | Skylightnrg | Franklin City |  | N/A | NA | Approved dominion | Drop box
Ivy Freeman - SL | Charles Carufel | Cumberland County |  | APPROVED 5.11 | applied | Applied Novec | Drop Box
Mariam Menkir - DV | Derrol Mcclaren | Charles County | MD | N/A | in review | Approved SMECO | Drop Box | issued
Vivian Segovia - GL | Thirza Iglesias | Frederick County | MD | CANCELED | NA | Approved-REC | Drop Box | [10 empty] | Yes
Frank Mestecky - GL | USA Solar Network | Pike County |  | APPROVED 5.19 | applied | Applied Met-Ed | Drop Box
MANUEL GUTIERREZ - SN | Thornton Fennell | PG County | MD | N/A | NA | Approved-BGE | Drop Box | in review
Olivier Komeka - DV | Skylighting | PG County | MD | N/A | to follow | Need Bill | Drop Box | in review
Joseph Flora - GL | True Energy (David Twitty) | Cabell County |  | APPROVED 5.11 | NA | Metert Number require | Drop Box
Shenee Turner - GL | IDC | PG County | MD | APPROVED 5.11 | applied | Approved-Pepco | Drop box | in review
Ramon Campos - GL | Carlos cueto | PG County | MD | APPROVED 5.11 | NA | Approved-Pepco | Drop box | in review
Richard Thornburgh - CASH | Michael Reid | Montgomery County | MD | N/A | NA | Applied-Pepco | Drop box | Applied
Edward Holman - DV | Skylighting | Chesterfield |  | N/A | NA | need HOI | Drop box | [10 empty] | Yes
Maribel Giovanna Sanchez - GL | Carlos cueto | PG County | MD | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Philippa & Danielle Durham - CASH | Inside Sales | Caroline County | MD | N/A | need info | Conditional Approved-Choptank | Drop Box | applied
Kenia Benitez - GL | Marcelo Ortiz | Harrisonburg City |  | CANCELED | NA | Applied SVEC | Drop Box | [10 empty] | Yes
Luis Perez - EZ | Peter Kyle | Spotsylvania County |  | N/A | applied | Approved REC | Drop Box
Anthony Olaiya Oni - GL | Thornton Fennell | Baltimore County | MD | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop Box
Thai-Anh Perry - SL | Charles Carufel | Prince William County |  | STIP - OWNERSHIP | in review | Approved-Novec | Drop Box
MARLYN PIPER WILLIAMS - SN | Samuel Edwards | PG County | MD | N/A | need info | Applied-Pepco | Drop Box | in review
Edward Miller - DV | Skylightnrg | Howard County | MD | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Collins - GL | Heath Dewalt (Nitro) | Charlottesville City |  | ON HOLD UNTIL NTP | need info
Susan Silman - GL | True Energy (David Twitty) | Kanawha County |  | APPROVED 5.16 | NA | Applied-Appalachian | Drop Box
Blanca R Guzman Escobar - GL | Ana Romero | Montgomery County | MD | APPROVED 5.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Benjamin Bacon - DV | Skylighting | Frederick County | MD | N/A | approved | Approved Potomac | Drop Box | issued
Jamie Summers - GL | Strong Solar | Kanawha County |  | APPROVED 5.18 | NA | Applied-Appalachian Power | Drop Box
Ravinder Mathaudu - SN | Samuel Edwards | Montgomery County | MD | N/A | need info | need bill
Everth Alvarado - DV | Danny Dubois | Manassas City |  | N/A | need info | Need Info | Drop Box | [10 empty] | Yes
Kuele Ndingsa - GL | Mark Davis | PG County | MD | APPROVED 5.27 | NA | Approved-BGE | Drop Box | in review
Jeff Boggs - GL | Strong Solar | Kanawha County |  | APPROVED 5.16 | NA | Applied-Apalachian Power | Drop Box
Joseph Cotterino - GL | Quativa | Carbon County |  | STIP - OWNERSHIP | NA | PPL | Drop Box
Nang and Hong Huynh - DV | Danny Dubois | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | issued
Isaias Bustamante - GL | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Applied Dominion | Drop Box | [10 empty] | Yes
Edith S Gonzalez Mejia - GL | Carlos cueto | Anne Arundel County | MD | APPROVED 6.3 | applied | Approved-BGE | Drop Box | applied
Georgia Thomas - GL | Aaron Dawkins | PG County | MD | APPROVED 5.119 | NA | Approved-Pepco | Drop Box | in review
Gabriel Rosenberg - SL | Charles Carufel | Fairfax County |  | APPROVED 5.19 | NA | need correct HOI | Drop Box | applied
Michael Newkirk Jr - SN | Ric Peters | Anne Arundel County | MD |  | NA | Approved-BGE | Drop Box | applied
JACQUELIN MARTINEZ - SN | Ric Peters | Anne Arundel County | MD | N/A | NA | Approved-BGE | Drop Box | applied
Carol Jackson - DV | Skylighting | Charles County | MD | ON HOLD UNTIL NTP | to follow | Approved Smeco | Drop Box | applied
Wubishet Yizengaw - DV | Skylighting | Montgomery County | MD | N/A | NA | Applied-Pepco | Drop Box | issued
Florinda Escobar - GL | Raf Solar | PG County | MD | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Janice Walters - GL | Thornton Fennell | PG County | MD | APPROVED 5.20 | NA | Applied-Pepco | Drop Box | in review
Rosalba Ayala Magana - GL | Thirza Iglesias | Frederick County | MD | NEED CORRECTION/ADDRESS | need action | Applied-REC | Drop Box
Yessenia Rios rubio - SL | Dawit Abraham | PG County | MD | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
David Poindexter - SL | Malik Walker | PG County | MD | APPROVED 5.20 | need action | Applied-Pepco | Drop Box | applied
Kathy Rivera - GL | Quativa | Chesterfield County |  | APPROVED 5.20 | NA | Need HOI | Drop Box | applied
Scott Seladoki - GL | Quativa | Ohio County |  | APPROVED 5.20 | NA | Applied Appalachian Power | Drop Box
Rhys Buntua - CASH | Peter Kyle | Fairfax County |  | N/A | NA | Applied Dominion | Drop Box | applied
Krystle Gray - GL | Ismael | Anne Arundel County | MD | APPROVED 5.28 | NA | Approved-BGE | Drop Box | applied
Abilio Hernandez - GL | Marcelo Ortiz | PG County | MD | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Syed Abbas - CASH | Theodore Brown | Howard County | MD | N/A | applied | Approved-BGE | Drop Box | Issued
María Angélica Ventura Chavez - DV | Bianca del Castillo | Montgomery County/ City of Gaithsburg/City of rockville | MD | APPROVED 5.24 | NA | Applied-Pepco | Drop Box
David Bentley - GL | True Energy (David Twitty) | Clay County |  | CANCELED | [13 empty] | Yes
Jai Patel - DV | Skylightngr | Harford County | MD | APPROVED 5.24 | applied | Applied-BGE | Drop Box
Toi Wiseman - GL | Ismael | PG County | MD | APPROVED 5.24 | NA | Applied-Pepco | Drop Box | in review
Santos Menjivar - DV | Bianca del Castillo | Frederick County | MD | N/A | NA | Approved Potomac | Drop Box
Neil de Castro - DV | Danny Dubois | Virginia Beach City |  | ON HOLD UNTIL NTP | NA | Applied-Dominion | Drop Box
Shahjahan Molla - CASH | Peter kyle | Cumberland County |  | N/A | NA | Approved PPL | Drop Box
Patrick Norman - CASH | John Lee | Arlington County |  | N/A | NA | need new bill | Drop Box | issued
Christina Sanchez - SL | Eric Strouse | Raleigh County |  | STIP - CUSTOMER NEEDS TO CALL SL | NA | applied-Apalachian Power | Drop Box
Eduviges Zavala - DV | Bianca del Castillo | Montgomery County | MD | STIP - ID | NA | Applied-Pepco | Drop Box
Lilian Maribel Martinez Orellana - DV | Bianca del Castillo | Montgomery County | MD | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | applied
Jaime Cordero - GL | Marcelo ortiz | Montgomery County | MD | APPROVED 5.25 | applied | Applied-Pepco | Drop Box | applied
Ebony Shirley - GL | IDC (Ishmael) | PG County | MD | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | in review
Robert Feeman - GL | Quativa | Cumberland County |  | APPROVED 5.25 | need action | Have bill PPL | Drop Box
Rene Smith/Patrick Ward - DV | Skylighting | Frederick County | MD | CANCELED | NA | Have Bill-Potomac | [11 empty] | YES
David J. Poindexter III - SL | Malik Walker | PG County | MD | APPROVED 5.25 | NA |  | 200 Amp/In Progress | applied
Craig Vaughan - CASH | SolarSurge | Chesterfield County |  | N/A | NA |  | Drop Box | in review
Benedicta Njoku - GL | Dawit Abraham | District of Columbia |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
Anthony Aponte - GL | Quativa | Spotsylvania County |  | APPROVED 5.27 | NA | Have bill & HOI | 200 Amp/Sunova Design
Patrick German - CASH | Quativa | Charles County | MD | N/A | NA | Have bill SMECO | 200 Amp/Sunova Design
John Kolber - CASH | Inside Sales | Cumberland County |  | N/A | need info |  | ELD On Hold/MSP Pics Needed
Matthew Herbaugh - CASH | Inside Sales | Isle of Wight County |  | N/A | need info |  | Drop Box | in review
Boleslaw Stefanski - CASH | Inside Sales | Pike County |  | N/A | need action |  | Dropbox
Nick Vattimo - CASH | Inside Sales | Frederick County | MD | N/A | need info |  | In Review
Emundo Trivelli - SL | Inside Sales | Prince William County |  | APPROVED 6.1 | need info | Applied Dominion | Drop Box
Jonathan Araya - CASH | Inside Sales | Loudoun County |  | N/A | need info | Apllied Dominion | Drop Box
Raed Jarrar - EZ | Inside Sales | District of Columbia |  | N/A | need info | Pepco | Sunnova Design | applied
Melanie Johnson - SL | Aaron Dawkins | PG County | MD | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | applied
Cheryl Baker - SL | Eric Strouse | Mineral County |  | IN REVIEW | NA | Applied Potomac | Drop Box
Rosalynn Asamoah - DV | Skylighting | Montgomery County | MD | STIP - ACH | need action | Have Bill Potomac | Inverter Details N/A
Sergio Martinez - DV | Skylighting | Baltimore City | MD | STIP - OWNERSHIP | NA | Applied-BGE | Drop Box | Applied
Kevin Kidwell - CASH | Quativa | Hampshire County |  | N/A | NA |  | Inverter Details N/A
Patrick Primm - GL | Quativa | ClearField County |  | APPROVED 5.31 | NA | Have Bill-Potomac | ELD On Hold/MSP Pics Needed
Cyrus Hormozi - GL | Skylighting | Washington County | MD | APPROVED 5.31 | approved | Approved Potomac | Drop Box
Socoya Gorham - GL | Brandon Hyman | District of Columbia |  | IN REVIEW | NA | Applied-Pepco | Drop Box | applied
Sean Hodgins - GL | Skylighting | Baltimore City | MD | APPROVED 6.1 | NA | Applied-BGE | Drop Box
Liz Ehrich - CASH | John Lee (Inside Sales) | Stafford County |  | N/A | need action | Applied -Dominion | Drop Box
Harrison Parson - CASH | Tim Clark (Inside Sales) | Susquehanna County |  | N/A | NA | Have Bill-Penelec | In Progress/Waiting fo Client Consultation
Rene Humberto Suarez- GL | Ana Romero | PG County | MD | APPROVED 6.2 | NA | Applied-BGE | Dropbox | applied
Adrian Herring - SL | Tim Clark (Inside Sales) | Allegheny County |  |  | need info |  | Everbright Design N/A
Carol Smith - SL | Solar Strong | Taylor County |  | APPROVED 6.2 | NA |  | 200 amp/Everbright Design
Ramiro Moya - GL | Carlos cueto | Montgomery County | MD | APPROVED 6.3 | need action | Applied Potomac | Drop Box | applied
Edgar Sorto - GL | Raf Solar | Winchester City |  | APPROVED 6.3 | applied |  | Drop Box
Mayor William Sanders III - 1 |  |  |  |  | need info
Mayor William Sanders III - 2 |  |  |  |  | need info
Olufemi Oluwatobi Ikusika - DV | Skylighting | Baltimore County | MD | APPROVED 6.6 | need action | Applied-BGE | Dropbox
Frank Trujillo - CASH | Peter Kyle ( Inside sales) | Prince William County |  | N/A | applied | Applied -Dominion | Dropbox
Jason Chandler - GL | John Lee (Inside Sales) | District of Columbia |  | STIP | NA | Approved-Pepco | Dropbox | applied
Linda and James Dwyer - CASH | John Lee (Inside Sales) | PG County | MD | N/A | need info |  | Dropbox | applied
James Rodgers - GL | Aaron Dawkins | District of Columbia |  | APPROVED 6.7 | NA | Applied-Pepco | Dropbox | applied
Omotayo Ogundana - GL | Thornton Fennell | PG County | MD | STIP - ID | need info |  | ELD on Hold | applied
Timothy Dixon - SL | John Lee (Inside Sales) | Howard County | MD | NEED CORRECTION | need action | Have Bill-BGE | Sunnova Design//200 amp/Waiting fo Client Consultation
Karen Ireland - CASH | John Lee (Inside Sales) | Montgomery County | MD | N/A | NA | Applied-Pepco | Dropbox | applied
James Ortmann | John Lee (Inside Sales) | PG County | MD |  | NA | Applied-Pepco | Dropbox | applied
Christopher Arzadon - SL | John Lee (Inside Sales) | Prince William County |  | APPROVED 6.8 | need action | Have Bill-Dominion | Dropbox
Olawale Tolulope Ayorinde - SN | IDC (Ishmael) | PG County | MD | N/A | need action | Have Bill-Pepco | 200 amp/In progress | applied
Emma Davenport - DV | Skylighting | Baltimore County | MD | APPROVED 6.8 | NA | Have Bill-BGE | Site Visit Requested
Matthew Beyers - DV | Skylighting | Frederick County | MD | STIP - ACH | need action | Applied Potomac | Dropbox
Christopher Means - SL | Eric Strouse | Kanawha County |  | APPROVED 6.8 | NA | Applied Appalachian | Dropbox
Charles Messerschmidt - GL | Ric Peters | Anne Arundel County | MD | APPROVED 6.9 | NA | Applied-BGE | Dropbox
Heather Levander - | Quativa | Fayette County |  |  |  |  | Everbright Design N/A
Harold Gerhart - GL | Quativa | Cumberland County |  | CHANGE ORDER? | NA | Have Bill PPL | Inverter Details N/A
Justin Strickland - GL | Quativa | Cumberland County |  | APPROVED 6.9 | NA | Have Bill-PPL | Everbright Design N/A
Berta Lidia - GL | Marcelo Ortiz | Frederick county | MD | APPROVED 6.9 | NA | Have bill potomac
Kenneth Blankenship - SL | Eric Strouse | Nicholas county |  | STIP - OWNERSHIP | NA |  | In Progress
Keith Scarsdale - SL | Mark Davis | Culpeper County |  | IN REVIEW | NA
Sean Magee - CASH | Cinthia Rivera | Loudoun county |  | N/A | NA | Have bill dominion | Drop Box
Todd Benbow - DV | SkylightNGR | Charlotte County |  | IN REVIEW | NA |  | ELD On Hold/MSP Pics Needed
Jlicery Diaz - SL | Eric Strouse | Kanawha County |  | STIP - OWNERSHIP | NA | Have Bill Appalachian AND hoi | drop Box
Austin Snyder - GL | Voltaic (Freddye Jackson) | Lehigh County |  | IN REVIEW |  | PPL | Dropbox
Luis Rosas - GL | Justin Hall | PG county | MD | IN REVIEW |  |  | ELD On Hold/MSP Pics Needed
Fatoumatta Bah - DV | SkylightNGR | Frederick county | MD | IN REVIEW | need action | Have bill potomac | ELD On Hold/MSP Pics Needed
Jose Martinez - GL | Marcelo Ortiz | Montgomery County | MD | IN REVIEW |  |  | In Progress

## VA
NAME | SALES REP | COUNTY | STATE | NTP | HOA | Interconnection | Design | Permit | Installation | Inspection | Meter Change | Access | Registration | PTO Uploaded | SRECs | MD Grant | QA | CANCELLED | PEARL CERTIFICATION
Angel M Lima - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done
Dan Notestein - CASH | Sam Albert | Montgomery County/Town of Blacksburg |  | N/A | approved | Approved VTES | Done | issued | Installation Completed
Juan L Guillen - GL | Thirza Iglesias | Frederick County |  | APPROVED 1.21 | approved | Approved Rappahannock | Done | issued | Installation Completed | Passed | Applied
Fizel Jabbar - DV | Aaron Dawkins | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | site created |  | Done | Done | Done |  |  | Done
Jose Chacon - GL | Carlos Cueto | PG County |  |  | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Julio Fuentes - GL | Carlos Cueto | Montgomery County |  | APPROVED 1.07 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Misael Guillermo - SN | Thornton Fennell | PG County |  |  | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Payment pending | Payment pending |  |  | Done
Willie Ford - GL | Thornton Fennell | PG County |  | APPROVED 1.05 | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Yolanda Zelaya - GL | Sarah Romero | PG County |  | APPROVED 1/10 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Mark Reid - GL | Aaron Dawkins | PG County |  | CANCELED |  |  | Done | [10 empty] | YES
Lynne Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 1/20 | N/A | Approved-Pepco | Done | Issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | Done
Raymond Marquis - GL | Noblesolar | Norfolk County |  | APPROVED 2.4 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Jessie Miles - GL | Noblesolar | Norfolk County |  | APPROVED 1/12 | NA | Approved Dominion | Done | B-Issued | Installation Completed | Passed | Applied | done |  | Received | Done
Yilia Jackson - SN | Ted Brown | Baltimore City |  | N/A | NA | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | done |  | Done
Ronny/Taylor Sylvester - GL | Noblesolar | Chesapeake City |  | APPROVED 2.8 | NA | Approved Dominion | Done | Issued | Installation Completed | Passed | Applied | Done |  | Received | Done
Kathryn Alexander - CASH | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Charles Cucina - DV | Danny Dubois | FrederickCounty |  | N/A | NA | Approved Potomac | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Miguel Angel Vernal Nolasco - GL | Sarah Romero | Baltimore County |  | LOAN CANCELED | NA | Have bill | [11 empty] | Yes
Juan Martinez - DV | Sarah Romero | Winchester City | VA | N/A | NA | Approved SVEC | Done | issued | Scheduled 6/9
Jose H. Baca Oseguera - GL | Ana Romero | PG County |  | APPROVED 2.8 | NA | Approved-Pepco |  | issued | Installation Completed | Passed | Applied | Done | [6 empty] | Done
Oluseyi Ajayi - GL | Noblesolar | Chesapeake City | VA | APPROVED 1.28 | applied | Approved Dominion 02/15/2022 | DONE | Issued | NA
Darryl Girtz - GL | Noblesolar | Norfolk City |  | APPROVED 1.31 | NA | Approved Dominion | Done | Applied-1/24 | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Gerry Evans - GL | Noblesolar | Newport News City | VA | APPROVED 1.24 | approved | Approved Dominion | Done | issued | Installation Completed
Matthew Griffin - GL | Noblesolar | VA Beach City | VA | APPROVED 1.25 | NA | Approved Dominion | Done | issued | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Donald Deely - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done | Issued | TBS
Brayan Godines - DV | Sarah Romero | PG County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved | done |  | Done | Done | Done |  |  | Done
Matthew Gomez - SL | Roberto Smith | PG County |  | APPROVED 1.24 | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Maxie Lawton -GL | Volt (Ishmael) | PG County |  | APPROVED 1.24 | approved | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Engracio Edesar Abris - DV | Danny Dubois | Arlington County | VA | N/A | NA | Approved 03/01/2022 | Done | issued | Installation Completed | Passed |  | Done | [6 empty] | Done
Chris Luk - Cash | Richard Thrutchley | Fairfax County | VA | N/A | approved | Approved Dominion | Done | issued | Scheduled 6/3 |  |  | Done
Nabil Ahmed - SL | Roberto Smith | Montgomery County |  | APPROVED 1.28 | approved | Approved Potomac | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | DONE | Done |  |  | Done
Sharon Flowers - DV | Jedi | PG County |  | CANCELED | applied | Approved-BGE | Done | issued
Maricela Pena - GL | Sarah Romero | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | [9 empty] | Done
Malik Abdunafi - SL | Jedi | Baltimore City |  | APPROVED 2.7 | NA | Approved-BGE | Done | Issued | TBS
Delphine London - NS | Noblesolar | VA Beach City |  | APPROVED 2.7 | approved | Approved Dominion | Done |  | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Gary Hill - GL | Noblesolar | York County | VA | APPROVED 1.28 | APPROVED | Approved Dominion | Done | applied | Installation Completed
Carmen Bona - SN | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Applied PECO | Done
Tyleek Harris - GL | Noblesolar | Newport News City | VA | APPROVED 2.7 | applied | Approved Dominion | Done | issued
Harrison Eacho - GL | Noblesolar | Norfollk City | VA | APPROVED 1/28 | NA | Applied Dominion | Done
Olawole Olayinka - GL | Volt Solar (Freddye) | Howard County |  | APPROVED 1/28 | approved | Approved-BGE | Done | Issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | V.S
Justin Shoemaker - GL | Noblesolar | PG County |  | APPROVED 2.1 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Applied | Done |  | Done | Done |  |  |  | N.S
Adewale Daramola - GL | Noblesolar | Chesapeake City | VA | APPROVED 1.31.22 | applied | Approved Dominion | Done
Silvia Rivera - DV | Sarah Romero | City of Frederick |  | N/A | NA | Approved-Potomac Edison | Done | issued | TBS
Darwin A Fuentes - GL | Alberto Sosa | PG County |  | APPROVED 2.3 | NA |  | Dropbox | issued | [9 empty] | Yes
Charles Hiller - EZ | Sam Albert | Pike County |  | Declined by EZSolarLoan | NA | Applied Met-Ed | Done | [10 empty] | Yes
John Coombs - SL | Roberto Smith | Baltimore County |  | APPROVED 2.1 | NA | Approved-BGE | Done | issued | Installation Completed | [9 empty] | Done
Amy Cervantes - EZ | Sam Albert | Distric of Columbia County |  | N/A | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Eli Apuya - GL | Noblesolar | Suffolk City | VA | APPROVED 2.24 | applied | Approved dominion | Done
Brett Dash - GL | Noblesolar | Suffolk City | VA | APPROVED 2.1 | in review | Approved dominion | Drop Box
Alexander Vasquez Fernandez - GL | Noblesolar | Suffolk City | VA | APPROVED 2.1 | in review | Approved-dominion | Done
Taiwo Olayinka - GL | Volt Solar (Freddye) | Anne Arundel County |  | APPROVED 2.2 | approved | Approved-BGE | Done | in review | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jessica Green - SN | USA Solar Network | Westmoreland County |  | CANCELED | N/A | Applied - Westpenn Power | Drop Box | issued
William Bryan - GL | USA Solar Network | Bucks County |  | APPROVED 2.3 | N/A | Applied PECO | Done | issued
Kimberly Hayes - GL | USA Solar Network | Luzerne County |  | APPROVED 2..3 | N/A | Approved PPL WO 58650550 | Done | issued | Installation Completed | [9 empty] | U.S solar network
Devin Sharp - GL | USA Solar Network | Pittsylvania County | VA | CANCELED | NA | Have Bill Danvill | ELD On Hold | [10 empty] | Yes
James Spadoni - GL | USA Solar Network | Northampton County |  | APPROVED 2.4 | N/A | Applied Met ED | Done
Edward Coley - CASH | USA Solar Network | Montgomery County *PA* |  | N/A | NA | Approved PECO | Done |  | TBS - Roof Pending
Christopher Doane - GL | NobleSolar | Suffolk City | VA | APPROVED 2.4 | applied | Approved-dominion | Drop Box
David Nicklas - CASH | Sam Albert | Allegheny county |  | N/A | NA | Approved DLC | Done
Margaret Galega - SL | Joseph Allo | PG County |  | APPROVED 2.4 | applied | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Raymond Kabacinski - GL | NobleSolar | Norfolk City |  | APPROVED 2.7 | NA | Approved-dominion | Done | B-issued | Installation Completed |  | Applied | Site Created |  | Received | DONE |  |  |  | N.S
Karen Songwe - SL | Aaron Dawkins | PG County |  | APPROVED 2.8 | applied/NO HOA for this address | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | 22.57 |  |  | Done
Jose H Vega Carapia - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | N/A | Approved - potomac Edison | Done | issued
Jonas Chicas - DV | Sarah Romero | Louisa County | VA | N/A | NA | Approved-Dominion | Done | issued | Installation Completed | [9 empty] | Done
Joy Dalesandro - GL - ON HOLD | NobleSolar | Chesapeake City | VA | APPROVED 2.9 | applied | Applied Dominion | Done
Christopher Nunley - GL | SolarStrong | Berkeley County |  | APPROVED 3.23 | NA | Approved Potomac WV | Done | in review | Installation Completed | Passed | Applied | DONE
Kevin Coates - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | in review | [9 empty] | Yes
Francis Hawkins - SL | Thornton Fennell | Charles County |  | APPROVED 2.24 | NA | Approved SMECO | Done | issued | Installation Completed | Passed | Approved | DONE |  | Done | Done | 22.2 |  |  | Done
Jon Walman - DV | Skylightnrg | Stafford County | VA | N/A | NA | Project Cancell (James Nguyen) | Done | [10 empty] | Yes
Britteny Stone-Joel - GL | NobleSolar | Isle of Wight County | VA | APPROVED 3.1 | approved | Approved-Dominion | Drop Box | issued | Installation in Progress |  |  | DONE
Donna Delgado-Johnson - SL | Thornton Fennell | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  | Done |  |  | Done
Kenneth King - GL | NobleSolar | Hampton City |  | APPROVED 2.14 | N/A | Approved-Dominion | Done | issued | Installation Completed |  | Applied | Done |  | Uploaded | Done |  |  |  | N.S
Jaramie York - SN | Jedi | Charles County |  | CANCELED | NA | Have Bill SMECO | [11 empty] | Yes
Jose Oscar Velasco - GL | Carlos Cueto | Montgomery County |  | APPROVED 2.15 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Melvin Blackwell - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved- Pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Kenmanze Edmonds - GL | NobleSolar | Isle of Wight County | VA | PROJECT CANCELED | NA | Have bill | [11 empty] | Yes
Christopher Bonzek - CASH | Inside Sales | Newport News City | VA | N/A | NA | Approved dominion | Done | issued | TBS - Rec Panels
Mary Clowe - SL | Thornton Fennell | PG County |  | APPROVED 2.14 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mridul Gupta - DV | Skylightnrg | Henrico County |  | N/A | approved | Approved dominion | Done | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | skylight
Jose Blanco - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Blanca Arevalo - GL | Raf Solar | PG County |  | APPROVED 2.14 | NA | Approved PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Mark Whitling - GL | NobleSolar | VA Beach City | VA | APPROVED 2.14 | deal cancelled | deal cancel | [11 empty] | Yes
Joe Leugers - GL | NobleSolar | Suffolk City | VA | APPROVED 2.23 | approved | Approved dominion | Drop Box | issued | Installation Completed |  | Applied | Done | [6 empty] | N.S
Alejandra Juarez - GL | Raf Solar | PG County |  | APPROVED 2.15 | NA | Approved-Pepco | Done | issued | [9 empty] | Yes
Paul Warren - GL | NobleSolar | VA Beach City | VA | APPROVED 2.15 | need action |  | Drop Box | [10 empty] | Yes
Miguel Vernal - GL | Raf Solar | Baltimore County |  | APPROVED 2.15 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
William Smith - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.15 | NA | Approved-pepco | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Eros Lazzerini - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Done | issued | Installation Completed | Passed | Approved |  |  | Done |  |  |  |  | Done
Cletus Ayuk - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved |  |  | Done | Done | Done |  |  | Done
Hannah Emert - GL | NobleSolar | Suffolk City | VA | APPROVED 2.17 | applied | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done | [6 empty] | N.S
Franklin A Garcia - GL | Alberto Sosa | PG County |  | APPROVED 2.16 | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Guillermo West - GL | Volt Solar (Freddye) | PG County |  | APPROVED 2.18 | NA | Approved- PEPCO | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Shirlene Ogburn - DV | Skylightnrg | Charles County |  | N/A |  | Project Cancel by Dealer | [11 empty] | Yes
Kelsey Mijal - GL | NobleSolar | Chesapeake City |  | APPROVED 2.16 | NA | Approved dominion | Done |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Danielle Goodrum - GL | NobleSolar | Chesapeake City | VA | APPROVED 2.16 | applied | Approved dominion | Done
Nathan Carl - GL | NobleSolar | Portsmouth City | VA | APPROVED 3.8 | NA | Approved dominion | Drop Box | in review | Scheduled 5/27 | Passed
Meaghan Jenks - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Done | issued | Installation Completed | Passed | Applied | Done |  |  | DONE |  |  |  | Done
Queenie May Escubio - EZ |  | Portsmouth City | VA | APPROVED 2.17 | NA | Approved dominion | Done | in review | Scheduled 5/28 | Passed | Applied
Alexander Phillips - GL | NobleSolar | Chesapeake City | VA | APPROVED 2.17 | applied | Approved dominion | Done | issued
`William Sanders - CASH | Solarsurge | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | in review
Michelle Gomez - GL | Alberto Sosa | PG County |  | APPROVED 3.1 | NA | Approved-Pepco | Drop Box | issued | [9 empty] | Yes
George Knight - GL | NobleSolar | Chesapeake City | VA | APPROVED 2.25 | NA | need policy no# | Drop Box
May Petalcorin - GL | NobleSolar | Suffolk City | VA | PROJECT CANCELED | need action | [12 empty] | Yes
DePaul Griffin - GL | NobleSolar | Chesapeake City |  | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed | Passed | Applied | Done |  | Received | Done |  |  |  | N.S
Richard Taylor - GL | NobleSolar | VA Beach City | VA | APPROVED 2.21 | NA | Approved dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Rebecca Phillips Ferguson - GL | NobleSolar | Suffolk City | VA | APPROVED 2.24 | applied | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Peter Keller - CASH | Solarsurge | Montgomery |  | N/A | NA | Have bill-Pepco
Malcolm Dixon - GL | NobleSolar | Chesapeake City | VA | APPROVED 2.21 | in review | Approved dominion | Drop Box
Michael Osumlalu - GL | NobleSolar | Chesapeake City | VA | APPROVED 2.21 | in review | Approved dominion | Drop Box
Constance Kinge -SL | Aaron Dawkins | PG County |  | APPROVED 2.21 | NA | Approved PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Jennifer Joynes - SL | Jedi | Pricness Ann |  | APPROVED 2.21 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | TBS
Ruperto Rivera - GL | Raf Solar | Montgomery County |  | APPROVED 2.21 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed |  | Site created | [6 empty] | Done
Salvador Cueva - GL | Thirza Iglesias | City of frederick |  | APPROVED 2.21 | NA | Approved Potomac Edison | Drop Box | issued | Installation in Progress
Martin Medina Estrada - GL | Carlos Cueto | Town of Elkton |  | APPROVED 2.25 | NA | Approved- PEPCO(Delmarva) | Drop Box | issued | TBS
Luisa Figaro - SL | Remesh Sartani | Princess Anne |  | APPROVED 2.25 | NA | Approved- PEPCO | Drop Box | issued | Installation Completed
Fernando Ortez - GL | Raf Solar | Prince William County |  | APPROVED 2.25 | NA | Approved NOVEC | Done | [10 empty] | Yes
Telesfora Briones - GL | Raf Solar | City of Annapolis |  | APPROVED 2.21 | approved | Approved- BGE | Done | applied
Lap T. Vo - SL | Michael Reid | Montgomery County |  | APPROVED 2.21 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Candy Huynh - GL | NobleSolar | Chesapeake City | VA | APPROVED 2.21 | applied | Approved Dominion | Drop Box |  | Installation Completed | [9 empty] | N.S
Keith Layne - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.1 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Oscar Jimenez - GL | Raf Solar | Prince william |  | APPROVED 2.25 | NA | Approved - NOVEC | Drop Box | In review
George Hoskin - SL | Michael Reid | Montgomery County |  | APPROVED 3.4 | NA | Approved- BGE | Done | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Octavia Pearson - GL | Thornton Fennell | PG County |  | APPROVED 2.24 | NA | Approved - PEPCO | Drop Box | issued | Installation in Progress | Passed | Approved |  |  | Done | Monit not done | Done
Nicolas Lovo - GL | Raf Solar | Charles County |  | APPROVED 3.1 | applied | Approved - SMECO SMECOINT-08593 | Drop Box | Applied
Marcos A Flores - GL | Ana Romero | City of Frederick |  | APPROVED 2.24 | NA | Approved potomac | Drop Box | issued | TBS
Paul Rudicki - GL | NobleSolar | Chesapeake City |  | APPROVED 2.24 | NA | Approved Dominion | Drop Box |  | Installation Completed |  | Applied | Done |  |  | DONE |  |  |  | N.S
Katherine Heun - GL | NobleSolar | Chesapeake City | VA | APPROVED 2.25 | NA | Approved Dominion | Drop Box |  | Installation Completed |  |  | Done | [6 empty] | N.S
Kyle Scherele - GL | NobleSolar | Hampton City | VA | APPROVED 2.24 | NA | Approved Dominion | Drop Box | in review | Installation Completed | [9 empty] | N.S
Myrna Michelle Flores - GL | NobleSolar | VA Beach City | VA | APPROVED 3.1 | approved | Approved dominion | Drop Box |  | Installation Completed |  | Applied | Done | [6 empty] | N.S
Santos Soto - GL | NobleSolar | Suffolk City | VA | APPROVED 2.24 | applied | Approved dominion | Drop Box | [10 empty] | Yes
Mary Rampolla - DV | Skylightnrg | Howard County |  | N/A | NA | Approved- BGE | Drop Box | [10 empty] | Yes
Tracy Winters - SN | USA Solar Network | Delaware County |  | CANCELED | need info | Have Bill - PECO | [11 empty] | Yes
Santos Rivera - GL | Raf Solar | Frederick County |  | APPROVED 2.25 | NA | Have Bill - Dominion | Drop Box | [10 empty] | Yes
Leslie Braithwaite - DV | Skylightnrg | PG County |  | N/A | NA | Applied - PEPCO | Done | in review | [9 empty] | Yes
Keith Wilburn - GL | NobleSolar | Suffolk City | VA | APPROVED 2.25 | applied | Approved dominion | Drop Box
Thanaporn Cockran - SL | Jedi | Anne Arundel County |  | APPROVED 5.13 | NA | Approved-BGE | Drop Box | issued | TBS
Florimon Arrey Ndip Etta - GL | Aaron Dawkins | PG County |  | APPROVED 2.28 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Site created |  | Done | DONE | Done |  |  | Done
Yamarco Figaro - SL | Remesh Sartani | Wicomico County |  | APPROVED 2.28 | NA | Approved-PEPCO(Delmarva) | Drop Box | issued | Installation Completed | [9 empty] | Done
Veronica Brooks - SL | Thornton Fennell | PG County |  | APPROVED 2.28 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | Monit not done | Done |  |  | Done
Garrye Hepburn - GL | Skylightnrg | PG County |  | APPROVED 3.1 | approved | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | skylight
Adriene Muhammad - DV | Skylightnrg | Branchville | VA | N/A | NA | Approved Dominion | Drop Box
Ron Leese - DV | Skylightnrg | Carroll County |  | N/A | NA | Approved-BGE | Drop Box | applied
Samuel Nelson - GL | Inside Sales | Distric of Columbia County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Site Created
Jorge A. Soto Sanabria - GL | Thirza Iglesias | PG County |  | APPROVED 3.2 | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Site Created | [6 empty] | Done
Federico Vega - GL | Thirza Iglesias | Winchester City | VA | APPROVED 3.2 | NA | Applied SVEC | Drop Box | issued
Tae Kim - DV | Skylightnrg | Montgomery County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS | [8 empty] | Yes
Raul Morales Martínez - GL | Carlos Cueto | PG County |  | APPROVED 3.8 | NA | Approved-Pepco | Drop Box | issued | Installation In Progess
Jose Campos - GL | Carlos Cueto | PG County |  | APPROVED 3.4 | NA | Approved-PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE | Done |  |  | Done
Jesus Aguilera - GL | Raf Solar | PG County |  | APPROVED 3.4 | HOA approved | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done |  | SS above 20 |  |  | Done
Miguel Mendoza - GL | Raf Solar | Gaithersburg City |  | APPROVED 3.4 | approved | Approved-PEPCO | Drop Box | in review | Installation In Progess
Steven Miles - GL | Volt Solar (Freddye) | Accokeek County/PG |  | APPROVED 3.9 | NA | Approved SMECO | Drop Box | issued | Installation Completed | [9 empty] | V.S
Virginia Chaziva - GL | Aaron Dawkins | PG County |  | APPROVED 3.9 | applied | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Dilsa Rosales Moscoso - GL | Ana Romero | Montgomery County |  | APPROVED 3.3 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  |  | Done |  |  |  | Done
Mary Satterwhite - SN | Jonathan Ngo | Loudoun County | VA | N/A | approved by Jon | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received |  |  |  |  | Done
Patrick Brown - SL | Ric Peters | Baltimore County |  | APPROVED 3.9 | NA | Approved- BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | Done
Philip Faxio - GL | Volt Solar (Brandon) | Distric of Columbia County |  | APPROVED 3.9 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Trad Leavitt - DV | Skylightnrg | Frederick County |  | N/A | approved | Approved Rappahannock | Drop Box | issued | Installation Completed | Passed | Applied | Done
Dante Fenwick - GL | Skylightnrg | PG County |  | APPROVED 3.9 | in review | Approved-Pepco | Drop Box | issued
Steve Kinaman - EZ | Inside Sales | Loudoun County | VA | N/A | approved | Approved Dominion | Drop Box | issued | Scheduled 6/2 | Passed | Applied
Raja Balasubramanian - CASH | Inside Sales | Loudoun County |  | N/A | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Applied | Done |  | Received | DONE |  |  |  | Done
Jian Liu - SL | Roman Bondari | Loudoun County | VA | APPROVED 3.11 | approved | Approved Dominion | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Received |  |  |  |  | Done
Michael Mills - SL | Jedi | Wicomico County |  | APPROVED 3.11 | NA | Approved - PEPCO(Delmarva) | Drop Box | applied | Scheduled 6/2
Karla Martinez - GL | Raf Solar | Fauquier County | VA | APPROVED 3.15 | approved | Approved Dominion (modifications) | Drop Box | in review (modifications) | Installation in Progress
Rita Fallon - SL | Ric Peters | Anne Arundel County |  | APPROVED 3.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
David Sheffey - SN | Thornton Fennell | PG County |  | N/A | NA | Applied - PEPCO | Drop Box | issued
Jaiyeola Oluwatosin - GL | USA Solar Network | PG County |  | APPROVED 3.14 | need info | Applied- PEPCO | Drop Box | in review
Ureka Wise - GL | Volt Solar (Ishmael) | PG County |  | APPROVED 3.14 | approved | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | V.S
Adam Karaffa - GL | USA Solar Network | Westmoreland County |  | APPROVED 3.14 |  | Approved Westpenn Power | Drop Box
Martha Rodriguez - DV | Michael Reid | Prince William County |  | N/A | approved | Approved- Dominion | Drop Box | Applied
Jordan Calabrese - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
Joseph Sheffey - DV | Thornton Fennell | PG County |  | N/A | NA | Approved-PEPCO | Drop Box | in review | Installation Completed | [9 empty] | Done
Jose Yaselli - SN | Jedi | Carroll County |  | N/A | NA | Approved-BGE | Drop Box
Saqr Alawdi - GL | NobleSolar | Hampton City | VA | APPROVED 3.23 | NA | Have bill and HOI | ON HOLD | [10 empty] | Yes
John Delgadillo - DV | Jonathan Ngo | Chesterfield County | VA | N/A | NA | Approved- Dominion | Drop Box | issued | Installation Completed | [9 empty] | Done
Joel Gonzalez - GL | Marcelo Ortiz | Fairfax County | VA | APPROVED 3.17 | NA | Approved 4/4/22 | Drop Box | issued | Installation Completed | Passed | Applied | [7 empty] | Done
Arthur Cockran - SL | Jedi | Queen Anne County |  | ON HOLD UNTIL NTP | NA | Approved Choptank Electric | Drop Box | in review
Jose R Guzman Delcid - GL | Ana Romero | City of frederick |  | CHANGE ORDER 5.24 | NA | Approved potomac | Drop Box | issued
Janet Thompson - CASH | Inside Sales | Stafford County | VA | N/A | approved | Approved- Dominion | Drop Box | in review
Omkar Prabhu - CASH | Inside Sales | Monroe County |  | N/A | NA | Approved - PPL | Drop Box | issued | TBS
Delia/Joseph Palmer - GL | NobleSolar | Suffolk City | VA | CANCELED | need action | have bill & HOI | ELD on hold | [10 empty] | Yes
Misael Moreno - GL | Raf Solar | Anne Arundel County |  | APPROVED 3.31 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | Done
Rose Bennett - DV | Skylightnrg | Howard County |  | PROJECT CANCELED | need action | Cancelled by Skylight (Adrienne) | [11 empty] | Yes
Rebecca Gaither - SL | Thornton Fennell | PG County |  | CANCELED | [13 empty] | Yes
Joy Alorro - DV | Danny Dubois | Fairfax County | VA | N/A | applied | Approved Novec | Drop Box | in review
Elizabeth Mason - DV | Danny Dubois | Staunton County | VA | N/A | NA | Approved- Dominion | Drop Box
Clifford McQueen - GL | Volt (Ishmael) | PG County |  | APPROVED 5.13 | NA | Approved- Pepco | Drop Box | issued | Installation in Progress
Deborah Bailey - SN | Jedi | Baltimore County |  | N/A | NA | Approved-BGE | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Dawn Banks- SN | Inside Sales (Ishmael) | Charles County |  | N/A | NA | Approved - SMECO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Chikodili Ugokwe - SN | Thornton Fennell | PG County |  | N/A | NA | Approved- BGE | Drop Box | in review | Installation in Progress
Maximiliano Posada - GL | Ana Romero | Montgomery County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Conor P. Williams - CASH | Inside Sales | District of Columbia |  | N/A | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | Passed | Approved | Site Created |  | Done | Done |  |  |  | Done
Francisco Jacobo Sanchez - GL | Ana Romero | PG County |  | APPROVED 3.22 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | [9 empty] | Done
Dustin Schultz - GL | USA Solar Network | Calvert County |  | APPROVED 3.23 | NA | Conditionally Approved SMECO | Drop Box
Mary Ukwu - SL | Aaron Dawkins | PG County |  | APPROVED 4.1 | approved | Approved- BGE | Drop Box |  | Installation Completed | Passed | Applied | [7 empty] | Done
Liliane Batista - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 3.31 | NA | Approved - PEPCO | Drop Box | issued | Installation Completed | 2022-06-01 | [8 empty] | Done
Sharon McGee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.1 |  | Applied-Pepco | Drop Box | issued | Scheduled 5/30
Sandor Slager - CASH | Volt Solar (Brandon) | Distric of Columbia County |  | N/A | NA | Approved- PEPCO | Drop Box | issued | Installation in Progress
James D. Bryden - EZ | Inside sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - U anchor check
Anthony Field - DV | SkylightNRG | PG County |  | N/A | NA | Have Bill PEPCO | 200AMP | applied
Grace Brunner - CASH | Inside Sales | Distric of Columbia County |  | N/A | NA | Approved-PEPCO | Drop Box | issued | TBS - Roof repair pending
Jeremy Black - CASH | Inside Sales | Lycoming County |  | N/A | NA | Approved PPL | Drop Box | issued | TBS
Phil Nawrocki - CASH | Inside Sales | Allegheny County |  | N/A | NA | Approved DLC | Drop Box
Deborah Whitaker - GL | Jedi | Baltimore City |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Tod Harach - EZ | Inside Sales | Lancaster County |  | N/A | NA | Approved PPL | Drop Box
Guillermo Mendoza - GL | Raf Solar | Montgomery County |  | APPROVED 3.26 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Leonel Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.10 | NA | Approved REC | Drop Box | Applied-5/26
Renardo Williams - DV | Jedi | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Ronisha Dickerson - GL | Volt (Ishmael) | PG County |  | APPROVED 3.27 | approved | Conditional approved SMECO | Drop Box | issued | TBS |  |  | done
Jose Coreas - GL | Carlos Cueto | Baltimore County |  | APPROVED 3.27 | Cancelled by Carlos |  | ELD on Hold | [10 empty] | Yes
Peter Kurilla - GL | USA Solar Network | Montgomery County *PA* |  | APPROVED 4.11 | NA | Applied PECO | Drop Box
Tatiana McCook - GL | Volt Solar (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done |  |  |  | V.S
Rachelle Stephens - SL | Remesh Sartani | Charles County |  | APPROVED 4.20 | NA | Approved SMECOINT-08682 | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Catherine Heath - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | [8 empty] | V.S
De'Andre Sheppard - DV | Skylightnrg | Baltimore County |  | N/A | NA | BGE | Drop Box
Sandra Dieterle - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Marisol Muñoz - GL | Bianca del Castillo | City of Rockville |  | APPROVED 5.3 | NA | Approved-Pepco | Drop Box | issued | TBS
Donnie Waites - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.1 | NA | Approved-Pepco | Drop Box | issued
Faye Coles - DV | Skylightnrg | Anne Arundel County |  | N/A | approved | Approved-BGE | Drop Box | applied
Gerald Newsome - DV | Skylightnrg | Charles County |  | N/A | Approved | Approved -SMECO | Drop Box | issued
Queenie May Escubio - EZ | Inside sales | Prince william county |  | N/A | approved | Approved Dominion | Drop Box | Applied
Santosha Lee - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.27 | NA | Approved-BGE | Drop Box | issued | Installation Completed | [9 empty] | V.S
Jose Morales - GL | Marcelo Ortiz | Stafford County | VA | CANCELED | NA | Applied NNEC | Drop Box | [10 empty] | Yes
Robert & Suzette Kinstler - GL | USA Solar Network | Montgomery County*PA |  | APPROVED 4.1 | NA | Approved PECO | Drop Box | [10 empty] | Yes
Peter Hughes | Double Inside Sale |  |  |  |  | Applied Rappahannock | Drop Box | in revie
Terence Collins - GL | Skylightnrg | Baltimore County |  | APROVED 3.31 | NA |  | Canceled Dt:3/31/22 | [10 empty] | Yes
Dustin Blankenship - GL | USA Solar Network | Carroll County |  | APPROVED 3.31 | NA | Approved Potomac GEN-MD-8107 | Drop Box | in review
Jay Vodela - SN | Jonathan Ngo | Montgomery County |  | N/A | approved | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done |  |  |  |  | Done
Jaime Salazar - CASH | Inside Sales | Montgomery County |  | N/A | NA | Approved-Pepco | Drop Box | issued | Installation Completed |  |  | Done | [6 empty] | Done
Melanie Choh - GL | Volt (Ishmael) | PG County |  | APPROVED 3.31 | Approved | Approved-Pepco | Drop Box | issued | TBS
Dawn Peterson - GL | IDC | PG County |  | APPROVED 4.1 | approved | Approved-Pepco | Drop Box | issued | TBS |  |  | DONE
Kwame Gyamfi - SL | Derrol Mcclaren | Montgomery County |  | APPROVED 5.6 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Yvette Dowtin - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved |  |  | Done | DONE
Bianca Christie - SL | Derrol Mcclaren | Baltimore County |  | APPROVED 4.20 | NA | Approved -BGE | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Silvia Centeno - GL | "Rafael Cabello (Raf Solar )" | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Leroy Inabinett - SL | Aaron Dawkins | Baltimore City |  | CANCELEED | NA | Approved-BGE | Drop Box | In review | [9 empty] | Yes
Edgar Bonilla - GL | Marcelo Ortiz | PG County |  | APPROVED 5.2 | approved | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Marina del Carmen Bonilla - GL | Carlos Cueto | PG County |  | APPROVED 4.12 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | [9 empty] | Done
Reina Alfaro - GL | Marcelo Ortiz | Montgomery County |  | CANCELEED | NA | Approved-Pepco | Drop Box | applied | [9 empty] | Yes
Silvio Espinal - GL | Jorge Carias | Montgomery County |  | APPROVED 4.5 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Ana Majano - GL | Marcelo Ortiz | Frederick County |  | APPROVED 5.6 | NA | Applied REC | Drop Box
Silvia Centeno - GL | Raf Solar | PG County |  | APPROVED 4.12 | NA | APPROVED-PEPCO | Drop Box | applied | Installation in Progress
Carlos Hoschmin - GL | Raf Solar | Fairfax county | VA | CANCELED | cancel by SR |  | Canceled Email Dt:4/8/22 | [10 empty] | Yes
Colin Eckman - CASH | Inside Sales | Prince William County |  | N/A | approved | Approved dominion | Drop Box | Applied
Jonathan Ford - CASH | Inside Sales | Carrol County |  | N/A | NA | Applied-BGE | Drop Box
Rene Lemus - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | Done | Done |  |  | Done
Pierre Tekem Noumbi - DV | Skylightnrg | PG County |  | N/A | need action |  | Drop Box | issued
Jose de la Cruz Reyes - GL | Carlos Cueto | Frederick County |  | APPROVED 4.12 | Approved | Approved potomac | Drop Box | issued | TBS
Roger Yobani Diaz - GL | Bianca del Castillo | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Approved | Done |  | Done | DONE |  |  |  | Done
Jose Castillo - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 4.11 | approved | Approved Potomac | Drop Box | issued | Installation Completed | Passed | Applied | Done
Elizabeth Mason - DV | Inside Sales | (Chesterfield) | VA | N/A | approved | Applied Dominion | Drop Box | issued
Jose Perez - GL | Raf Solar | PG County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Installation Completed | Passed | Applied
Juan Villatoro - GL | Marcelo ortiz | Anne Arundel County |  | APPROVED 4.11 | NA | Approved-BGE | Drop Box | issued | Scheduled 5/23 |  |  | Done
Vinicia R Torres - GL | Ana Romero | PG County |  | APPROVED 4.12 | NA | Approved-BGE | Drop Box | issued | Installation Completed
Juan Soto - GL | Raf Solar | PG County |  | APPROVED 4.26 | NA | Applied-Pepco | Drop Box | in review
Nestor Tchinda - SL | Derrol Mcclaren | Montgomery County |  | ON HOLD UNTIL NTP |  | Have Bill BGE
Bernice Alston - GL | Thornton Fennell | PG County |  | APPROVED 4.11 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Josias Tekle - DV | Skylightnrg | city of hagerstown |  | N/A | approved | Approved potomac | Drop Box | applied
Tim Johnson - DV | Skylightnrg | St. Mary's County |  | N/A | NA | Approved SMECO | Drop Box | issued | TBS
Theresa Terry - GL | Volt Solar (Freddye) | PG County |  | CANCELED | need info | Have Bill SMECO | 200AMP | applied | [9 empty] | Yes
Louis Drury - GL | Elijah Sutton | Calvert County |  | APPROVED 4.12 | NA | Approved SMECO | Drop Box
Hakeem Ayodeji - SN | Samuel Edwards | Charles County |  | N/A | need info | Conditionally Approved Smeco | Drop Box | issued
Kenisha Jefferson - SN | Theodore Brown | PG County |  | N/A | approved | Approved-PEPCO | Drop Box | issued
Rosa Garcia - GL | Carlos Cueto | PG County |  | APPROVED 4.13 | NA | Approved-BGE | Drop Box | issued | Installation in Progress
Abdullah Amin - GL | Volt (Thomas) | Distric of Columbia County |  | APPROVED 4.14 | NA | Approved-Pepco | Drop Box | issued | Scheduled 5/30
Demetri Kappatos - SL | Charles Carufel | Loudoun County | VA | IN REVIEW | IN REVIEW |  | Drop Box
Teodoro Carranza - GL | Ana Romero | Montgomery County |  | APPROVED 4.13 | NA | Approved-Pepco | Drop Box | issued | Installation Completed | Passed | Applied | Done
Vicki Powell - DV | Skylightnrg | Cecil County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Kenneth Pilpel - DV | Skylightnrg | Montgomery County |  | N/A | Approved | Approved-Potomac | Drop Box | issued | TBS
Jose Resendiz - DV | Skylightnrg | Baltimore City |  | N/A | NA | Approved-BGE | Drop Box | In review
Yessenia Marilu Cruz - GL | Carlos Cueto | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Lydia Hagos - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  |  | ELD on Hold | [10 empty] | Yes
Latanya Cannady - GL | IDC | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Austin Johnson - GL | Volt Solar (Freddye) | PG County |  | APPROVED 4.19 | approved | Approved SMECO | Drop Box | issued |  |  |  | Site created
Kirk Ramirez - EZ | Tim Clark | PG County |  | N/A | applied | Approved-Pepco | Drop Box | in review
Derell Kennedo - EZ | Peter kyke | Distric of Columbia County |  | N/A | NA | Approved-Pepco | Drop Box | in review
Ramon Eclavea - DV | Danny Dubois | Prince William County |  | N/A | applied | Approved Novec | Drop Box | Applied
Ian Roach - SL | Aaron Dawkins | PG County |  | APPROVED 4.19 | NA | Approved-Pepco | Drop Box | in review | TBS
Sade Brown - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued
Jason Coy - CASH | Tim Clark | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | issued | TBS
William Burgess - CASH | Tim Clark | Arlington County | VA | N/A | NA | Approved Dominion | Drop Box | issued
Paul Leger - DV | Elijah Sutton | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Park - DV | Havar Espedal | Distric of Columbia County |  | N/A | already approved by HAVAR | Approved-Pepco | Drop Box | in review
John Greesh - DV | Havar Espedal | Distric of Columbia County |  | N/A | need info | Approved-Pepco | Drop Box | in review
Matthew Lewis - DV | Derrol Mcclaren | PG County |  | CANCELED | NA | Applied-Pepco | Drop Box | in review | [9 empty] | Yes
Marion Bedford - GL | Volt Solar (Freddye) | PG County |  | CANCELED |  | Cancel by Dealer | Designed But Canceled | applied | [9 empty] | Yes
Delcita Lemus - GL | Raf Solar | PG County |  | APPROVED 4.20 | NA | Approved-Pepco | Drop Box | in review
Maria Consuelo Baires - GL | Thirza Iglesias | Loudorn County | VA | CANCELED |  | Project Cancelled | Drop Box | [10 empty] | Yes
Richard Vasquez - GL | Marcelo Ortiz | Fairfax County | VA | APPROVED 4.25 | NA | Applied Dominion | Drop Box | issued
Abdi Mohamed - DV | Derrol Mcclaren | Montgomery County |  | N/A | applied | Approved Potomac | Drop Box | issued
Kuega Ekue - SL | Dawit Abraham | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daysi Martinez - GL | Bianca del Castillo | city of frederick |  | APPROVED 4.25 | NA | Approved Potomac | Drop Box | in review
Rotimi Shittu - SL | Thornton Fennell | PG County |  | APPROVED 4.25 | NA | Approved-Pepco | Drop Box | in review | TBS
Daniel Andres Yanez - GL | Carlos Cueto | Frederick County |  | APPROVED 4.25 | applied | Applied SVEC | Drop Box
James Arthur - SL | Jonathan NGO | Charles County |  | APPROVED 4.25 | approved | Conditionally Approved SMECO | Drop Box | issued
Andrian Cruz - DV | Derrol Mcclaren | Montgomery County |  | N/A | approved | Approved Potomac | Drop Box | issued | TBS
TRAVIS MELSON - SN | USA Solar Network | Petersburg City | VA | N/A | NA | Have Bill Dominion HOI | On Hold
Matthew Dreitlein - EZ | Peter Kyke | Fairfax County | VA | N/A | applied | Approved Dominion | Drop Box | issued
Melat & Fanual Dawit - EZ | Inside Sales | Distric of Columbia County |  | N/A | NA | Applied-Pepco | Drop Box | in review
David Brunco - CASH | Peter Kyke | Butler County |  | N/A | NA | Approved Penn Power | Drop Box
Ethan Pacifico - DV | Danny Dubois | Town of Herndon | VA | N/A | Approved | Approved Dominion | Drop Box | Issued
Fermin Kelly - SL | Remesh Sertani | Wicomico County |  | APPROVED 4.25 | NA | Approved-Pepco(Delmarva Power) | Drop Box | applied
Mike Mendley - DV | Skylighting | Montgomery County |  | N/A | no need for approval | Approved-Pepco | Drop Box | Issued
Adolfo Mata Garcia - GL | Carlos Cueto | PG County |  | CANCELED | NA | Applied-Pepco(Project Withdrawn) | Drop Box | applied | [9 empty] | Yes
Dawn Frisby - GL | Skylightnrg | PG County |  | ON HOLD UNTIL NTP | approved | Approved-Pepco | Drop Box | in review
Michael Chernau - CASH | Tim Clark | Henrico County | VA |  | NA | Applied- Dominion | Drop Box | in review
Douglas Ross - GL | Skylighting | Montgomery County |  | APPROVED 5.19 | NA | Applied-Pepco | Drop Box
Melvin Hernandez - GL | Marcelo Ortiz | Montgomery County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop Box | issued | TBS
James M. McDermott - SL | Charles Carufel | Loudorn County | VA | APPROVED 5.4 | Approved | Approved Dominion | Drop Box | in review | TBS
Doris Scott - GL | Mark Davis | PG County |  | CANCELED | need info | f | ELD on Hold | applied | [9 empty] | Yes
Nicholas Hinko - SL | Charles Carufel | Loudoun County | VA | APPROVED 5.5 | Approved | conditional /Approved SMECO | Drop Box | in review | TBS
Karima Ali - DV | Skylighting | Loudorn County | VA | N/A | applied | Applied - Dominion | Drop Box | in review
John Whelan - DV | Jedi | Frederick County |  | N/A | applied | Approved-Potomac | Drop Box | issued
Michael Sparks - DV | Jedi | Charles County |  | N/A | NA | approved-Smeco | Drop Box | issued
Travis Melson - GL | USA Solar Network | Chesterfield County | VA | ON HOLD UNTIL NTP | NA | Applied- Dominion | Drop Box
Candance Watson - SN | Greg Jonhson - BBS | Chesterfield County | VA | N/A | NA | Approved Dominion | Drop Box | issued
GARFIELD KELLIER - SN | Jonathan NGO | PG |  | N/A | applied | Applied-Pepco | Drop Box | in review
Thomas Hayhurst - DV | Skylightngr | Garrett County |  | N/A | to follow | have UB | 200 Amp/On Hold
Carlos M. Claros - GL | Marcelo Ortiz | Prince William County |  | APPROVED 5.2 | approved | Approved Dominion | Drop Box | Applied
Mary Borders - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | Applied
Carolina Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.2 | NA | Applied-Pepco | Drop Box | in review
Tabitha Demaio - SL | Derrol Mcclaren | Charles County |  | ON HOLD UNTIL NTP | NA | need bill | 200 Amp/On Hold
Richard Cook/Betty Siu - DV | Elijah Sutton | Charles County |  | N/A | NA | conditional /Approved SMECO | Drop Box | issued
Jose Guzman - SN | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Approved- Dominion | Drop Box | Applied | [9 empty] | Yes
Giles Nathaniel Cooke Jr - GL | Thornton Fennell | PG |  | APPROVED 5.20 | NA | Approved-PEPCO | Drop Box | in review
Jose Arbaiza - GL | Carlos cueto | Montgomery County |  | APPROVED 5.10 | NA | Approved-Pepco | Drop Box | issued | Installation in Progress
Marina I. Tejada - DV | Ana Romero | PG |  | APPROVED 5.7 | NA | Approved-Pepco | Drop Box | in review
Thomas Broach - GL ( Ground Mount) | SolarStrong | Fayette County |  | APPROVED 5.5 | NA | applied-Appalachian power | Drop Box
Regan Crump - CASH | Inside Sales | Montgomery County |  | N/A | Approved | Applied Potomac | Drop Box | issued
Richard Fecher - CASH | Peter Kyle | Loudorn County | VA | N/A | need action | Applied dominion | Dropbox
Sandra Schultz - GL | Mark Davis |  |  | CANCELED | [13 empty] | Yes
Fidel Santos - GL | Raf Solar | Montgomery County |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | applied
Lyle Craddock - GL | True Energy (David Twitty) | Boone County |  | APPROVED 5.5 | NA | Applied Applachian Power | Drop Box
Tamara Perez - GL | IDC | PG |  | APPROVED 5.5 | NA | Approved-Pepco | Drop Box | in review
Crystal Sprowls - EZ | Inside Sales | Allegheny County |  | N/A | need info | Have Dequesne Light | 200 Amp/On Hold
Vincent Lombardi - GL | True Energy (David Twitty) | Tucker County |  | APPROVED 5.23 | NA | Have Bill-MonPower | 200 Amp
Blake Bozeman - SN | Inside Sales | District of Columbia |  | N/A | NA | Approved-Pepco | Drop box | in review
Celia Delara - SN | Jonathan NGO | Hardford County |  | N/A | NA | Applied-BGE | Drop box | in review
Kemberly Gutierrez - SN | Thornton Fennell | PG County |  | N/A | NA | Applied-Pepco | Drop Box
Anthony Turner 1 - DV | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop box
Anthony Turner 2 - GL | Skylightnrg | Baltimore County |  | ON HOLD UNTIL NTP | NA | BGE | ELD On Hold/MSP Pics Needed
Anselmo Guzman - GL | Raf Solar | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Renett Little - GL | IDC | PG County |  | APPROVED 5.10 | Approved | Approved-Pepco | Drop box | in review
Auildo Kelly Azor - SL | Remesh Sertani | Wicomico County |  | CANCELED | NA | Approved-Pepco(Delmarva Power) | Drop box | [10 empty] | Yes
Lee Webb - GL | True Energy (David Twitty) | Fayette County |  | APPROVED 5.10 | NA | Have Bill-Appalachian Power | Drop box |  | Notes: Take Two 20 and Two 15 Single Pole QO Tandum breaker
Glenn Allander - GL | Daniel Gibson | Cumberland County |  | APPROVED 5.10 | NA | Applied PPL | Drop box
Jacob Richmond- EZ | Sam Albert | Wythe County |  | N/A | need info | on Hold | Drop box
Sandra Gascon-Gracia - CASH | Sam Albert | Cumberland County |  | N/A | need info | have bill PPL | 200 Amp (In Progress)
Brandy Shamrock - DV | Skylightnrg | Franklin City | VA | N/A | NA | Approved dominion | Drop box
Ivy Freeman - SL | Charles Carufel | Cumberland County |  | APPROVED 5.11 | applied | Applied Novec | Drop Box
Mariam Menkir - DV | Derrol Mcclaren | Charles County |  | N/A | in review | Approved SMECO | Drop Box | issued
Vivian Segovia - GL | Thirza Iglesias | Frederick County |  | CANCELED | NA | Approved-REC | Drop Box | [10 empty] | Yes
Frank Mestecky - GL | USA Solar Network | Pike County |  | APPROVED 5.19 | applied | Applied Met-Ed | Drop Box
MANUEL GUTIERREZ - SN | Thornton Fennell | PG County |  | N/A | NA | Approved-BGE | Drop Box | in review
Olivier Komeka - DV | Skylighting | PG County |  | N/A | to follow | Need Bill | Drop Box | in review
Joseph Flora - GL | True Energy (David Twitty) | Cabell County |  | APPROVED 5.11 | NA | Metert Number require | Drop Box
Shenee Turner - GL | IDC | PG County |  | APPROVED 5.11 | applied | Approved-Pepco | Drop box | in review
Ramon Campos - GL | Carlos cueto | PG County |  | APPROVED 5.11 | NA | Approved-Pepco | Drop box | in review
Richard Thornburgh - CASH | Michael Reid | Montgomery County |  | N/A | NA | Applied-Pepco | Drop box | Applied
Edward Holman - DV | Skylighting | Chesterfield | VA | N/A | NA | need HOI | Drop box | [10 empty] | Yes
Maribel Giovanna Sanchez - GL | Carlos cueto | PG County |  | APPROVED 5.12 | NA | Approved-Pepco | Drop box | in review
Philippa & Danielle Durham - CASH | Inside Sales | Caroline County |  | N/A | need info | Conditional Approved-Choptank | Drop Box | applied
Kenia Benitez - GL | Marcelo Ortiz | Harrisonburg City | VA | CANCELED | NA | Applied SVEC | Drop Box | [10 empty] | Yes
Luis Perez - EZ | Peter Kyle | Spotsylvania County | VA | N/A | applied | Approved REC | Drop Box
Anthony Olaiya Oni - GL | Thornton Fennell | Baltimore County |  | ON HOLD UNTIL NTP | NA | Approved-BGE | Drop Box
Thai-Anh Perry - SL | Charles Carufel | Prince William County |  | STIP - OWNERSHIP | in review | Approved-Novec | Drop Box
MARLYN PIPER WILLIAMS - SN | Samuel Edwards | PG County |  | N/A | need info | Applied-Pepco | Drop Box | in review
Edward Miller - DV | Skylightnrg | Howard County |  | N/A | NA | Approved-BGE | Drop Box | Issued | TBS
Karen Collins - GL | Heath Dewalt (Nitro) | Charlottesville City | VA | ON HOLD UNTIL NTP | need info
Susan Silman - GL | True Energy (David Twitty) | Kanawha County |  | APPROVED 5.16 | NA | Applied-Appalachian | Drop Box
Blanca R Guzman Escobar - GL | Ana Romero | Montgomery County |  | APPROVED 5.19 | NA | Approved-Pepco | Drop Box | issued | TBS
Benjamin Bacon - DV | Skylighting | Frederick County |  | N/A | approved | Approved Potomac | Drop Box | issued
Jamie Summers - GL | Strong Solar | Kanawha County |  | APPROVED 5.18 | NA | Applied-Appalachian Power | Drop Box
Ravinder Mathaudu - SN | Samuel Edwards | Montgomery County |  | N/A | need info | need bill
Everth Alvarado - DV | Danny Dubois | Manassas City | VA | N/A | need info | Need Info | Drop Box | [10 empty] | Yes
Kuele Ndingsa - GL | Mark Davis | PG County |  | APPROVED 5.27 | NA | Approved-BGE | Drop Box | in review
Jeff Boggs - GL | Strong Solar | Kanawha County |  | APPROVED 5.16 | NA | Applied-Apalachian Power | Drop Box
Joseph Cotterino - GL | Quativa | Carbon County |  | STIP - OWNERSHIP | NA | PPL | Drop Box
Nang and Hong Huynh - DV | Danny Dubois | Fairfax County | VA | N/A | NA | Applied Dominion | Drop Box | issued
Isaias Bustamante - GL | Marcelo Ortiz | Prince William County |  | CANCELED | NA | Applied Dominion | Drop Box | [10 empty] | Yes
Edith S Gonzalez Mejia - GL | Carlos cueto | Anne Arundel County |  | APPROVED 6.3 | applied | Approved-BGE | Drop Box | applied
Georgia Thomas - GL | Aaron Dawkins | PG County |  | APPROVED 5.119 | NA | Approved-Pepco | Drop Box | in review
Gabriel Rosenberg - SL | Charles Carufel | Fairfax County | VA | APPROVED 5.19 | NA | need correct HOI | Drop Box | applied
Michael Newkirk Jr - SN | Ric Peters | Anne Arundel County |  |  | NA | Approved-BGE | Drop Box | applied
JACQUELIN MARTINEZ - SN | Ric Peters | Anne Arundel County |  | N/A | NA | Approved-BGE | Drop Box | applied
Carol Jackson - DV | Skylighting | Charles County |  | ON HOLD UNTIL NTP | to follow | Approved Smeco | Drop Box | applied
Wubishet Yizengaw - DV | Skylighting | Montgomery County |  | N/A | NA | Applied-Pepco | Drop Box | issued
Florinda Escobar - GL | Raf Solar | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Janice Walters - GL | Thornton Fennell | PG County |  | APPROVED 5.20 | NA | Applied-Pepco | Drop Box | in review
Rosalba Ayala Magana - GL | Thirza Iglesias | Frederick County |  | NEED CORRECTION/ADDRESS | need action | Applied-REC | Drop Box
Yessenia Rios rubio - SL | Dawit Abraham | PG County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
David Poindexter - SL | Malik Walker | PG County |  | APPROVED 5.20 | need action | Applied-Pepco | Drop Box | applied
Kathy Rivera - GL | Quativa | Chesterfield County | VA | APPROVED 5.20 | NA | Need HOI | Drop Box | applied
Scott Seladoki - GL | Quativa | Ohio County |  | APPROVED 5.20 | NA | Applied Appalachian Power | Drop Box
Rhys Buntua - CASH | Peter Kyle | Fairfax County | VA | N/A | NA | Applied Dominion | Drop Box | applied
Krystle Gray - GL | Ismael | Anne Arundel County |  | APPROVED 5.28 | NA | Approved-BGE | Drop Box | applied
Abilio Hernandez - GL | Marcelo Ortiz | PG County |  | APPROVED 5.23 | NA | Applied-Pepco | Drop Box | in review
Syed Abbas - CASH | Theodore Brown | Howard County |  | N/A | applied | Approved-BGE | Drop Box | Issued
María Angélica Ventura Chavez - DV | Bianca del Castillo | Montgomery County/ City of Gaithsburg/City of rockville |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box
David Bentley - GL | True Energy (David Twitty) | Clay County |  | CANCELED | [13 empty] | Yes
Jai Patel - DV | Skylightngr | Harford County |  | APPROVED 5.24 | applied | Applied-BGE | Drop Box
Toi Wiseman - GL | Ismael | PG County |  | APPROVED 5.24 | NA | Applied-Pepco | Drop Box | in review
Santos Menjivar - DV | Bianca del Castillo | Frederick County |  | N/A | NA | Approved Potomac | Drop Box
Neil de Castro - DV | Danny Dubois | Virginia Beach City | VA | ON HOLD UNTIL NTP | NA | Applied-Dominion | Drop Box
Shahjahan Molla - CASH | Peter kyle | Cumberland County |  | N/A | NA | Approved PPL | Drop Box
Patrick Norman - CASH | John Lee | Arlington County | VA | N/A | NA | need new bill | Drop Box | issued
Christina Sanchez - SL | Eric Strouse | Raleigh County |  | STIP - CUSTOMER NEEDS TO CALL SL | NA | applied-Apalachian Power | Drop Box
Eduviges Zavala - DV | Bianca del Castillo | Montgomery County |  | STIP - ID | NA | Applied-Pepco | Drop Box
Lilian Maribel Martinez Orellana - DV | Bianca del Castillo | Montgomery County |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | applied
Jaime Cordero - GL | Marcelo ortiz | Montgomery County |  | APPROVED 5.25 | applied | Applied-Pepco | Drop Box | applied
Ebony Shirley - GL | IDC (Ishmael) | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | in review
Robert Feeman - GL | Quativa | Cumberland County |  | APPROVED 5.25 | need action | Have bill PPL | Drop Box
Rene Smith/Patrick Ward - DV | Skylighting | Frederick County |  | CANCELED | NA | Have Bill-Potomac | [11 empty] | YES
David J. Poindexter III - SL | Malik Walker | PG County |  | APPROVED 5.25 | NA |  | 200 Amp/In Progress | applied
Craig Vaughan - CASH | SolarSurge | Chesterfield County | VA | N/A | NA |  | Drop Box | in review
Benedicta Njoku - GL | Dawit Abraham | District of Columbia |  | APPROVED 5.27 | NA | Applied-Pepco | Drop Box | in review
Anthony Aponte - GL | Quativa | Spotsylvania County | VA | APPROVED 5.27 | NA | Have bill & HOI | 200 Amp/Sunova Design
Patrick German - CASH | Quativa | Charles County |  | N/A | NA | Have bill SMECO | 200 Amp/Sunova Design
John Kolber - CASH | Inside Sales | Cumberland County |  | N/A | need info |  | ELD On Hold/MSP Pics Needed
Matthew Herbaugh - CASH | Inside Sales | Isle of Wight County | VA | N/A | need info |  | Drop Box | in review
Boleslaw Stefanski - CASH | Inside Sales | Pike County |  | N/A | need action |  | Dropbox
Nick Vattimo - CASH | Inside Sales | Frederick County |  | N/A | need info |  | In Review
Emundo Trivelli - SL | Inside Sales | Prince William County |  | APPROVED 6.1 | need info | Applied Dominion | Drop Box
Jonathan Araya - CASH | Inside Sales | Loudoun County | VA | N/A | need info | Apllied Dominion | Drop Box
Raed Jarrar - EZ | Inside Sales | District of Columbia |  | N/A | need info | Pepco | Sunnova Design | applied
Melanie Johnson - SL | Aaron Dawkins | PG County |  | APPROVED 5.31 | applied | Applied-Pepco | Drop Box | applied
Cheryl Baker - SL | Eric Strouse | Mineral County |  | IN REVIEW | NA | Applied Potomac | Drop Box
Rosalynn Asamoah - DV | Skylighting | Montgomery County |  | STIP - ACH | need action | Have Bill Potomac | Inverter Details N/A
Sergio Martinez - DV | Skylighting | Baltimore City |  | STIP - OWNERSHIP | NA | Applied-BGE | Drop Box | Applied
Kevin Kidwell - CASH | Quativa | Hampshire County |  | N/A | NA |  | Inverter Details N/A
Patrick Primm - GL | Quativa | ClearField County |  | APPROVED 5.31 | NA | Have Bill-Potomac | ELD On Hold/MSP Pics Needed
Cyrus Hormozi - GL | Skylighting | Washington County |  | APPROVED 5.31 | approved | Approved Potomac | Drop Box
Socoya Gorham - GL | Brandon Hyman | District of Columbia |  | IN REVIEW | NA | Applied-Pepco | Drop Box | applied
Sean Hodgins - GL | Skylighting | Baltimore City |  | APPROVED 6.1 | NA | Applied-BGE | Drop Box
Liz Ehrich - CASH | John Lee (Inside Sales) | Stafford County | VA | N/A | need action | Applied -Dominion | Drop Box
Harrison Parson - CASH | Tim Clark (Inside Sales) | Susquehanna County |  | N/A | NA | Have Bill-Penelec | In Progress/Waiting fo Client Consultation
Rene Humberto Suarez- GL | Ana Romero | PG County |  | APPROVED 6.2 | NA | Applied-BGE | Dropbox | applied
Adrian Herring - SL | Tim Clark (Inside Sales) | Allegheny County |  |  | need info |  | Everbright Design N/A
Carol Smith - SL | Solar Strong | Taylor County |  | APPROVED 6.2 | NA |  | 200 amp/Everbright Design
Ramiro Moya - GL | Carlos cueto | Montgomery County |  | APPROVED 6.3 | need action | Applied Potomac | Drop Box | applied
Edgar Sorto - GL | Raf Solar | Winchester City | VA | APPROVED 6.3 | applied |  | Drop Box
Mayor William Sanders III - 1 |  |  |  |  | need info
Mayor William Sanders III - 2 |  |  |  |  | need info
Olufemi Oluwatobi Ikusika - DV | Skylighting | Baltimore County |  | APPROVED 6.6 | need action | Applied-BGE | Dropbox
Frank Trujillo - CASH | Peter Kyle ( Inside sales) | Prince William County |  | N/A | applied | Applied -Dominion | Dropbox
Jason Chandler - GL | John Lee (Inside Sales) | District of Columbia |  | STIP | NA | Approved-Pepco | Dropbox | applied
Linda and James Dwyer - CASH | John Lee (Inside Sales) | PG County |  | N/A | need info |  | Dropbox | applied
James Rodgers - GL | Aaron Dawkins | District of Columbia |  | APPROVED 6.7 | NA | Applied-Pepco | Dropbox | applied
Omotayo Ogundana - GL | Thornton Fennell | PG County |  | STIP - ID | need info |  | ELD on Hold | applied
Timothy Dixon - SL | John Lee (Inside Sales) | Howard County |  | NEED CORRECTION | need action | Have Bill-BGE | Sunnova Design//200 amp/Waiting fo Client Consultation
Karen Ireland - CASH | John Lee (Inside Sales) | Montgomery County |  | N/A | NA | Applied-Pepco | Dropbox | applied
James Ortmann | John Lee (Inside Sales) | PG County |  |  | NA | Applied-Pepco | Dropbox | applied
Christopher Arzadon - SL | John Lee (Inside Sales) | Prince William County |  | APPROVED 6.8 | need action | Have Bill-Dominion | Dropbox
Olawale Tolulope Ayorinde - SN | IDC (Ishmael) | PG County |  | N/A | need action | Have Bill-Pepco | 200 amp/In progress | applied
Emma Davenport - DV | Skylighting | Baltimore County |  | APPROVED 6.8 | NA | Have Bill-BGE | Site Visit Requested
Matthew Beyers - DV | Skylighting | Frederick County |  | STIP - ACH | need action | Applied Potomac | Dropbox
Christopher Means - SL | Eric Strouse | Kanawha County |  | APPROVED 6.8 | NA | Applied Appalachian | Dropbox
Charles Messerschmidt - GL | Ric Peters | Anne Arundel County |  | APPROVED 6.9 | NA | Applied-BGE | Dropbox
Heather Levander - | Quativa | Fayette County |  |  |  |  | Everbright Design N/A
Harold Gerhart - GL | Quativa | Cumberland County |  | CHANGE ORDER? | NA | Have Bill PPL | Inverter Details N/A
Justin Strickland - GL | Quativa | Cumberland County |  | APPROVED 6.9 | NA | Have Bill-PPL | Everbright Design N/A
Berta Lidia - GL | Marcelo Ortiz | Frederick county |  | APPROVED 6.9 | NA | Have bill potomac
Kenneth Blankenship - SL | Eric Strouse | Nicholas county |  | STIP - OWNERSHIP | NA |  | In Progress
Keith Scarsdale - SL | Mark Davis | Culpeper County |  | IN REVIEW | NA
Sean Magee - CASH | Cinthia Rivera | Loudoun county | VA | N/A | NA | Have bill dominion | Drop Box
Todd Benbow - DV | SkylightNGR | Charlotte County | VA | IN REVIEW | NA |  | ELD On Hold/MSP Pics Needed
Jlicery Diaz - SL | Eric Strouse | Kanawha County |  | STIP - OWNERSHIP | NA | Have Bill Appalachian AND hoi | drop Box
Austin Snyder - GL | Voltaic (Freddye Jackson) | Lehigh County |  | IN REVIEW |  | PPL | Dropbox
Luis Rosas - GL | Justin Hall | PG county |  | IN REVIEW |  |  | ELD On Hold/MSP Pics Needed
Fatoumatta Bah - DV | SkylightNGR | Frederick county |  | IN REVIEW | need action | Have bill potomac | ELD On Hold/MSP Pics Needed
Jose Martinez - GL | Marcelo Ortiz | Montgomery County |  | IN REVIEW |  |  | In Progress